## Sheet1
Project ID | Project Description | Contract ID | Contract Description | WBS | WBS Description | Activity ID | Activity Description | Currency | Vendor | Name | Period | Year | Timestamp | % Accumulative Prog. | Price / Activity | Current Period Accumulation | Last Period Accumulation | PO Progress Price | PO Sequence | PO Number | PO Value
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.1.1.1 | ECC_Steel Pile With 609 mm Diameter (Thickness 12 mm) - Gas Engine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.731 | 7660800000 | 5600044800 | 5600044800 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.1.1 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 559249653 | 559249653 | 559249653 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JY | Construction - PILING WORKS | ECC.1.11.2.2.1 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Administration Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167774896 | 167774896 | 167774896 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.3.1 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Central Control Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167774896 | 167774896 | 167774896 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.4.1 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - HSD Storage And Facility | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 838874479 | 838874479 | 838874479 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.4.2 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Service And Fire Water Storage Tank Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.0703 | 838874479 | 58972876 | 58972876 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.4.3 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Radiator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 279624826 | 279624826 | 279624826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.4.4 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Lube Oil Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.12 | 838874479 | 100664937 | 100664937 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.JY | Construction - PILING WORKS | ECC.1.11.2.4.5 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Emergency Diesel Generator (EDG) Including HSD Fu | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 279624826 | 279624826 | 279624826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JY | Construction - PILING WORKS | ECC.1.11.2.5.1 | ECC_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Plant Water Facilities | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 279624826 | 279624826 | 279624826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.1 | ECC_Testing & Start Up - Mechanical Completion | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.28 | 560.98 | 157.07 | 0 | 157.07 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.10 | ECC_Testing & Start Up - Emmission Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8414.9 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.11 | ECC_Testing & Start Up - Performance Guarantee Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1121.98 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.2 | ECC_Testing & Start Up - First Backfeeding | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 560.98 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.3 | ECC_Testing & Start Up - System Commissioning Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3365.95 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.4 | ECC_Testing & Start Up - Back Feeding | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3365.95 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.5 | ECC_Testing & Start Up - First Sycnchronization | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 560.98 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.6 | ECC_Testing & Start Up - Sycnchronization | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8414.9 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.7 | ECC_Testing & Start Up - Power Plant Capacity Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8414.9 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.8 | ECC_Testing & Start Up - Load Rejection Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1682.97 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.2.A.9 | ECC_Testing & Start Up - Realibity Run Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8414.9 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.1 | ECC_Power Generation Unit - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15707.83 | 15707.83 | 0 | 15707.83 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.2 | ECC_Power Generation Unit - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 7853.92 | 4712.35 | 0 | 4712.35 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.3 | ECC_Power Generation Unit - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.2 | 7853.92 | 1570.78 | 0 | 1570.78 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.4 | ECC_Power Generation Unit - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.25 | 11780.87 | 2945.22 | 0 | 2945.22 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.5 | ECC_Power Generation Unit - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 11780.87 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.6 | ECC_Power Generation Unit - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 11780.87 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.1.7 | ECC_Power Generation Unit - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 11780.87 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.10.1 | ECC_Complete 20/70/150 KV Substation Equipment - Testing of 20/70/150 kV Substation equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 11780.87 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.1 | ECC_Fuel Supply System - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11780.87 | 11780.87 | 5890.44 | 5890.43 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.2 | ECC_Fuel Supply System - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 3926.96 | 1963.48 | 1963.48 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.3 | ECC_Fuel Supply System - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.2 | 3926.96 | 785.39 | 785.39 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.4 | ECC_Fuel Supply System - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 7853.92 | 3926.96 | 3490.28 | 436.68 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.5 | ECC_Fuel Supply System - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.6 | ECC_Fuel Supply System - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 7853.92 | 3926.96 | 0 | 3926.96 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.2.7 | ECC_Fuel Supply System - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 7853.92 | 3926.96 | 0 | 3926.96 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.1 | ECC_Waste Water Collection And Treatment System - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11780.87 | 11780.87 | 0 | 11780.87 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.2 | ECC_Waste Water Collection And Treatment System - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 3926.96 | 1963.48 | 0 | 1963.48 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.3 | ECC_Waste Water Collection And Treatment System - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3926.96 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.4 | ECC_Waste Water Collection And Treatment System - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.5 | ECC_Waste Water Collection And Treatment System - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.6 | ECC_Waste Water Collection And Treatment System - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.3.7 | ECC_Waste Water Collection And Treatment System - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.1 | ECC_Compressed Air System - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7853.92 | 7853.92 | 3926.96 | 3926.96 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.2 | ECC_Compressed Air System - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 2804.97 | 2243.98 | 1402.49 | 841.49 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.3 | ECC_Compressed Air System - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 2804.97 | 1402.49 | 1402.49 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.4 | ECC_Compressed Air System - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3926.96 | 3141.57 | 3141.57 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.5 | ECC_Compressed Air System - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3926.96 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.6 | ECC_Compressed Air System - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3926.96 | 3141.57 | 0 | 3141.57 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.4.7 | ECC_Compressed Air System - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3926.96 | 3141.57 | 0 | 3141.57 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.1 | ECC_Water Supply And Treatment System - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11780.87 | 11780.87 | 0 | 11780.87 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.2 | ECC_Water Supply And Treatment System - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 3926.96 | 1963.48 | 0 | 1963.48 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.3 | ECC_Water Supply And Treatment System - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3926.96 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.4 | ECC_Water Supply And Treatment System - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.5 | ECC_Water Supply And Treatment System - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.6 | ECC_Water Supply And Treatment System - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.5.7 | ECC_Water Supply And Treatment System - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.1 | ECC_Fire Protection System - Piping Hydrotest | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11780.87 | 9424.7 | 0 | 9424.7 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.2 | ECC_Fire Protection System - Piping Flushing & Blowing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.4 | 3926.96 | 1570.78 | 0 | 1570.78 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.3 | ECC_Fire Protection System - Piping Reinstatement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 3926.96 | 1963.48 | 0 | 1963.48 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.4 | ECC_Fire Protection System - Motor & Mechanical Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.5 | ECC_Fire Protection System - Instrumentation Calibration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.6 | ECC_Fire Protection System - Loop Check | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.6.7 | ECC_Fire Protection System - Function Test | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.7.1 | ECC_Distributed Digital Control System And PLC Control System - Function Test for PLC system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.8.1 | ECC_Complete Plant Electrical Equipment - Testing of EDG/ black start up | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.8.2 | ECC_Complete Plant Electrical Equipment - Testing of communication equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.8.3 | ECC_Complete Plant Electrical Equipment - Function test of lighting system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 7853.92 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1O.EZ | Construction - COMMISSIONING WORKS | ECC.A.9.1 | ECC_Complete Power Transformers - Testing of Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.25 | 7853.92 | 1963.48 | 0 | 1963.48 | 1 | 3500235947 | 92737.01
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.1.1.1 | ECC_Land Survey Work - Topographical Survey Execution | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19964157 | 19964157 | 19964157 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.1.1.2 | ECC_Land Survey Work - Benchmarks Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1246171 | 1246171 | 1246171 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.1.1.3 | ECC_Land Survey Work - Benchmark Verification during Site Hand - Over | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9969368 | 9969368 | 9969368 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.1.1.4 | ECC_Land Survey Work - Topography Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12946096 | 12946096 | 12946096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.1 | ECC_Soil Investigation Work - Deep Boring (Incl. setup & moving of Drilling rig) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 107170702 | 107170702 | 107170702 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.10 | ECC_Soil Investigation Work - Down Hole Soil Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37385128 | 37385128 | 37385128 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.2 | ECC_Soil Investigation Work - SPT every 1.5 m depth | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24861110 | 24861110 | 24861110 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.3 | ECC_Soil Investigation Work - Undisturbed Soil Sampling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7975494 | 7975494 | 7975494 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.4 | ECC_Soil Investigation Work - DCPT 10Ton capacity (Incl. Setup & moving of DCPT) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7477026 | 7477026 | 7477026 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.5 | ECC_Soil Investigation Work - Borrow Pit Sampling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41123641 | 41123641 | 41123641 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.6 | ECC_Soil Investigation Work - Soil Resistivity | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12461709 | 12461709 | 12461709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.7 | ECC_Soil Investigation Work - Insitu permeabilitas | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6230855 | 6230855 | 6230855 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.8 | ECC_Soil Investigation Work - Sample Transportation from Site to Lab | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5981621 | 5981621 | 5981621 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.1.9 | ECC_Soil Investigation Work - Hand Boring | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19938735 | 19938735 | 19938735 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.1 | ECC_Soil Investigation Work - Visual and Laboratory Classification of Soils | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2791423 | 2791423 | 2791423 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.10 | ECC_Soil Investigation Work - CD Triaxial Compression Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13957115 | 13957115 | 13957115 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.11 | ECC_Soil Investigation Work - CU Triaxial Compression Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27914229 | 27914229 | 27914229 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.12 | ECC_Soil Investigation Work - CBR (California Bearing Ratio) Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5607769 | 5607769 | 5607769 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.13 | ECC_Soil Investigation Work - Direct Shear Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5981621 | 5981621 | 5981621 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.14 | ECC_Soil Investigation Work - Expansion Index Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19938735 | 19938735 | 19938735 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.15 | ECC_Soil Investigation Work - Water Sample | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5981621 | 5981621 | 5981621 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.17 | ECC_Soil Investigation Work - Soil Investigation Report, Analysis & Recommendation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 89475074 | 89475074 | 89475074 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.2 | ECC_Soil Investigation Work - Grain Size Distribution ( Sieve Analysis ) and hydrometer test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5981621 | 5981621 | 5981621 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.3 | ECC_Soil Investigation Work - Atteberg Limits | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2791423 | 2791423 | 2791423 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.4 | ECC_Soil Investigation Work - Moisture Content and Unit Dry Weight Combined | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1993874 | 1993874 | 1993874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.5 | ECC_Soil Investigation Work - Specific Gravity | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1993874 | 1993874 | 1993874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.6 | ECC_Soil Investigation Work - Dynamic Soil properties | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1993874 | 1993874 | 1993874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.7 | ECC_Soil Investigation Work - Permeability Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1196324 | 1196324 | 1196324 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.8 | ECC_Soil Investigation Work - Corrosivity | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2990810 | 2990810 | 2990810 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.2.2.9 | ECC_Soil Investigation Work - Consolidation Test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7177945 | 7177945 | 7177945 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.1.1 | ECC_Well Drilling Construction Work - Geo-electric survey | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12461709 | 12461709 | 12461709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.1.2 | ECC_Well Drilling Construction Work - Setting drilling machine and tools | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2492342 | 2492342 | 2492342 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.1 | ECC_Well Drilling Construction Work - Water supply for drilling circulations | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6230855 | 6230855 | 6230855 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.2 | ECC_Well Drilling Construction Work - Pilot Drilling with dia 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 149540514 | 149540514 | 149540514 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.3 | ECC_Well Drilling Construction Work - Widenning drilling hole, and logging preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12461709 | 12461709 | 12461709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.4 | ECC_Well Drilling Construction Work - Drilling with electric logging | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24923419 | 24923419 | 24923419 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.5 | ECC_Well Drilling Construction Work - Widenning drilling hole from 4" to 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 186925642 | 186925642 | 186925642 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.6 | ECC_Well Drilling Construction Work - Supply bentonite (if required) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18692564 | 18692564 | 18692564 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.2.7 | ECC_Well Drilling Construction Work - Others (please specify) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18692564 | 18692564 | 18692564 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.1 | ECC_Well Drilling Construction Work - Supply & Install Jambang PVC pipe dia 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 25934064 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.2 | ECC_Well Drilling Construction Work - Supply & Install Blind PVC pipe dia 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 23340657 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.3 | ECC_Well Drilling Construction Work - Supply and install Connector PVC Pipe from Dia. 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 498468 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.4 | ECC_Well Drilling Construction Work - Supply & Install Screening Pipe | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 76265662 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.5 | ECC_Well Drilling Construction Work - Supply and install gravel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8972431 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.3.6 | ECC_Well Drilling Construction Work - Cleaning drilling hole | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6230855 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.4.1 | ECC_Well Drilling Construction Work - Submersible Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 149540514 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.4.2 | ECC_Well Drilling Construction Work - Panel Control - Start Delta (incl cable) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 49846838 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.4.3 | ECC_Well Drilling Construction Work - Supply and install Riser Galvanized Pipe Dia. 3" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 74770257 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.4.4 | ECC_Well Drilling Construction Work - Water Meter Actaris | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 12461709 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.4.5 | ECC_Well Drilling Construction Work - Laboratory Test for Sample | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2990810 | 2990810 | 2990810 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.5.1 | ECC_Well Drilling Construction Work - Drilling hole grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6230855 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.5.2 | ECC_Well Drilling Construction Work - Pumping test | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6230855 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.5.3 | ECC_Well Drilling Construction Work - Report and documentation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1246171 | 1246171 | 1246171 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.6.1 | ECC_Well Drilling Construction Work - Obtain the necessary permits | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 24923419 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.6.2 | ECC_Well Drilling Construction Work - SIPA permit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 37385128 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.7.1 | ECC_Well Drilling Construction Work - Groundwater observation well (depth to be determined after geoelectric survei resu | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31154274 | 31154274 | 31154274 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.A.3.7.2 | ECC_Well Drilling Construction Work - Analysis and Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6230855 | 6230855 | 6230855 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.1 | ECC_Access Road Construction Work - Clearing & Grubbing Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 456938943 | 456938943 | 456938943 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.2 | ECC_Access Road Construction Work - Soil Cut & disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 609414077 | 609414077 | 609414077 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.3 | ECC_Access Road Construction Work - Soil Fill & Compaction | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.85 | 5118460595 | 4350691506 | 3924323738 | 426367768 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.4 | ECC_Access Road Construction Work - Bamboo Matress for soil improvement | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1159834053 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.5 | ECC_Access Road Construction Work - Fill material for soil improvement area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.85 | 4124673100 | 3505972135 | 3162386866 | 343585269 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.1.B.1.1.6 | ECC_Access Road Construction Work - Geotextile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 900537142 | 900537142 | 450268571 | 450268571 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.B.2.1.1 | ECC_Clearing & Grubbing Work - Site Clearing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 926227588 | 926227588 | 926227588 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.B.2.1.2 | ECC_Clearing & Grubbing Work - Organic Soil Grubbing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 926474104 | 926474104 | 926474104 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.B.2.1.3 | ECC_Clearing & Grubbing Work - Temporary Fencing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1139846567 | 1139846567 | 1139846567 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.B.3.1.1 | ECC_Earthwork Construction - Soil Fill (Imported) & Compaction | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.85 | 10375257963 | 8818969269 | 7954710280 | 864258989 | 1 | 3500235911 | 864258989
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KI | Construction - PREPARATION WORKS | ECC.I.1.B.3.1.2 | ECC_Earthwork Construction - Dewatering | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 84598292 | 84598292 | 84598292 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JB | Construction - LANDSCAPING | ECC.I.10.1.1.1 | ECC_Finished Grading | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.2 | 47778219 | 9555644 | 4777822 | 4777822 | 1 | 3500235911 | 4777822
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JB | Construction - LANDSCAPING | ECC.I.10.2.1.1 | ECC_Enviromental Consideration And Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 47778219 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JB | Construction - LANDSCAPING | ECC.I.10.3.1.1 | ECC_Site Landscaping | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 47778219 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.1 | ECC_Power Generation Package A - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 493981343 | 493981343 | 493981343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.10 | ECC_Power Generation Package A - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47781915 | 47781915 | 47781915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.12 | ECC_Power Generation Package A - Pile Head Treatment (PHT) Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13172836 | 13172836 | 13172836 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.2 | ECC_Power Generation Package A - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291723427 | 291723427 | 291723427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.3 | ECC_Power Generation Package A - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2833440 | 2833440 | 2833440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.4 | ECC_Power Generation Package A - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 122647 | 122647 | 122647 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.5 | ECC_Power Generation Package A - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2616916 | 2616916 | 2616916 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.6 | ECC_Power Generation Package A - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26571805 | 26571805 | 26571805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.7 | ECC_Power Generation Package A - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13236505 | 13236505 | 13236505 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.8 | ECC_Power Generation Package A - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51681426 | 51681426 | 51681426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.1.9 | ECC_Power Generation Package A - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 921572 | 921572 | 921572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.1 | ECC_Power Generation Package B - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 493981343 | 493981343 | 493981343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.10 | ECC_Power Generation Package B - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47781915 | 47781915 | 47781915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.12 | ECC_Power Generation Package B - Pile Head Treatment (PHT) Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13172836 | 13172836 | 13172836 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.2 | ECC_Power Generation Package B - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291723427 | 291723427 | 291723427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.3 | ECC_Power Generation Package B - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2833440 | 2833440 | 2833440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.4 | ECC_Power Generation Package B - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 122647 | 122647 | 122647 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.5 | ECC_Power Generation Package B - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2616916 | 2616916 | 2616916 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.6 | ECC_Power Generation Package B - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26571805 | 26571805 | 26571805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.7 | ECC_Power Generation Package B - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13236505 | 13236505 | 13236505 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.8 | ECC_Power Generation Package B - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51681426 | 51681426 | 51681426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.2.9 | ECC_Power Generation Package B - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 921572 | 921572 | 921572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.1 | ECC_Power Generation Package C - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 493981343 | 493981343 | 493981343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.10 | ECC_Power Generation Package C - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47781915 | 47781915 | 47781915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.12 | ECC_Power Generation Package C - Pile Head Treatment (PHT) Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13172836 | 13172836 | 13172836 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.2 | ECC_Power Generation Package C - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291723427 | 291723427 | 291723427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.3 | ECC_Power Generation Package C - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2833440 | 2833440 | 2833440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.4 | ECC_Power Generation Package C - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 122647 | 122647 | 122647 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.5 | ECC_Power Generation Package C - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2616916 | 2616916 | 2616916 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.6 | ECC_Power Generation Package C - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26571805 | 26571805 | 26571805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.7 | ECC_Power Generation Package C - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13236505 | 13236505 | 13236505 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.8 | ECC_Power Generation Package C - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51681426 | 51681426 | 51681426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.3.9 | ECC_Power Generation Package C - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 921572 | 921572 | 921572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.1 | ECC_Power Generation Package D - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 493981343 | 493981343 | 493981343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.10 | ECC_Power Generation Package D - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47781915 | 47781915 | 47781915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.12 | ECC_Power Generation Package D - Pile Head Treatment (PHT) Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13172836 | 13172836 | 13172836 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.2 | ECC_Power Generation Package D - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291723427 | 291723427 | 291723427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.3 | ECC_Power Generation Package D - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2833440 | 2833440 | 2833440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.4 | ECC_Power Generation Package D - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 122647 | 122647 | 122647 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.5 | ECC_Power Generation Package D - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2616916 | 2616916 | 2616916 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.6 | ECC_Power Generation Package D - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26571805 | 26571805 | 26571805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.7 | ECC_Power Generation Package D - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13236505 | 13236505 | 13236505 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.8 | ECC_Power Generation Package D - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51681426 | 51681426 | 51681426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.4.9 | ECC_Power Generation Package D - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 921572 | 921572 | 921572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.1 | ECC_Power Generation Package E - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 493981343 | 493981343 | 493981343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.10 | ECC_Power Generation Package E - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47781915 | 47781915 | 47781915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.12 | ECC_Power Generation Package E - Pile Head Treatment (PHT) Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13172836 | 13172836 | 13172836 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.2 | ECC_Power Generation Package E - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291723427 | 291723427 | 291723427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.3 | ECC_Power Generation Package E - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2833440 | 2833440 | 2833440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.4 | ECC_Power Generation Package E - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 122647 | 122647 | 122647 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.5 | ECC_Power Generation Package E - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2616916 | 2616916 | 2616916 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.6 | ECC_Power Generation Package E - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26571805 | 26571805 | 26571805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.7 | ECC_Power Generation Package E - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13236505 | 13236505 | 13236505 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.8 | ECC_Power Generation Package E - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51681426 | 51681426 | 51681426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.2.A.5.9 | ECC_Power Generation Package E - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 921572 | 921572 | 921572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.1 | ECC_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 83576173 | 83576173 | 83576173 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.10 | ECC_Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1187214 | 1187214 | 1187214 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.2 | ECC_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 110264238 | 110264238 | 110264238 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.3 | ECC_Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6714231 | 6714231 | 6714231 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.4 | ECC_Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5992882 | 5992882 | 5992882 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.5 | ECC_Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1261389 | 1261389 | 1261389 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.6 | ECC_Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21500001 | 21500001 | 21500001 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.7 | ECC_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10710031 | 10710031 | 10710031 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.8 | ECC_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25623447 | 25623447 | 25623447 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.1.9 | ECC_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1431193 | 1431193 | 1431193 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.2.1 | ECC_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 33634380 | 26907504 | 13453752 | 13453752 | 1 | 3500235911 | 57339307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.2.2 | ECC_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 108534648 | 86827718 | 43413859 | 43413859 | 1 | 3500235911 | 57339307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.2.3 | ECC_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48865382 | 48865382 | 48865382 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.3.1 | ECC_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 290972024 | 290972024 | 290972024 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.4.1 | ECC_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5728512 | 5728512 | 5728512 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.4.2 | ECC_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 13429770 | 12086793 | 12086793 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.4.3 | ECC_Finishing - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 436458036 | 392812232 | 392812232 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.4.4 | ECC_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24205984 | 24205984 | 24205984 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.5.1 | ECC_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 628937 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.5.2 | ECC_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 471696 | 471696 | 0 | 471696 | 1 | 3500235911 | 57339307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DU | Construction - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | ECC.I.2.B.5.3 | ECC_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 749613 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.1 | ECC_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45520818 | 45520818 | 45520818 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.10 | ECC_Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4921070 | 4921070 | 4921070 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.2 | ECC_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34318177 | 34318177 | 34318177 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.3 | ECC_Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11715204 | 11715204 | 11715204 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.4 | ECC_Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10326248 | 10326248 | 10326248 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.5 | ECC_Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2313809 | 2313809 | 2313809 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.6 | ECC_Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22358052 | 22358052 | 22358052 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.7 | ECC_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11137462 | 11137462 | 11137462 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.8 | ECC_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 147843330 | 147843330 | 147843330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.1.9 | ECC_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11864751 | 11864751 | 11864751 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.2.1 | ECC_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63643802 | 63643802 | 63643802 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.2.2 | ECC_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27950236 | 27950236 | 25155212 | 2795024 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.3.1 | ECC_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19652784 | 19652784 | 19652784 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.4.1 | ECC_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3821375 | 3057100 | 2292825 | 764275 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.4.2 | ECC_Finishing - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 29479176 | 29479176 | 26531258 | 2947918 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.4.3 | ECC_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 13647767 | 12282990 | 12282990 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.4.4 | ECC_Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14466769 | 14466769 | 13020092 | 1446677 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.4.5 | ECC_Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 19816557 | 17834901 | 15853246 | 1981655 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.5.1 | ECC_Plumbing & Sanitary - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167277003 | 167277003 | 167277003 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.5.2 | ECC_Plumbing & Sanitary - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45906655 | 45906655 | 45906655 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.5.3 | ECC_Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15510116 | 15510116 | 15510116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.5.4 | ECC_Plumbing & Sanitary - Septictank + Leatching Pit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6530442 | 6530442 | 6530442 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.6.1 | ECC_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15016202 | 15016202 | 0 | 15016202 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.6.2 | ECC_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3753992 | 3753992 | 0 | 3753992 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.6.3 | ECC_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22371761 | 22371761 | 15660233 | 6711528 | 1 | 3500235911 | 35417271
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AP | Construction - ADMINISTRATION BUILDING | ECC.I.3.A.6.4 | ECC_Doors & Windows - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8668432 | 8668432 | 8668432 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.1 | ECC_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63269293 | 63269293 | 63269293 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.10 | ECC_Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 898752 | 898752 | 898752 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.2 | ECC_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 83472838 | 83472838 | 83472838 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.3 | ECC_Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5082844 | 5082844 | 5082844 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.4 | ECC_Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4536764 | 4536764 | 4536764 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.5 | ECC_Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 954904 | 954904 | 954904 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.6 | ECC_Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16276049 | 16276049 | 16276049 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.7 | ECC_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8107766 | 8107766 | 8107766 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.8 | ECC_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19397602 | 19397602 | 19397602 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.1.9 | ECC_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1083450 | 1083450 | 1083450 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.2.1 | ECC_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25462083 | 25462083 | 25462083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.2.2 | ECC_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 82163494 | 73947145 | 0 | 73947145 | 1 | 3500235911 | 76265002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.2.3 | ECC_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36992339 | 36992339 | 36992339 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.3.1 | ECC_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 220273237 | 220273237 | 220273237 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.4.1 | ECC_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 4336629 | 4119798 | 3902966 | 216832 | 1 | 3500235911 | 76265002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.4.2 | ECC_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 10166678 | 9150010 | 9150010 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.4.3 | ECC_Finishing - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 330409855 | 297368870 | 297368870 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.4.4 | ECC_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18324547 | 18324547 | 18324547 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.5.1 | ECC_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 714182 | 714182 | 0 | 714182 | 1 | 3500235911 | 76265002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.5.2 | ECC_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 535628 | 535628 | 0 | 535628 | 1 | 3500235911 | 76265002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.FL | Construction - CONTROL & MONITORING BUILDING | ECC.I.4.A.5.3 | ECC_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 851215 | 851215 | 0 | 851215 | 1 | 3500235911 | 76265002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.1 | ECC_Fuel Oil Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 972922608 | 972922608 | 972922608 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.11 | ECC_Fuel Oil Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20198539 | 20198539 | 20198539 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.2 | ECC_Fuel Oil Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 574564851 | 574564851 | 574564851 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.3 | ECC_Fuel Oil Daily Tank - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43226611 | 43226611 | 43226611 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.4 | ECC_Fuel Oil Daily Tank - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3333860 | 3333860 | 3333860 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.5 | ECC_Fuel Oil Daily Tank - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 38656161 | 38656161 | 38656161 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.6 | ECC_Fuel Oil Daily Tank - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 130836470 | 130836470 | 130836470 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.7 | ECC_Fuel Oil Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65175004 | 65175004 | 65175004 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.8 | ECC_Fuel Oil Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 61171470 | 61171470 | 61171470 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.1.9 | ECC_Fuel Oil Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1815084 | 1815084 | 1815084 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.1 | ECC_Fuel Oil Forwarding Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 49394532 | 49394532 | 49394532 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.11 | ECC_Fuel Oil Forwarding Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13331035 | 13331035 | 13331035 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.2 | ECC_Fuel Oil Forwarding Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 29170216 | 29170216 | 29170216 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.3 | ECC_Fuel Oil Forwarding Pump - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2865789 | 2865789 | 2865789 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.4 | ECC_Fuel Oil Forwarding Pump - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 913915 | 913915 | 913915 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.5 | ECC_Fuel Oil Forwarding Pump - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1962544 | 1962544 | 1962544 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.6 | ECC_Fuel Oil Forwarding Pump - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6642467 | 6642467 | 6642467 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.7 | ECC_Fuel Oil Forwarding Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3308885 | 3308885 | 3308885 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.8 | ECC_Fuel Oil Forwarding Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15170524 | 15170524 | 15170524 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.2.9 | ECC_Fuel Oil Forwarding Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 92150 | 92150 | 92150 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.1 | ECC_Fuel Oil Purification Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 60285860 | 60285860 | 60285860 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.10 | ECC_Fuel Oil Purification Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20048946 | 20048946 | 20048946 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.11 | ECC_Fuel Oil Purification Shelter - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8315578 | 8315578 | 8315578 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.2 | ECC_Fuel Oil Purification Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 79536718 | 79536718 | 79536718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.3 | ECC_Fuel Oil Purification Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20330812 | 20330812 | 20330812 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.4 | ECC_Fuel Oil Purification Shelter - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17722107 | 17722107 | 17722107 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.5 | ECC_Fuel Oil Purification Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4187200 | 4187200 | 4187200 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.6 | ECC_Fuel Oil Purification Shelter - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24322164 | 24322164 | 24322164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.7 | ECC_Fuel Oil Purification Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12115866 | 12115866 | 12115866 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.8 | ECC_Fuel Oil Purification Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 70632657 | 70632657 | 70632657 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.1.9 | ECC_Fuel Oil Purification Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1077255 | 1077255 | 1077255 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.2.1 | ECC_Fuel Oil Purification Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36968492 | 36968492 | 0 | 36968492 | 1 | 3500235911 | 124237710
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.3.1 | ECC_Fuel Oil Purification Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 23948864 | 23948864 | 23948864 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.4.1 | ECC_Fuel Oil Purification Shelter - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 35923296 | 32330966 | 32330966 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.4.2 | ECC_Fuel Oil Purification Shelter - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 16631156 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DH | Construction - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | ECC.I.5.A.3.5.1 | ECC_Fuel Oil Purification Shelter - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 290897392 | 261807653 | 174538435 | 87269218 | 1 | 3500235911 | 124237710
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.1 | ECC_Air Compressor Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 142150503 | 142150503 | 142150503 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.11 | ECC_Air Compressor Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 38364841 | 38364841 | 38364841 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.2 | ECC_Air Compressor Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 83947769 | 83947769 | 83947769 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.3 | ECC_Air Compressor Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8247336 | 8247336 | 8247336 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.4 | ECC_Air Compressor Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2630119 | 2630119 | 2630119 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.5 | ECC_Air Compressor Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5647924 | 5647924 | 5647924 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.6 | ECC_Air Compressor Foundation - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19116084 | 19116084 | 19116084 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.7 | ECC_Air Compressor Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9522504 | 9522504 | 9522504 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.8 | ECC_Air Compressor Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43658631 | 43658631 | 43658631 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EF | Construction - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | ECC.I.5.B.1.9 | ECC_Air Compressor Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 265196 | 265196 | 265196 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.1 | ECC_Fuel Gas System Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25172641 | 25172641 | 25172641 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.11 | ECC_Fuel Gas System Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5681910 | 5681910 | 5681910 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.2 | ECC_Fuel Gas System Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14865843 | 14865843 | 14865843 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.3 | ECC_Fuel Gas System Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1247938 | 1247938 | 1247938 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.4 | ECC_Fuel Gas System Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229958 | 229958 | 229958 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.5 | ECC_Fuel Gas System Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1000159 | 1000159 | 1000159 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.6 | ECC_Fuel Gas System Foundation - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3385161 | 3385161 | 3385161 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.7 | ECC_Fuel Gas System Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1686287 | 1686287 | 1686287 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.8 | ECC_Fuel Gas System Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4142560 | 4142560 | 4142560 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.1.9 | ECC_Fuel Gas System Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46962 | 46962 | 46962 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.1 | ECC_Gas Metering System Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5415502 | 5415502 | 5415502 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.10 | ECC_Gas Metering System Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3123598 | 3123598 | 3123598 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.11 | ECC_Gas Metering System Shelter - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1295555 | 1295555 | 1295555 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.2 | ECC_Gas Metering System Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7144815 | 7144815 | 7144815 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.3 | ECC_Gas Metering System Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2052134 | 2052134 | 2052134 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.4 | ECC_Gas Metering System Shelter - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1853924 | 1853924 | 1853924 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.5 | ECC_Gas Metering System Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 366245 | 366245 | 366245 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.6 | ECC_Gas Metering System Shelter - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 953873 | 953873 | 953873 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.7 | ECC_Gas Metering System Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 475163 | 475163 | 475163 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.8 | ECC_Gas Metering System Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9511368 | 9511368 | 9511368 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.1.9 | ECC_Gas Metering System Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167835 | 167835 | 167835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.2.1 | ECC_Gas Metering System Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5748004 | 5748004 | 0 | 5748004 | 1 | 3500235911 | 14812285
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.3.1 | ECC_Gas Metering System Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4643270 | 4643270 | 4643270 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.4.1 | ECC_Gas Metering System Shelter - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6964906 | 6268415 | 6268415 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CV | Construction - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | ECC.I.5.C.2.5.1 | ECC_Gas Metering System Shelter - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 30214271 | 27192844 | 18128563 | 9064281 | 1 | 3500235911 | 14812285
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.1 | ECC_Combine Raw Water Storage & Fire Water Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 457558353 | 457558353 | 457558353 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.11 | ECC_Combine Raw Water Storage & Fire Water Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 112008994 | 112008994 | 112008994 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.2 | ECC_Combine Raw Water Storage & Fire Water Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 270213627 | 270213627 | 270213627 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.3 | ECC_Combine Raw Water Storage & Fire Water Tank - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20315312 | 20315312 | 20315312 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.4 | ECC_Combine Raw Water Storage & Fire Water Tank - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1552529 | 1552529 | 1552529 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.5 | ECC_Combine Raw Water Storage & Fire Water Tank - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18179708 | 18179708 | 18179708 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.6 | ECC_Combine Raw Water Storage & Fire Water Tank - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 61531430 | 61531430 | 61531430 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.7 | ECC_Combine Raw Water Storage & Fire Water Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30651326 | 30651326 | 30651326 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.8 | ECC_Combine Raw Water Storage & Fire Water Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28494507 | 28494507 | 28494507 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EB | Construction - CIVIL WORKS FOR RAW WATER SYSTEM | ECC.I.5.D.1.9 | ECC_Combine Raw Water Storage & Fire Water Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 853621 | 853621 | 853621 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.1 | ECC_Gas Engine Radiator - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 318465085 | 318465085 | 318465085 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.11 | ECC_Gas Engine Radiator - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85950188 | 85950188 | 85950188 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.2 | ECC_Gas Engine Radiator - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 188071325 | 188071325 | 188071325 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.3 | ECC_Gas Engine Radiator - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16099728 | 16099728 | 16099728 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.4 | ECC_Gas Engine Radiator - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3255141 | 3255141 | 3255141 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.5 | ECC_Gas Engine Radiator - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12653255 | 12653255 | 12653255 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.6 | ECC_Gas Engine Radiator - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42826477 | 42826477 | 42826477 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.7 | ECC_Gas Engine Radiator - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21333622 | 21333622 | 21333622 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.8 | ECC_Gas Engine Radiator - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56522498 | 56522498 | 56522498 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.EA | Construction - CIVIL WORKS FOR RADIATOR SYSTEM | ECC.I.5.H.1.9 | ECC_Gas Engine Radiator - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 594128 | 594128 | 594128 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.1 | ECC_Lube Oil Storage Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 374404391 | 374404391 | 374404391 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.11 | ECC_Lube Oil Storage Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 68735551 | 68735551 | 68735551 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.2 | ECC_Lube Oil Storage Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 221106593 | 221106593 | 221106593 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.3 | ECC_Lube Oil Storage Tank - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20950141 | 20950141 | 20950141 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.4 | ECC_Lube Oil Storage Tank - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6070685 | 6070685 | 6070685 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.5 | ECC_Lube Oil Storage Tank - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14875835 | 14875835 | 14875835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.6 | ECC_Lube Oil Storage Tank - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50349071 | 50349071 | 50349071 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.7 | ECC_Lube Oil Storage Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25080934 | 25080934 | 25080934 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.8 | ECC_Lube Oil Storage Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 101605579 | 101605579 | 101605579 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CP | Construction - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | ECC.I.5.I.1.9 | ECC_Lube Oil Storage Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 698489 | 698489 | 698489 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.1 | ECC_Exhaust Stack - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66798241 | 66798241 | 66798241 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.11 | ECC_Exhaust Stack - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1802059 | 1802059 | 1802059 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.2 | ECC_Exhaust Stack - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 433928796 | 433928796 | 433928796 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.3 | ECC_Exhaust Stack - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4403880 | 4403880 | 4403880 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.4 | ECC_Exhaust Stack - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1413607 | 1413607 | 1413607 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.5 | ECC_Exhaust Stack - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3007898 | 3007898 | 3007898 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.6 | ECC_Exhaust Stack - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5389727 | 5389727 | 5389727 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.7 | ECC_Exhaust Stack - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2684844 | 2684844 | 2684844 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.8 | ECC_Exhaust Stack - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10696807 | 10696807 | 10696807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.1.9 | ECC_Exhaust Stack - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1370807 | 1370807 | 1370807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.2.1 | ECC_Exhaust Structure - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53861472 | 53861472 | 53861472 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.2.2 | ECC_Exhaust Structure - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10800232 | 10800232 | 8640186 | 2160046 | 1 | 3500235911 | 2691702
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.2.3 | ECC_Exhaust Structure - Steel Ladder | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 886094 | 886094 | 354438 | 531656 | 1 | 3500235911 | 2691702
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.2.4 | ECC_Exhaust Structure - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8860939 | 8860939 | 8860939 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.CL | Construction - CIVIL WORKS FOR EXHAUST SYSTEM | ECC.I.5.J.2.5 | ECC_Exhaust Structure - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 101491038 | 101491038 | 101491038 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.1 | ECC_Circulating Cooling Water System - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 235376632 | 235376632 | 235376632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.11 | ECC_Circulating Cooling Water System - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63525538 | 63525538 | 63525538 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.2 | ECC_Circulating Cooling Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 139002978 | 139002978 | 139002978 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.3 | ECC_Circulating Cooling Water System - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10864819 | 10864819 | 10864819 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.4 | ECC_Circulating Cooling Water System - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1258221 | 1258221 | 1258221 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.5 | ECC_Circulating Cooling Water System - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9351984 | 9351984 | 9351984 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.6 | ECC_Circulating Cooling Water System - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31652926 | 31652926 | 31652926 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.7 | ECC_Circulating Cooling Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15767619 | 15767619 | 15767619 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.8 | ECC_Circulating Cooling Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 23086525 | 23086525 | 23086525 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.BU | Construction - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | ECC.I.5.K.1.9 | ECC_Circulating Cooling Water System - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439119 | 439119 | 439119 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.1 | ECC_Emergency Diesel Generator (EDG) - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10890470 | 10890470 | 10890470 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.11 | ECC_Emergency Diesel Generator (EDG) - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 911911 | 911911 | 0 | 911911 | 1 | 3500235911 | 6447622
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.2 | ECC_Emergency Diesel Generator (EDG) - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6431427 | 6431427 | 6431427 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.3 | ECC_Emergency Diesel Generator (EDG) - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 909231 | 909231 | 909231 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.4 | ECC_Emergency Diesel Generator (EDG) - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 448996 | 448996 | 448996 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.5 | ECC_Emergency Diesel Generator (EDG) - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 484887 | 484887 | 484887 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.6 | ECC_Emergency Diesel Generator (EDG) - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1994422 | 1994422 | 1994422 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.7 | ECC_Emergency Diesel Generator (EDG) - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 993503 | 993503 | 993503 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.8 | ECC_Emergency Diesel Generator (EDG) - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4491807 | 4491807 | 4491807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.5.L.1.9 | ECC_Emergency Diesel Generator (EDG) - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20317 | 20317 | 0 | 20317 | 1 | 3500235911 | 6447622
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.1 | ECC_Transformer Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8242396 | 8242396 | 8242396 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.10 | ECC_Transformer Foundation - Joint Filler | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 105442 | 105442 | 105442 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.11 | ECC_Transformer Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1659522 | 1659522 | 1659522 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.12 | ECC_Transformer Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 895923 | 895923 | 895923 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.2 | ECC_Transformer Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6084491 | 6084491 | 6084491 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.3 | ECC_Transformer Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 426173 | 426173 | 426173 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.4 | ECC_Transformer Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 94772 | 94772 | 94772 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.5 | ECC_Transformer Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 327487 | 327487 | 327487 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.6 | ECC_Transformer Foundation - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1108419 | 1108419 | 1108419 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.7 | ECC_Transformer Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 552149 | 552149 | 552149 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.8 | ECC_Transformer Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1601732 | 1601732 | 1601732 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.1.9 | ECC_Transformer Foundation - Joint Sealant | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39145 | 39145 | 39145 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.1 | ECC_Fire Blast Transformer - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9646142 | 9646142 | 9646142 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.2 | ECC_Fire Blast Transformer - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9090292 | 9090292 | 9090292 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.3 | ECC_Fire Blast Transformer - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7406207 | 7406207 | 7406207 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.4 | ECC_Fire Blast Transformer - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7757102 | 7757102 | 7757102 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.5 | ECC_Fire Blast Transformer - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 398122 | 398122 | 398122 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.6 | ECC_Fire Blast Transformer - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 273937 | 273937 | 273937 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.7 | ECC_Fire Blast Transformer - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 272919 | 272919 | 272919 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.8 | ECC_Fire Blast Transformer - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12118439 | 12118439 | 12118439 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DX | Construction - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.I.6.A.2.9 | ECC_Fire Blast Transformer - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 565846 | 565846 | 565846 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BP | Construction - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | ECC.I.6.B.1.1 | ECC_Emergency Diesel Generator (Edg)/Black Start Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5515394 | 5515394 | 0 | 5515394 | 1 | 3500235911 | 6447622
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.C.1.1 | ECC_Electrical Tray Support - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3676929 | 3676929 | 2573850 | 1103079 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.1 | ECC_Duct Bank - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 816082 | 816082 | 652866 | 163216 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.2 | ECC_Duct Bank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 769056 | 769056 | 615245 | 153811 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.3 | ECC_Duct Bank - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1182776 | 1182776 | 946221 | 236555 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.4 | ECC_Duct Bank - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1190531 | 1190531 | 952425 | 238106 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.5 | ECC_Duct Bank - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 105407 | 105407 | 84326 | 21081 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.6 | ECC_Duct Bank - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 356763 | 356763 | 285410 | 71353 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.7 | ECC_Duct Bank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177718 | 177718 | 142174 | 35544 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.8 | ECC_Duct Bank - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 719711 | 719711 | 575769 | 143942 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.1.9 | ECC_Duct Bank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 612259 | 612259 | 489807 | 122452 | 1 | 3500235911 | 2289139
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.1 | ECC_Trench - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 816082 | 816082 | 816082 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.2 | ECC_Trench - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 769056 | 769056 | 769056 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.3 | ECC_Trench - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1182776 | 1182776 | 1182776 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.4 | ECC_Trench - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1190531 | 1190531 | 1190531 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.5 | ECC_Trench - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 105407 | 105407 | 105407 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.6 | ECC_Trench - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 356763 | 356763 | 356763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.7 | ECC_Trench - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177718 | 177718 | 177718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.8 | ECC_Trench - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 719711 | 719711 | 719711 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.BR | Construction - CIVIL WORKS FOR CABLE LAYING PROTECTION | ECC.I.6.D.2.9 | ECC_Trench - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 612259 | 612259 | 612259 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.1 | ECC_WTP Package - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16805743 | 16805743 | 16805743 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.11 | ECC_WTP Package - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4535683 | 4535683 | 4535683 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.2 | ECC_WTP Package - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9924725 | 9924725 | 9924725 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.3 | ECC_WTP Package - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 746673 | 746673 | 746673 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.4 | ECC_WTP Package - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 57587 | 57587 | 57587 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.5 | ECC_WTP Package - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 667726 | 667726 | 667726 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.6 | ECC_WTP Package - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2259999 | 2259999 | 2259999 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.7 | ECC_WTP Package - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1125798 | 1125798 | 1125798 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.8 | ECC_WTP Package - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1056643 | 1056643 | 1056643 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.1.9 | ECC_WTP Package - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31353 | 31353 | 31353 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.1 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1211953 | 1211953 | 1211953 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.11 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 99509 | 99509 | 99509 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.2 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 715725 | 715725 | 715725 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.3 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65435 | 65435 | 65435 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.4 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17009 | 17009 | 17009 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.5 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48153 | 48153 | 48153 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.6 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 162981 | 162981 | 162981 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.7 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 81187 | 81187 | 81187 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.8 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 285294 | 285294 | 285294 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.2.9 | ECC_Treated Water (Fresh Water) Water Tank & Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2261 | 2261 | 2261 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.1 | ECC_WTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1690921 | 1690921 | 1690921 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.10 | ECC_WTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 865787 | 865787 | 865787 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.11 | ECC_WTP Shelter - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 359097 | 359097 | 359097 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.2 | ECC_WTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2230876 | 2230876 | 2230876 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.3 | ECC_WTP Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 665298 | 665298 | 665298 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.4 | ECC_WTP Shelter - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 606096 | 606096 | 606096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.5 | ECC_WTP Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114355 | 114355 | 114355 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.6 | ECC_WTP Shelter - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 307852 | 307852 | 307852 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.7 | ECC_WTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 153354 | 153354 | 153354 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.8 | ECC_WTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3164646 | 3164646 | 3164646 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.1.9 | ECC_WTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46520 | 46520 | 46520 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.2.1 | ECC_WTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3479260 | 3479260 | 0 | 3479260 | 1 | 3500235911 | 4986702
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.3.1 | ECC_WTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4302270 | 4302270 | 4302270 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.4.1 | ECC_WTP Shelter - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6453405 | 5808065 | 5808065 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.ES | Construction - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | ECC.I.7.A.3.5.1 | ECC_WTP Shelter - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 5024805 | 4522325 | 3014883 | 1507442 | 1 | 3500235911 | 4986702
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.1 | ECC_Waste Water Treatment Facilities - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30225182 | 30225182 | 30225182 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.11 | ECC_Waste Water Treatment Facilities - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8157441 | 8157441 | 8157441 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.2 | ECC_Waste Water Treatment Facilities - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17849649 | 17849649 | 17849649 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.3 | ECC_Waste Water Treatment Facilities - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1379179 | 1379179 | 1379179 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.4 | ECC_Waste Water Treatment Facilities - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 143826 | 143826 | 143826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.5 | ECC_Waste Water Treatment Facilities - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1200907 | 1200907 | 1200907 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.6 | ECC_Waste Water Treatment Facilities - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4064615 | 4064615 | 4064615 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.7 | ECC_Waste Water Treatment Facilities - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2024751 | 2024751 | 2024751 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.8 | ECC_Waste Water Treatment Facilities - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2635188 | 2635188 | 2635188 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.1.9 | ECC_Waste Water Treatment Facilities - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56388 | 56388 | 56388 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.1 | ECC_WWTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4392738 | 4392738 | 4392738 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.10 | ECC_WWTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2249174 | 2249174 | 2249174 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.11 | ECC_WWTP Shelter - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 932876 | 932876 | 932876 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.2 | ECC_WWTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5795455 | 5795455 | 5795455 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.3 | ECC_WWTP Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1728336 | 1728336 | 1728336 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.4 | ECC_WWTP Shelter - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1574538 | 1574538 | 1574538 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.5 | ECC_WWTP Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 297076 | 297076 | 297076 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.6 | ECC_WWTP Shelter - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 799751 | 799751 | 799751 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.7 | ECC_WWTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 398389 | 398389 | 398389 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.8 | ECC_WWTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8221238 | 8221238 | 8221238 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.1.9 | ECC_WWTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120851 | 120851 | 120851 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.2.1 | ECC_WWTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9038554 | 9038554 | 0 | 9038554 | 1 | 3500235911 | 12954643
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.3.1 | ECC_WWTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11176601 | 11176601 | 11176601 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.4.1 | ECC_WWTP Shelter - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 16764901 | 15088411 | 15088411 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.EP | Construction - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | ECC.I.7.B.2.5.1 | ECC_WWTP Shelter - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 13053630 | 11748267 | 7832178 | 3916089 | 1 | 3500235911 | 12954643
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.1 | ECC_Motor Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1201041 | 1201041 | 1201041 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.11 | ECC_Motor Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 230315 | 230315 | 0 | 230315 | 1 | 3500235911 | 4077508
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.2 | ECC_Motor Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 709281 | 709281 | 709281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.3 | ECC_Motor Driven Fire Pump - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 69644 | 69644 | 69644 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.4 | ECC_Motor Driven Fire Pump - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22179 | 22179 | 22179 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.5 | ECC_Motor Driven Fire Pump - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47720 | 47720 | 47720 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.6 | ECC_Motor Driven Fire Pump - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161513 | 161513 | 161513 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.7 | ECC_Motor Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80456 | 80456 | 80456 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.8 | ECC_Motor Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 365807 | 365807 | 365807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.1.9 | ECC_Motor Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2241 | 2241 | 2241 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.1 | ECC_Diesel Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1201041 | 1201041 | 1201041 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.11 | ECC_Diesel Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 230315 | 230315 | 0 | 230315 | 1 | 3500235911 | 4077508
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.2 | ECC_Diesel Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 709281 | 709281 | 709281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.3 | ECC_Diesel Driven Fire Pump - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 69644 | 69644 | 69644 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.4 | ECC_Diesel Driven Fire Pump - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22179 | 22179 | 22179 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.5 | ECC_Diesel Driven Fire Pump - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47720 | 47720 | 47720 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.6 | ECC_Diesel Driven Fire Pump - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161513 | 161513 | 161513 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.7 | ECC_Diesel Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80456 | 80456 | 80456 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.8 | ECC_Diesel Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 365807 | 365807 | 365807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.2.9 | ECC_Diesel Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2241 | 2241 | 2241 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.1 | ECC_Fire Water Diesel Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 128006 | 128006 | 128006 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.11 | ECC_Fire Water Diesel Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10663 | 10663 | 10663 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.2 | ECC_Fire Water Diesel Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 75594 | 75594 | 75594 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.3 | ECC_Fire Water Diesel Daily Tank - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13230 | 13230 | 13230 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.4 | ECC_Fire Water Diesel Daily Tank - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8806 | 8806 | 8806 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.5 | ECC_Fire Water Diesel Daily Tank - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5086 | 5086 | 5086 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.6 | ECC_Fire Water Diesel Daily Tank - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17214 | 17214 | 17214 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.7 | ECC_Fire Water Diesel Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8575 | 8575 | 8575 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.8 | ECC_Fire Water Diesel Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 111602 | 111602 | 111602 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.3.9 | ECC_Fire Water Diesel Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 239 | 239 | 239 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.1 | ECC_Jockey Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 72568 | 72568 | 72568 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.11 | ECC_Jockey Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3276 | 3276 | 0 | 3276 | 1 | 3500235911 | 4077508
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.2 | ECC_Jockey Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42856 | 42856 | 42856 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.3 | ECC_Jockey Pump - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9633 | 9633 | 9633 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.4 | ECC_Jockey Pump - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7358 | 7358 | 7358 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.5 | ECC_Jockey Pump - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2883 | 2883 | 2883 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.6 | ECC_Jockey Pump - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9759 | 9759 | 9759 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.7 | ECC_Jockey Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4861 | 4861 | 4861 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.8 | ECC_Jockey Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 84074 | 84074 | 84074 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.4.9 | ECC_Jockey Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 135 | 135 | 135 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.1 | ECC_Fire Water Pump Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1321165 | 1321165 | 1321165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.10 | ECC_Fire Water Pump Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 762032 | 762032 | 762032 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.11 | ECC_Fire Water Pump Shelter - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 316063 | 316063 | 316063 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.2 | ECC_Fire Water Pump Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1743047 | 1743047 | 1743047 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.3 | ECC_Fire Water Pump Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 500638 | 500638 | 500638 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.4 | ECC_Fire Water Pump Shelter - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 452283 | 452283 | 452283 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.5 | ECC_Fire Water Pump Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 89349 | 89349 | 89349 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.6 | ECC_Fire Water Pump Shelter - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 232707 | 232707 | 232707 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.7 | ECC_Fire Water Pump Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 115921 | 115921 | 115921 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.8 | ECC_Fire Water Pump Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2320392 | 2320392 | 2320392 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.1.9 | ECC_Fire Water Pump Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 40945 | 40945 | 40945 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.2.1 | ECC_Fire Water Pump Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1402282 | 1402282 | 0 | 1402282 | 1 | 3500235911 | 4077508
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.3.1 | ECC_Fire Water Pump Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1132771 | 1132771 | 1132771 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.4.1 | ECC_Fire Water Pump Shelter - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1699157 | 1529241 | 1529241 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GR | Construction - FIRE FIGHTING SYSTEM | ECC.I.7.C.5.5.1 | ECC_Fire Water Pump Shelter - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 7371067 | 6633960 | 4422640 | 2211320 | 1 | 3500235911 | 4077508
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.1 | ECC_Laboratory - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3463441 | 3463441 | 3463441 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.11 | ECC_Laboratory - Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 159218 | 159218 | 159218 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.2 | ECC_Laboratory - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4569409 | 4569409 | 4569409 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.3 | ECC_Laboratory - Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 345320 | 345320 | 345320 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.4 | ECC_Laboratory - Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 293139 | 293139 | 293139 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.5 | ECC_Laboratory - Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 77939 | 77939 | 77939 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.6 | ECC_Laboratory - Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1922996 | 1922996 | 1922996 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.7 | ECC_Laboratory - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 957923 | 957923 | 957923 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.1.8 | ECC_Laboratory - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2136585 | 2136585 | 2136585 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.2.1 | ECC_Laboratory - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1667327 | 1333862 | 1000396 | 333466 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.3.1 | ECC_Laboratory - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1278615 | 1278615 | 1278615 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.4.1 | ECC_Laboratory - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 737072 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.4.2 | ECC_Laboratory - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2243200 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.4.3 | ECC_Laboratory - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 270036 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.4.4 | ECC_Laboratory - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 369894 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.5.1 | ECC_Laboratory - Plumbing & Sanitary - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 13530315 | 6765158 | 0 | 6765158 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.5.2 | ECC_Laboratory - Plumbing & Sanitary - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3713191 | 3341872 | 2227915 | 1113957 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.5.3 | ECC_Laboratory - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1254546 | 1003637 | 752728 | 250909 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.6.1 | ECC_Laboratory - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 202433 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.6.2 | ECC_Laboratory - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 303644 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.A.6.3 | ECC_Laboratory - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 241274 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.1 | ECC_Security Guardhouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1172718 | 1172718 | 1172718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.11 | ECC_Security Guardhouse - Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53911 | 53911 | 53911 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.2 | ECC_Security Guardhouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1547198 | 1547198 | 1547198 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.3 | ECC_Security Guardhouse - Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 116925 | 116925 | 116925 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.4 | ECC_Security Guardhouse - Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 99257 | 99257 | 99257 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.5 | ECC_Security Guardhouse - Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26390 | 26390 | 26390 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.6 | ECC_Security Guardhouse - Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 651125 | 651125 | 651125 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.7 | ECC_Security Guardhouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 324352 | 324352 | 324352 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.1.8 | ECC_Security Guardhouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 723446 | 723446 | 723446 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.2.1 | ECC_Security Guardhouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 564556 | 564556 | 564556 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.3.1 | ECC_Security Guardhouse - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 432938 | 432938 | 432938 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.4.1 | ECC_Security Guardhouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 249572 | 224615 | 224615 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.4.2 | ECC_Security Guardhouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 759546 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.4.3 | ECC_Security Guardhouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 91434 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.4.4 | ECC_Security Guardhouse - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 125246 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.5.1 | ECC_Security Guardhouse - Plumbing & Sanitary - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 9162709 | 4581355 | 0 | 4581355 | 1 | 3500235911 | 4984646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.5.2 | ECC_Security Guardhouse - Plumbing & Sanitary - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2514567 | 1508740 | 1508740 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.5.3 | ECC_Security Guardhouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 849577 | 424789 | 424789 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.6.1 | ECC_Security Guardhouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 137087 | 137087 | 0 | 137087 | 1 | 3500235911 | 4984646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.6.2 | ECC_Security Guardhouse - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 102814 | 102814 | 0 | 102814 | 1 | 3500235911 | 4984646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.I.8.B.6.3 | ECC_Security Guardhouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 163390 | 163390 | 0 | 163390 | 1 | 3500235911 | 4984646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.1 | ECC_Workshop - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6836571 | 6836571 | 6836571 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.10 | ECC_Workshop - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 741248 | 741248 | 741248 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.11 | ECC_Workshop - Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 307443 | 307443 | 307443 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.2 | ECC_Workshop - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9019667 | 9019667 | 9019667 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.3 | ECC_Workshop - Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 908638 | 908638 | 908638 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.4 | ECC_Workshop - Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 805254 | 805254 | 805254 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.5 | ECC_Workshop - Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175697 | 175697 | 175697 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.6 | ECC_Workshop - Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2290885 | 2290885 | 2290885 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.7 | ECC_Workshop - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1141183 | 1141183 | 1141183 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.8 | ECC_Workshop - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7752858 | 7752858 | 7752858 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.1.9 | ECC_Workshop - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39828 | 39828 | 39828 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.2.1 | ECC_Workshop - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 735895 | 588716 | 441537 | 147179 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.2.2 | ECC_Workshop - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2043292 | 2043292 | 0 | 2043292 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.3.1 | ECC_Workshop - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2518573 | 2518573 | 2518573 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.4.1 | ECC_Workshop - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 49584 | 49584 | 0 | 49584 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.4.2 | ECC_Workshop - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 293833 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.4.3 | ECC_Workshop - Finishing - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3777859 | 3400073 | 3400073 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.4.4 | ECC_Workshop - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2361162 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.4.5 | ECC_Workshop - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1853967 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.5.1 | ECC_Workshop - Plumbing & Sanitary - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 20901202 | 10450601 | 0 | 10450601 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.5.2 | ECC_Workshop - Plumbing & Sanitary - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 5736020 | 5162418 | 3441612 | 1720806 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.5.3 | ECC_Workshop - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1937983 | 1550386 | 1162790 | 387596 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.6.1 | ECC_Workshop - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 390886 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.6.2 | ECC_Workshop - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 625423 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.C.6.3 | ECC_Workshop - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 745425 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.1 | ECC_Warehouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6836571 | 6836571 | 6836571 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.10 | ECC_Warehouse - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 741248 | 741248 | 741248 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.11 | ECC_Warehouse - Foundation - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 307443 | 307443 | 307443 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.2 | ECC_Warehouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9019667 | 9019667 | 9019667 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.3 | ECC_Warehouse - Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 908638 | 908638 | 908638 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.4 | ECC_Warehouse - Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 805254 | 805254 | 805254 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.5 | ECC_Warehouse - Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175697 | 175697 | 175697 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.6 | ECC_Warehouse - Foundation - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2290885 | 2290885 | 2290885 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.7 | ECC_Warehouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1141183 | 1141183 | 1141183 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.8 | ECC_Warehouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7752858 | 7752858 | 7752858 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.1.9 | ECC_Warehouse - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39828 | 39828 | 39828 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.2.1 | ECC_Warehouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 735895 | 588716 | 441537 | 147179 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.2.2 | ECC_Warehouse - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2043292 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.3.1 | ECC_Warehouse - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2518573 | 2518573 | 2518573 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.4.1 | ECC_Warehouse - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 49584 | 49584 | 0 | 49584 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.4.2 | ECC_Warehouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 293833 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.4.3 | ECC_Warehouse - Finishing - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3777859 | 3400073 | 3400073 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.4.4 | ECC_Warehouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2361162 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.4.5 | ECC_Warehouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1853967 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.5.1 | ECC_Warehouse - Plumbing & Sanitary - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 20901202 | 10450601 | 0 | 10450601 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.5.2 | ECC_Warehouse - Plumbing & Sanitary - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 5736020 | 5162418 | 3441612 | 1720806 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.5.3 | ECC_Warehouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1937983 | 1550386 | 1162790 | 387596 | 1 | 3500235911 | 36018314
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.6.1 | ECC_Warehouse - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 390886 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.6.2 | ECC_Warehouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 625423 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JA | Construction - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | ECC.I.8.D.6.3 | ECC_Warehouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 745425 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.1 | ECC_Carpark - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6502116 | 6502116 | 6502116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.10 | ECC_Carpark - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1236883 | 1236883 | 1236883 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.11 | ECC_Carpark - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 513014 | 513014 | 513014 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.2 | ECC_Carpark - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8578412 | 8578412 | 8578412 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.3 | ECC_Carpark - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1527862 | 1527862 | 1527862 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.4 | ECC_Carpark - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1333856 | 1333856 | 1333856 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.5 | ECC_Carpark - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 312903 | 312903 | 312903 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.6 | ECC_Carpark - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2966529 | 2966529 | 2966529 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.7 | ECC_Carpark - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1477749 | 1477749 | 1477749 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.8 | ECC_Carpark - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5246507 | 5246507 | 5246507 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.1.9 | ECC_Carpark - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66459 | 66459 | 66459 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.2.1 | ECC_Carpark - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3916360 | 3916360 | 0 | 3916360 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.3.1 | ECC_Carpark - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3939951 | 3939951 | 3939951 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.4.1 | ECC_Carpark - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5909926 | 5909926 | 5318933 | 590993 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.E.5.1 | ECC_Carpark - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 11964256 | 10767830 | 10767830 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.1 | ECC_Mosque - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 23660748 | 23660748 | 23660748 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.2 | ECC_Mosque - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17837855 | 17837855 | 17837855 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.3 | ECC_Mosque - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3356893 | 3356893 | 3356893 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.4 | ECC_Mosque - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2848390 | 2848390 | 2848390 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.5 | ECC_Mosque - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 758734 | 758734 | 758734 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.6 | ECC_Mosque - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7068251 | 7068251 | 7068251 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.7 | ECC_Mosque - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3520985 | 3520985 | 3520985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.1.8 | ECC_Mosque - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34413907 | 34413907 | 34413907 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.2.1 | ECC_Mosque - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11445541 | 11445541 | 11445541 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.3.1 | ECC_Mosque - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15401144 | 15401144 | 15401144 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.4.1 | ECC_Mosque - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 5998198 | 4798558 | 4198739 | 599819 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.4.2 | ECC_Mosque - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7344732 | 7344732 | 6610259 | 734473 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.4.3 | ECC_Mosque - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 5406590 | 4865931 | 4865931 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.4.4 | ECC_Mosque - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 7405938 | 6665344 | 6665344 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.5.1 | ECC_Mosque - Potable Water (Faucet, PVC Pipe, fitting, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 48762135 | 39009708 | 0 | 39009708 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.5.2 | ECC_Mosque - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 13382034 | 12043831 | 8029220 | 4014611 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.5.3 | ECC_Mosque - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4521281 | 4521281 | 2712769 | 1808512 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.6.1 | ECC_Mosque - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2188651 | 2188651 | 0 | 2188651 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.6.2 | ECC_Mosque - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1094309 | 1094309 | 0 | 1094309 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.F.6.3 | ECC_Mosque - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4347658 | 4347658 | 3043361 | 1304297 | 1 | 3500235911 | 55261733
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.1 | ECC_Storage - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3449426 | 3449426 | 3449426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.10 | ECC_Storage - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 922811 | 922811 | 922811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.11 | ECC_Storage - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 382749 | 382749 | 382749 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.2 | ECC_Storage - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4550918 | 4550918 | 4550918 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.3 | ECC_Storage - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 935785 | 935785 | 935785 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.4 | ECC_Storage - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 815711 | 815711 | 815711 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.5 | ECC_Storage - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 192728 | 192728 | 192728 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.6 | ECC_Storage - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1466929 | 1466929 | 1466929 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.7 | ECC_Storage - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 730737 | 730737 | 730737 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.8 | ECC_Storage - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3251073 | 3251073 | 3251073 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.1.9 | ECC_Storage - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 49584 | 49584 | 49584 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.2.1 | ECC_Storage - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1986898 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.3.1 | ECC_Storage - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1763705 | 1763705 | 1763705 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.4.1 | ECC_Storage - Steel Structure Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2645558 | 2381002 | 2381002 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.4.2 | ECC_Storage - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1224795 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.8.G.5.1 | ECC_Storage - Strom Water (Gutter, Downspout Pipe, Clamp, etc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 8926264 | 5355758 | 5355758 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.1 | ECC_Pit & Pond - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1071200 | 1071200 | 1071200 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.10 | ECC_Pit & Pond - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 81928 | 81928 | 81928 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.2 | ECC_Pit & Pond - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1009473 | 1009473 | 1009473 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.3 | ECC_Pit & Pond - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 254268 | 254268 | 254268 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.4 | ECC_Pit & Pond - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 157509 | 157509 | 157509 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.5 | ECC_Pit & Pond - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 107925 | 107925 | 107925 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.6 | ECC_Pit & Pond - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 113887 | 113887 | 113887 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.7 | ECC_Pit & Pond - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56732 | 56732 | 56732 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.8 | ECC_Pit & Pond - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1440019 | 1440019 | 1440019 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.HQ | Construction - GENERAL SERVICES FACILITIES | ECC.I.9.A.1.9 | ECC_Pit & Pond - Waterproofing Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 860249 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.1 | ECC_Lighting Pole Foundation - Concrete for Non Structural | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 268275 | 268275 | 174379 | 93896 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.2 | ECC_Lighting Pole Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 246358 | 246358 | 160133 | 86225 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.3 | ECC_Lighting Pole Foundation - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 379944 | 379944 | 246964 | 132980 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.4 | ECC_Lighting Pole Foundation - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 399219 | 399219 | 259492 | 139727 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.5 | ECC_Lighting Pole Foundation - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19321 | 19321 | 12559 | 6762 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.6 | ECC_Lighting Pole Foundation - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27837 | 27837 | 18094 | 9743 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.7 | ECC_Lighting Pole Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27733 | 27733 | 18026 | 9707 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.8 | ECC_Lighting Pole Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 563512 | 563512 | 366283 | 197229 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.JC | Construction - LIGHTING SYSTEM | ECC.I.9.B.1.9 | ECC_Lighting Pole Foundation - Anchor Bolt M12 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 143077 | 143077 | 93000 | 50077 | 1 | 3500235911 | 726346
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.1 | ECC_Lightning Protection - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63536 | 63536 | 63536 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.10 | ECC_Lightning Protection - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 38572 | 38572 | 38572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.11 | ECC_Lightning Protection - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20482 | 20482 | 20482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.2 | ECC_Lightning Protection - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 59874 | 59874 | 59874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.3 | ECC_Lightning Protection - Anchor Bolt M16 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27218 | 27218 | 27218 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.4 | ECC_Lightning Protection - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11711 | 11711 | 11711 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.5 | ECC_Lightning Protection - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8953 | 8953 | 8953 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.6 | ECC_Lightning Protection - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3499 | 3499 | 3499 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.7 | ECC_Lightning Protection - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4132 | 4132 | 4132 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.8 | ECC_Lightning Protection - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4116 | 4116 | 4116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.I.9.C.1.9 | ECC_Lightning Protection - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 498 | 498 | 498 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.1 | ECC_Pipe Sleeper - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2303163 | 2303163 | 2303163 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.10 | ECC_Pipe Sleeper - Pile Head Treatment (PHT) PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 296991 | 296991 | 296991 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.2 | ECC_Pipe Sleeper - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2170446 | 2170446 | 2170446 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.3 | ECC_Pipe Sleeper - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 863218 | 863218 | 863218 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.4 | ECC_Pipe Sleeper - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 794223 | 794223 | 794223 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.5 | ECC_Pipe Sleeper - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 141600 | 141600 | 141600 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.6 | ECC_Pipe Sleeper - Sand bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 215669 | 215669 | 215669 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.7 | ECC_Pipe Sleeper - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 214867 | 214867 | 214867 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.8 | ECC_Pipe Sleeper - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2604208 | 2604208 | 2604208 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1C.DO | Construction - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | ECC.I.9.D.1.9 | ECC_Pipe Sleeper - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 62373 | 62373 | 62373 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.1 | ECC_Road & Paving - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 24756399 | 19805119 | 7426920 | 12378199 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.2 | ECC_Road & Paving - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 3266344 | 3103027 | 979903 | 2123124 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.3 | ECC_Road & Paving - Soil Backfill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 724757 | 724757 | 217427 | 507330 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.4 | ECC_Road & Paving - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2511373 | 2260236 | 753412 | 1506824 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.5 | ECC_Road & Paving - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 2820573 | 2256458 | 846172 | 1410286 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.6 | ECC_Road & Paving - Welded Wiremesh M8 @ 150 X 150 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 9175670 | 7340536 | 2752701 | 4587835 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.7 | ECC_Road & Paving - Polyethylene Sheet 0.15 mm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 303006 | 242405 | 90902 | 151503 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.8 | ECC_Road & Paving - Kansteen, L = 60 cm, W = 45 cm, H = 24 cm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.3 | 2560508 | 768152 | 384076 | 384076 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.AN | Construction - ACCESS ROAD & ROAD WORKS | ECC.I.9.E.1.9 | ECC_Road & Paving - Gravel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1720800 | 1376640 | 516240 | 860400 | 1 | 3500235911 | 1244131185
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.1 | ECC_Open Ditch for Storm Water System - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2591059 | 2591059 | 2591059 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.2 | ECC_Open Ditch for Storm Water System - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1533121 | 1533121 | 1533121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.3 | ECC_Open Ditch for Storm Water System - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1162100 | 1162100 | 1162100 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.4 | ECC_Open Ditch for Storm Water System - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2529522 | 2529522 | 2529522 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.5 | ECC_Open Ditch for Storm Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6750913 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.6 | ECC_Open Ditch for Storm Water System - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1361651 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.1.7 | ECC_Open Ditch for Storm Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 6063363 | 5942096 | 5153859 | 788237 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.1 | ECC_Open Ditch & RC Pipe for Oily Water System - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 108384 | 108384 | 86707 | 21677 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.2 | ECC_Open Ditch & RC Pipe for Oily Water System - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67638 | 67638 | 54110 | 13528 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.3 | ECC_Open Ditch & RC Pipe for Oily Water System - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45573 | 45573 | 36458 | 9115 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.4 | ECC_Open Ditch & RC Pipe for Oily Water System - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 99654 | 99654 | 79723 | 19931 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.5 | ECC_Open Ditch & RC Pipe for Oily Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 305817 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.6 | ECC_Open Ditch & RC Pipe for Oily Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 237593 | 213834 | 190074 | 23760 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.2.7 | ECC_Open Ditch & RC Pipe for Oily Water System - Waterproofing Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 983142 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.1 | ECC_Manhole for Storm Water System - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 108379 | 108379 | 97541 | 10838 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.2 | ECC_Manhole for Storm Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 102134 | 102134 | 91921 | 10213 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.3 | ECC_Manhole for Storm Water System - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48282 | 48282 | 43454 | 4828 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.4 | ECC_Manhole for Storm Water System - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 44486 | 44486 | 40037 | 4449 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.5 | ECC_Manhole for Storm Water System - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7866 | 7866 | 7079 | 787 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.6 | ECC_Manhole for Storm Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8716 | 8716 | 7844 | 872 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.3.7 | ECC_Manhole for Storm Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 165940 | 165940 | 149346 | 16594 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.4.1 | ECC_Culvert for Storm Water System - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56041 | 56041 | 56041 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.4.2 | ECC_Culvert for Storm Water System - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31426 | 31426 | 31426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.4.3 | ECC_Culvert for Storm Water System - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26636 | 26636 | 26636 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.4.4 | ECC_Culvert for Storm Water System - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177245 | 177245 | 177245 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.4.5 | ECC_Culvert for Storm Water System - RC Pipe 500 @2.4m | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64739 | 64739 | 58265 | 6474 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.1 | ECC_Around Building & Shelter - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1491205 | 1491205 | 1192964 | 298241 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.2 | ECC_Around Building & Shelter - Soil Cut | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 386373 | 386373 | 309098 | 77275 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.3 | ECC_Around Building & Shelter - Soil BackFill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 142885 | 142885 | 114308 | 28577 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.4 | ECC_Around Building & Shelter - Soil Disposal | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 247557 | 247557 | 198046 | 49511 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.5 | ECC_Around Building & Shelter - Sand Bedding | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 754097 | 754097 | 603278 | 150819 | 1 | 3500235911 | 1535726
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0C.GG | Construction - DRAINAGE TUNNEL AND CHANNELS | ECC.I.9.F.5.6 | ECC_Around Building & Shelter - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2480789 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.1 | ECC_Engine (Dual Fuel) A - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 640180835 | 640180835 | 640180835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.2 | ECC_Engine (Dual Fuel) A - Engine Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600452088 | 1600452088 | 1600452088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.3 | ECC_Engine (Dual Fuel) A - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.4 | ECC_Engine (Dual Fuel) A - Driver Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.5 | ECC_Engine (Dual Fuel) A - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.6 | ECC_Engine (Dual Fuel) A - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.7 | ECC_Engine (Dual Fuel) A - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.8 | ECC_Engine (Dual Fuel) A - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 80022604 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.1.9 | ECC_Engine (Dual Fuel) A - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 80022604 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.1 | ECC_Electric Generator E - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175760242 | 175760242 | 175760242 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.2 | ECC_Electric Generator E - Generator Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439400606 | 439400606 | 439400606 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.3 | ECC_Electric Generator E - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.4 | ECC_Electric Generator E - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.5 | ECC_Electric Generator E - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 43940061 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.6 | ECC_Electric Generator E - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 0 | 21970030 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.10.7 | ECC_Electric Generator E - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 21970030 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.1 | ECC_Engine (Dual Fuel) B - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 640180835 | 640180835 | 640180835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.2 | ECC_Engine (Dual Fuel) B - Engine Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600452088 | 1600452088 | 1600452088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.3 | ECC_Engine (Dual Fuel) B - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.4 | ECC_Engine (Dual Fuel) B - Driver Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.5 | ECC_Engine (Dual Fuel) B - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.6 | ECC_Engine (Dual Fuel) B - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.7 | ECC_Engine (Dual Fuel) B - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 80022605 | 80022604 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.8 | ECC_Engine (Dual Fuel) B - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 72020344 | 8002260 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.2.9 | ECC_Engine (Dual Fuel) B - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 40011302 | 40011302 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.1 | ECC_Engine (Dual Fuel) C - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 640180835 | 640180835 | 640180835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.2 | ECC_Engine (Dual Fuel) C - Engine Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600452088 | 1600452088 | 1600452088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.3 | ECC_Engine (Dual Fuel) C - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.4 | ECC_Engine (Dual Fuel) C - Driver Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.5 | ECC_Engine (Dual Fuel) C - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.6 | ECC_Engine (Dual Fuel) C - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.7 | ECC_Engine (Dual Fuel) C - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 0 | 160045209 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.8 | ECC_Engine (Dual Fuel) C - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 56015823 | 24006781 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.3.9 | ECC_Engine (Dual Fuel) C - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 0 | 80022604 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.1 | ECC_Engine (Dual Fuel) D - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 640180835 | 640180835 | 640180835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.2 | ECC_Engine (Dual Fuel) D - Engine Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600452088 | 1600452088 | 1600452088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.3 | ECC_Engine (Dual Fuel) D - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.4 | ECC_Engine (Dual Fuel) D - Driver Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.5 | ECC_Engine (Dual Fuel) D - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.6 | ECC_Engine (Dual Fuel) D - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.7 | ECC_Engine (Dual Fuel) D - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 160045209 | 80022605 | 0 | 80022605 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.8 | ECC_Engine (Dual Fuel) D - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 40011302 | 40011302 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.4.9 | ECC_Engine (Dual Fuel) D - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 80022604 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.1 | ECC_Engine (Dual Fuel) E - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 640180835 | 640180835 | 640180835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.2 | ECC_Engine (Dual Fuel) E - Engine Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600452088 | 1600452088 | 1600452088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.3 | ECC_Engine (Dual Fuel) E - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.4 | ECC_Engine (Dual Fuel) E - Driver Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.5 | ECC_Engine (Dual Fuel) E - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 128036167 | 32009042 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.6 | ECC_Engine (Dual Fuel) E - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160045209 | 160045209 | 160045209 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.7 | ECC_Engine (Dual Fuel) E - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 160045209 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.8 | ECC_Engine (Dual Fuel) E - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80022604 | 80022604 | 24006781 | 56015823 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.1.5.9 | ECC_Engine (Dual Fuel) E - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 80022604 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.1 | ECC_Electric Generator A - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175760242 | 175760242 | 175760242 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.2 | ECC_Electric Generator A - Generator Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439400606 | 439400606 | 439400606 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.3 | ECC_Electric Generator A - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.4 | ECC_Electric Generator A - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.5 | ECC_Electric Generator A - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43940061 | 43940061 | 43940061 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.6 | ECC_Electric Generator A - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 21970030 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.6.7 | ECC_Electric Generator A - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 21970030 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.1 | ECC_Electric Generator B - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175760242 | 175760242 | 175760242 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.2 | ECC_Electric Generator B - Generator Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439400606 | 439400606 | 439400606 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.3 | ECC_Electric Generator B - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.4 | ECC_Electric Generator B - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.5 | ECC_Electric Generator B - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43940061 | 43940061 | 21970031 | 21970030 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.6 | ECC_Electric Generator B - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 15379021 | 6591009 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.7.7 | ECC_Electric Generator B - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 10985015 | 10985015 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.1 | ECC_Electric Generator C - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175760242 | 175760242 | 175760242 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.2 | ECC_Electric Generator C - Generator Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439400606 | 439400606 | 439400606 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.3 | ECC_Electric Generator C - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.4 | ECC_Electric Generator C - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.5 | ECC_Electric Generator C - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43940061 | 43940061 | 0 | 43940061 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.6 | ECC_Electric Generator C - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 10985015 | 10985015 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.8.7 | ECC_Electric Generator C - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 0 | 21970030 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.1 | ECC_Electric Generator D - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175760242 | 175760242 | 175760242 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.2 | ECC_Electric Generator D - Generator Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 439400606 | 439400606 | 439400606 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.3 | ECC_Electric Generator D - Check Elevation & Leveling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.4 | ECC_Electric Generator D - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87880121 | 87880121 | 87880121 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.5 | ECC_Electric Generator D - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 43940061 | 21970031 | 0 | 21970031 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.6 | ECC_Electric Generator D - Aux. Equipment & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21970030 | 21970030 | 10985015 | 10985015 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.II.1.1.9.7 | ECC_Electric Generator D - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 21970030 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.1 | ECC_HT Cooling Water Radiator - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229140679 | 229140679 | 229140679 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.2 | ECC_HT Cooling Water Radiator - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 572851697 | 572851697 | 572851697 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.3 | ECC_HT Cooling Water Radiator - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114570339 | 114570339 | 114570339 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.4 | ECC_HT Cooling Water Radiator - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114570339 | 114570339 | 114570339 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.5 | ECC_HT Cooling Water Radiator - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 57285170 | 57285170 | 57285170 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.1.6 | ECC_HT Cooling Water Radiator - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 57285170 | 57285170 | 57285170 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.1 | ECC_LT Cooling Water Radiator - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120026070 | 120026070 | 120026070 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.2 | ECC_LT Cooling Water Radiator - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 300065175 | 300065175 | 300065175 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.3 | ECC_LT Cooling Water Radiator - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 60013035 | 60013035 | 60013035 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.4 | ECC_LT Cooling Water Radiator - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 60013035 | 60013035 | 60013035 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.5 | ECC_LT Cooling Water Radiator - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30006517 | 30006517 | 30006517 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.2.6 | ECC_LT Cooling Water Radiator - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30006517 | 30006517 | 30006517 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.1 | ECC_HT Cooling Water Expansion Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8456382 | 8456382 | 8456382 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.2 | ECC_HT Cooling Water Expansion Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21140955 | 21140955 | 21140955 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.3 | ECC_HT Cooling Water Expansion Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4228191 | 4228191 | 4228191 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.4 | ECC_HT Cooling Water Expansion Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4228191 | 4228191 | 4228191 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.5 | ECC_HT Cooling Water Expansion Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2114096 | 2114096 | 2114096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.3.6 | ECC_HT Cooling Water Expansion Tank - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2114096 | 2114096 | 2114096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.1 | ECC_LT Cooling Water Expansion Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8456382 | 8456382 | 8456382 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.2 | ECC_LT Cooling Water Expansion Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21140955 | 21140955 | 21140955 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.3 | ECC_LT Cooling Water Expansion Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4228191 | 4228191 | 4228191 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.4 | ECC_LT Cooling Water Expansion Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4228191 | 4228191 | 4228191 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.5 | ECC_LT Cooling Water Expansion Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2114096 | 2114096 | 2114096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.4.6 | ECC_LT Cooling Water Expansion Tank - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2114096 | 2114096 | 2114096 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.1 | ECC_Cooling Water Maintenace Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5373894 | 5373894 | 5373894 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.2 | ECC_Cooling Water Maintenace Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13434736 | 13434736 | 13434736 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.3 | ECC_Cooling Water Maintenace Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2686947 | 2686947 | 2686947 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.4 | ECC_Cooling Water Maintenace Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2686947 | 2686947 | 2686947 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.5 | ECC_Cooling Water Maintenace Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1343474 | 1343474 | 1343474 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.5.6 | ECC_Cooling Water Maintenace Tank - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1343474 | 1343474 | 1343474 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.1 | ECC_Cooling Water Maintenance Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10747789 | 10747789 | 10747789 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.2 | ECC_Cooling Water Maintenance Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26869472 | 26869472 | 26869472 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.3 | ECC_Cooling Water Maintenance Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5373894 | 5373894 | 5373894 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.4 | ECC_Cooling Water Maintenance Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5373894 | 5373894 | 5373894 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.5 | ECC_Cooling Water Maintenance Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2686947 | 2686947 | 2686947 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.FR | Construction - COOLING WATER SYSTEM | ECC.II.1.2.6.6 | ECC_Cooling Water Maintenance Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2686947 | 2686947 | 2686947 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.1 | ECC_Lube Oil Cooler - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 147757189 | 147757189 | 147757189 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.2 | ECC_Lube Oil Cooler - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 369392972 | 369392972 | 369392972 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.3 | ECC_Lube Oil Cooler - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 73878594 | 73878594 | 73878594 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.4 | ECC_Lube Oil Cooler - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 73878594 | 73878594 | 73878594 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.5 | ECC_Lube Oil Cooler - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36939297 | 36939297 | 36939297 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.3.1.6 | ECC_Lube Oil Cooler - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36939297 | 36939297 | 36939297 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.1 | ECC_Charge Air System/Air Intake System - Auto Filter - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 164974 | 164974 | 164974 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.2 | ECC_Charge Air System/Air Intake System - Auto Filter - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 412434 | 412434 | 412434 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.3 | ECC_Charge Air System/Air Intake System - Auto Filter - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 82487 | 82487 | 82487 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.4 | ECC_Charge Air System/Air Intake System - Auto Filter - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 82487 | 82487 | 82487 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.5 | ECC_Charge Air System/Air Intake System - Auto Filter - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41243 | 41243 | 24746 | 16497 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.1.6 | ECC_Charge Air System/Air Intake System - Auto Filter - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41243 | 41243 | 24746 | 16497 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.1 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4795745 | 4795745 | 4795745 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.2 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11989362 | 11989362 | 11989362 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.3 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2397872 | 2397872 | 2397872 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.4 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2397872 | 2397872 | 2397872 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.5 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1198936 | 1198936 | 1198936 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.2.6 | ECC_Charge Air System/Air Intake System - Intake Air Filter with silencer - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1198936 | 1198936 | 1198936 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.1 | ECC_Charge Air System/Air Intake System - Intake Air Duct - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1133714 | 1133714 | 1133714 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.2 | ECC_Charge Air System/Air Intake System - Intake Air Duct - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2834285 | 2834285 | 2834285 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.3 | ECC_Charge Air System/Air Intake System - Intake Air Duct - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 566857 | 566857 | 566857 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.4 | ECC_Charge Air System/Air Intake System - Intake Air Duct - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 566857 | 566857 | 566857 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.5 | ECC_Charge Air System/Air Intake System - Intake Air Duct - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 283429 | 283429 | 170057 | 113372 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.3.6 | ECC_Charge Air System/Air Intake System - Intake Air Duct - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 283429 | 283429 | 170057 | 113372 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.1 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 422026 | 422026 | 422026 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.2 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1055064 | 1055064 | 1055064 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.3 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 211013 | 211013 | 211013 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.4 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 211013 | 211013 | 211013 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.5 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 105506 | 105506 | 63304 | 42202 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.1.4.4.6 | ECC_Charge Air System/Air Intake System - Expansion joint for TC inlet - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 105506 | 105506 | 63304 | 42202 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.1 | ECC_Exhaust Gas Silencer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7549223 | 7549223 | 7549223 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.2 | ECC_Exhaust Gas Silencer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18873057 | 18873057 | 18873057 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.3 | ECC_Exhaust Gas Silencer - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3774611 | 3774611 | 3774611 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.4 | ECC_Exhaust Gas Silencer - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3774611 | 3774611 | 3774611 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.5 | ECC_Exhaust Gas Silencer - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1887306 | 1887306 | 1887306 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.1.6 | ECC_Exhaust Gas Silencer - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1887306 | 1887306 | 1887306 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.1 | ECC_Exhaust Gas Duct - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2510037 | 2510037 | 2510037 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.2 | ECC_Exhaust Gas Duct - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6275092 | 6275092 | 3765055 | 2510037 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.3 | ECC_Exhaust Gas Duct - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1255018 | 1255018 | 753011 | 502007 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.4 | ECC_Exhaust Gas Duct - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1255018 | 1255018 | 753011 | 502007 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.5 | ECC_Exhaust Gas Duct - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 627509 | 564758 | 376505 | 188253 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.2.6 | ECC_Exhaust Gas Duct - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 627509 | 627509 | 376505 | 251004 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.1 | ECC_Exhaust Gas Stack - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4706319 | 4706319 | 4706319 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.2 | ECC_Exhaust Gas Stack - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11765798 | 11765798 | 11765798 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.3 | ECC_Exhaust Gas Stack - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2353160 | 2353160 | 2353160 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.4 | ECC_Exhaust Gas Stack - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2353160 | 2353160 | 2353160 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.5 | ECC_Exhaust Gas Stack - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1176580 | 1176580 | 1176580 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.3.6 | ECC_Exhaust Gas Stack - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1176580 | 1176580 | 1176580 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.1 | ECC_Exhaust Gas Vent Fan - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 79633 | 79633 | 79633 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.2 | ECC_Exhaust Gas Vent Fan - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 199083 | 199083 | 199083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.3 | ECC_Exhaust Gas Vent Fan - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39817 | 39817 | 39817 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.4 | ECC_Exhaust Gas Vent Fan - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39817 | 39817 | 39817 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.5 | ECC_Exhaust Gas Vent Fan - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19908 | 19908 | 19908 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.4.6 | ECC_Exhaust Gas Vent Fan - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19908 | 19908 | 19908 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.1 | ECC_Expansion Joint for TC outlet #1 - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 350386 | 350386 | 350386 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.2 | ECC_Expansion Joint for TC outlet #1 - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 875965 | 875965 | 350386 | 525579 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.3 | ECC_Expansion Joint for TC outlet #1 - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175193 | 175193 | 70077 | 105116 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.4 | ECC_Expansion Joint for TC outlet #1 - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175193 | 175193 | 70077 | 105116 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.5 | ECC_Expansion Joint for TC outlet #1 - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87596 | 87596 | 35038 | 52558 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.GP | Construction - EXHAUST SYSTEM | ECC.II.1.5.5.6 | ECC_Expansion Joint for TC outlet #1 - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87596 | 87596 | 35038 | 52558 | 1 | 3500235911 | 4794235
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.6.1.1.2 | ECC_All Necessary Pipe Works, Flange And Coupling - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 88368253 | 86600888 | 75113015 | 11487873 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.6.1.2.1 | ECC_All Necessary Pipe Works, Flange And Coupling - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65786697 | 65786697 | 65786697 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.6.1.2.2 | ECC_All Necessary Pipe Works, Flange And Coupling - Largebore Piping Works ( = 2") - Piping Installation & Welding Work | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 65786697 | 64470963 | 55918692 | 8552271 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.6.2.1 | ECC_All Necessary Pipe Works, Flange And Coupling - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 786334 | 747017 | 550434 | 196583 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.1.6.3.1 | ECC_All Necessary Pipe Works, Flange And Coupling - NDE works (e.g RT, penetrant test etc as per piping standard and COD | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 7709160 | 7554977 | 6552786 | 1002191 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.1.1 | ECC_Administration Building VAC - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 466245 | 466245 | 466245 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.1.2 | ECC_Administration Building VAC - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1631859 | 1631859 | 1468673 | 163186 | 1 | 3500235911 | 467095
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.1.3 | ECC_Administration Building VAC - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 233123 | 233123 | 0 | 233123 | 1 | 3500235911 | 467095
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.2.1 | ECC_Ventilation System of Ware House - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11326 | 11326 | 5663 | 5663 | 1 | 3500235911 | 467095
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.2.2 | ECC_Ventilation System of Ware House - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 39640 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.2.3 | ECC_Ventilation System of Ware House - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 5663 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.3.1 | ECC_Ventilation System of Work Shop and Air Condition System for workshop office & warehouse & laboratory - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 130247 | 130247 | 65124 | 65123 | 1 | 3500235911 | 467095
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.3.2 | ECC_Ventilation System of Work Shop and Air Condition System for workshop office & warehouse & laboratory - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 455863 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.3.3 | ECC_Ventilation System of Work Shop and Air Condition System for workshop office & warehouse & laboratory - Test & Inspe | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 65123 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.4.1 | ECC_VAC for Switchyard Control Building - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3784705 | 3784705 | 3784705 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.4.2 | ECC_VAC for Switchyard Control Building - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13246468 | 13246468 | 11921821 | 1324647 | 1 | 3500235911 | 11460861
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.4.3 | ECC_VAC for Switchyard Control Building - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1892353 | 1892353 | 0 | 1892353 | 1 | 3500235911 | 11460861
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.5.1 | ECC_Other items specified in the specification and scope of work and other accessories required for system operation - P | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9698661 | 9698661 | 9698661 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.5.2 | ECC_Other items specified in the specification and scope of work and other accessories required for system operation - I | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33945312 | 33945312 | 30550781 | 3394531 | 1 | 3500235911 | 11460861
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.IC | Construction - HVAC SYSTEM | ECC.II.10.1.5.3 | ECC_Other items specified in the specification and scope of work and other accessories required for system operation - T | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4849330 | 4849330 | 0 | 4849330 | 1 | 3500235911 | 11460861
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.1 | ECC_Fuel Oil Daily Storage Tank - Tank Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56482358 | 56482358 | 56482358 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.2 | ECC_Fuel Oil Daily Storage Tank - Bottom & Annular/Sketch Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56482358 | 56482358 | 56482358 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.3 | ECC_Fuel Oil Daily Storage Tank - 1St Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56482358 | 56482358 | 56482358 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.4 | ECC_Fuel Oil Daily Storage Tank - 2Nd Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56482358 | 56482358 | 56482358 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.5 | ECC_Fuel Oil Daily Storage Tank - 3Rd Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37654906 | 37654906 | 37654906 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.6 | ECC_Fuel Oil Daily Storage Tank - 4Th-5Th Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37654906 | 37654906 | 37654906 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.7 | ECC_Fuel Oil Daily Storage Tank - Roof Plate & Structure/Top Angle | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37654906 | 37654906 | 37654906 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.8 | ECC_Fuel Oil Daily Storage Tank - Tank Accessory Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18827453 | 18827453 | 18827453 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.1.9 | ECC_Fuel Oil Daily Storage Tank - Test , Clean Up & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18827453 | 18827453 | 18827453 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.1 | ECC_Fuel Oil Water-Separator - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14699417 | 14699417 | 14699417 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.2 | ECC_Fuel Oil Water-Separator - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36748543 | 36748543 | 36748543 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.3 | ECC_Fuel Oil Water-Separator - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7349709 | 7349709 | 7349709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.4 | ECC_Fuel Oil Water-Separator - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7349709 | 7349709 | 7349709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.5 | ECC_Fuel Oil Water-Separator - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3674854 | 3674854 | 3674854 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.10.6 | ECC_Fuel Oil Water-Separator - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3674854 | 3674854 | 3674854 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.1 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20044660 | 20044660 | 20044660 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.2 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50111650 | 50111650 | 50111650 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.3 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10022330 | 10022330 | 10022330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.4 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10022330 | 10022330 | 10022330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.5 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5011165 | 5011165 | 5011165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.2.6 | ECC_Fuel Oil Pilot and Clean Leakage Tanks - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5011165 | 5011165 | 5011165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.1 | ECC_Fuel Oil Dirty Oil Tanks - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20044660 | 20044660 | 20044660 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.2 | ECC_Fuel Oil Dirty Oil Tanks - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50111650 | 50111650 | 50111650 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.3 | ECC_Fuel Oil Dirty Oil Tanks - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10022330 | 10022330 | 10022330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.4 | ECC_Fuel Oil Dirty Oil Tanks - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10022330 | 10022330 | 10022330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.5 | ECC_Fuel Oil Dirty Oil Tanks - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5011165 | 5011165 | 5011165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.3.6 | ECC_Fuel Oil Dirty Oil Tanks - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5011165 | 5011165 | 5011165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.1 | ECC_Fuel Oil Transfer Pumps - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4677087 | 4677087 | 4677087 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.2 | ECC_Fuel Oil Transfer Pumps - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11692718 | 11692718 | 11692718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.3 | ECC_Fuel Oil Transfer Pumps - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2338544 | 2338544 | 2338544 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.4 | ECC_Fuel Oil Transfer Pumps - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2338544 | 2338544 | 2338544 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.5 | ECC_Fuel Oil Transfer Pumps - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1169272 | 1169272 | 1169272 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.4.6 | ECC_Fuel Oil Transfer Pumps - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1169272 | 1169272 | 1169272 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.1 | ECC_Fuel Oil Forwarding Pumps - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14098078 | 14098078 | 14098078 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.2 | ECC_Fuel Oil Forwarding Pumps - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35245194 | 35245194 | 35245194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.3 | ECC_Fuel Oil Forwarding Pumps - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7049039 | 7049039 | 7049039 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.4 | ECC_Fuel Oil Forwarding Pumps - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7049039 | 7049039 | 7049039 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.5 | ECC_Fuel Oil Forwarding Pumps - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3524519 | 3524519 | 3524519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.5.6 | ECC_Fuel Oil Forwarding Pumps - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3524519 | 3524519 | 3524519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.1 | ECC_Pilot Oil Supply Pumps - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14098078 | 14098078 | 14098078 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.2 | ECC_Pilot Oil Supply Pumps - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35245194 | 35245194 | 35245194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.3 | ECC_Pilot Oil Supply Pumps - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7049039 | 7049039 | 7049039 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.4 | ECC_Pilot Oil Supply Pumps - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7049039 | 7049039 | 7049039 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.5 | ECC_Pilot Oil Supply Pumps - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3524519 | 3524519 | 3524519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.6.6 | ECC_Pilot Oil Supply Pumps - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3524519 | 3524519 | 3524519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.1 | ECC_Fo Clean & Pilot Leakage Pumps - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11893165 | 11893165 | 11893165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.2 | ECC_Fo Clean & Pilot Leakage Pumps - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 29732912 | 29732912 | 29732912 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.3 | ECC_Fo Clean & Pilot Leakage Pumps - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5946582 | 5946582 | 5946582 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.4 | ECC_Fo Clean & Pilot Leakage Pumps - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5946582 | 5946582 | 5946582 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.5 | ECC_Fo Clean & Pilot Leakage Pumps - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2973291 | 2973291 | 2973291 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.7.6 | ECC_Fo Clean & Pilot Leakage Pumps - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2973291 | 2973291 | 2973291 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.1 | ECC_Dirty Oil Pumps - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10957747 | 10957747 | 10957747 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.2 | ECC_Dirty Oil Pumps - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27394369 | 27394369 | 27394369 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.3 | ECC_Dirty Oil Pumps - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5478874 | 5478874 | 5478874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.4 | ECC_Dirty Oil Pumps - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5478874 | 5478874 | 5478874 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.5 | ECC_Dirty Oil Pumps - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2739437 | 2739437 | 2739437 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.8.6 | ECC_Dirty Oil Pumps - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2739437 | 2739437 | 2739437 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.1 | ECC_Pilot Oil Duplex Filters - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 835194 | 835194 | 835194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.2 | ECC_Pilot Oil Duplex Filters - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2087985 | 2087985 | 2087985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.3 | ECC_Pilot Oil Duplex Filters - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 417597 | 417597 | 417597 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.4 | ECC_Pilot Oil Duplex Filters - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 417597 | 417597 | 417597 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.5 | ECC_Pilot Oil Duplex Filters - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 208799 | 208799 | 208799 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.1.9.6 | ECC_Pilot Oil Duplex Filters - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 208799 | 208799 | 208799 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.2.1.1.2 | ECC_Fuel Oil Supply System - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16954984 | 16954984 | 16615884 | 339100 | 1 | 3500235911 | 761144
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.2.1.2.1 | ECC_Fuel Oil Supply System - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12622320 | 12622320 | 12622320 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.2.1.2.2 | ECC_Fuel Oil Supply System - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12622320 | 12622320 | 12369874 | 252446 | 1 | 3500235911 | 761144
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.2.2.1 | ECC_Fuel Oil Supply System - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 159747 | 159747 | 156552 | 3195 | 1 | 3500235911 | 761144
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.JF | Construction - LIQUID FUEL HANDLING SYSTEM | ECC.II.3.2.3.1 | ECC_Fuel Oil Supply System - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3328057 | 3328057 | 3161654 | 166403 | 1 | 3500235911 | 761144
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.1 | ECC_Fuel Gas Coalescing Filter (Common) - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5889416 | 5889416 | 5889416 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.2 | ECC_Fuel Gas Coalescing Filter (Common) - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14723541 | 14723541 | 14723541 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.3 | ECC_Fuel Gas Coalescing Filter (Common) - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2944708 | 2944708 | 0 | 2944708 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.4 | ECC_Fuel Gas Coalescing Filter (Common) - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2944708 | 2944708 | 0 | 2944708 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.5 | ECC_Fuel Gas Coalescing Filter (Common) - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1472354 | 1472354 | 0 | 1472354 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.3.1.6 | ECC_Fuel Gas Coalescing Filter (Common) - Inspection & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1472354 | 1472354 | 0 | 1472354 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.4.1.1.2 | ECC_Fuel Gas System - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16954984 | 16954984 | 11868489 | 5086495 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.4.1.2.1 | ECC_Fuel Gas System - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12622320 | 12622320 | 12622320 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.4.1.2.2 | ECC_Fuel Gas System - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12622320 | 12622320 | 8835624 | 3786696 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.4.2.1 | ECC_Fuel Gas System - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 159747 | 159747 | 63899 | 95848 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.HH | Construction - GAS ENGINE & AUXILIARIES SYSTEM | ECC.II.3.4.3.1 | ECC_Fuel Gas System - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3328057 | 2662446 | 0 | 2662446 | 1 | 3500235911 | 641874059
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.1 | ECC_Starting Air Compressor (Electric) - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5600860 | 5600860 | 5600860 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.2 | ECC_Starting Air Compressor (Electric) - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14002150 | 14002150 | 14002150 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.3 | ECC_Starting Air Compressor (Electric) - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2800430 | 2800430 | 2800430 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.4 | ECC_Starting Air Compressor (Electric) - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2800430 | 2800430 | 2800430 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.5 | ECC_Starting Air Compressor (Electric) - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1400215 | 1400215 | 1400215 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.1.6 | ECC_Starting Air Compressor (Electric) - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1400215 | 1400215 | 1400215 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.1 | ECC_Air Receiver for Engine Starting - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10865668 | 10865668 | 10865668 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.2 | ECC_Air Receiver for Engine Starting - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27164171 | 27164171 | 27164171 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.3 | ECC_Air Receiver for Engine Starting - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5432834 | 5432834 | 5432834 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.4 | ECC_Air Receiver for Engine Starting - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5432834 | 5432834 | 5432834 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.5 | ECC_Air Receiver for Engine Starting - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2716417 | 2716417 | 2716417 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.2.6 | ECC_Air Receiver for Engine Starting - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2716417 | 2716417 | 2716417 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.1 | ECC_Air Dryer and Filter for Engine Control Air - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 257640 | 257640 | 257640 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.2 | ECC_Air Dryer and Filter for Engine Control Air - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 644099 | 644099 | 644099 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.3 | ECC_Air Dryer and Filter for Engine Control Air - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 128820 | 128820 | 128820 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.4 | ECC_Air Dryer and Filter for Engine Control Air - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 128820 | 128820 | 128820 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.5 | ECC_Air Dryer and Filter for Engine Control Air - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64410 | 64410 | 64410 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.3.6 | ECC_Air Dryer and Filter for Engine Control Air - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64410 | 64410 | 64410 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.1 | ECC_Air Receiver for Engine Control Air - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1680258 | 1680258 | 1680258 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.2 | ECC_Air Receiver for Engine Control Air - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4200645 | 4200645 | 4200645 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.3 | ECC_Air Receiver for Engine Control Air - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 840129 | 840129 | 840129 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.4 | ECC_Air Receiver for Engine Control Air - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 840129 | 840129 | 840129 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.5 | ECC_Air Receiver for Engine Control Air - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 420064 | 420064 | 420064 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.1.4.6 | ECC_Air Receiver for Engine Control Air - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 420064 | 420064 | 420064 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.2.1.1.2 | ECC_Compressed Air System - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17729894 | 17729894 | 17375296 | 354598 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.2.1.2.1 | ECC_Compressed Air System - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13199211 | 13199211 | 13199211 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.2.1.2.2 | ECC_Compressed Air System - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13199211 | 13199211 | 12935227 | 263984 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.2.2.1 | ECC_Compressed Air System - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167048 | 167048 | 163707 | 3341 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1M.KZ | Construction - SERVICE & CONTROL AIR SYSTEM | ECC.II.4.2.3.1 | ECC_Compressed Air System - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1392065 | 1392065 | 1364224 | 27841 | 1 | 3500235911 | 993906
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.1 | ECC_Portable Oily Water Pit Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 170411 | 170411 | 170411 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.2 | ECC_Portable Oily Water Pit Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 426028 | 426028 | 0 | 426028 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.3 | ECC_Portable Oily Water Pit Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85206 | 85206 | 0 | 85206 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.4 | ECC_Portable Oily Water Pit Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85206 | 85206 | 0 | 85206 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.5 | ECC_Portable Oily Water Pit Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42603 | 42603 | 0 | 42603 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.1.6 | ECC_Portable Oily Water Pit Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42603 | 42603 | 0 | 42603 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.1 | ECC_Oil Skimmer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3067404 | 3067404 | 3067404 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.2 | ECC_Oil Skimmer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7668511 | 7668511 | 0 | 7668511 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.3 | ECC_Oil Skimmer - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1533702 | 1533702 | 0 | 1533702 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.4 | ECC_Oil Skimmer - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1533702 | 1533702 | 0 | 1533702 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.5 | ECC_Oil Skimmer - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 766851 | 766851 | 0 | 766851 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.2.6 | ECC_Oil Skimmer - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 766851 | 766851 | 0 | 766851 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.1 | ECC_Sludge Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 340823 | 340823 | 340823 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.2 | ECC_Sludge Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 852057 | 852057 | 0 | 852057 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.3 | ECC_Sludge Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 170411 | 170411 | 0 | 170411 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.4 | ECC_Sludge Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 170411 | 170411 | 0 | 170411 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.5 | ECC_Sludge Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85206 | 85206 | 0 | 85206 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.3.6 | ECC_Sludge Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85206 | 85206 | 0 | 85206 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.1 | ECC_Aeration Blower Unit - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1226962 | 1226962 | 1226962 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.2 | ECC_Aeration Blower Unit - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3067404 | 3067404 | 0 | 3067404 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.3 | ECC_Aeration Blower Unit - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 613481 | 613481 | 0 | 613481 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.4 | ECC_Aeration Blower Unit - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 613481 | 613481 | 0 | 613481 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.5 | ECC_Aeration Blower Unit - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 306740 | 306740 | 0 | 306740 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.4.6 | ECC_Aeration Blower Unit - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 306740 | 306740 | 0 | 306740 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.1 | ECC_Chemical Dosing Unit - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 471908 | 471908 | 471908 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.2 | ECC_Chemical Dosing Unit - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1179771 | 1179771 | 0 | 1179771 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.3 | ECC_Chemical Dosing Unit - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 235954 | 235954 | 0 | 235954 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.4 | ECC_Chemical Dosing Unit - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 235954 | 235954 | 0 | 235954 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.5 | ECC_Chemical Dosing Unit - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 117977 | 117977 | 0 | 117977 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.5.6 | ECC_Chemical Dosing Unit - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 117977 | 117977 | 0 | 117977 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.6.1 | ECC_Sanitary System - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 516615 | 516615 | 516615 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.6.2 | ECC_Sanitary System - Sanitary system work | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1808154 | 1808154 | 0 | 1808154 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.6.3 | ECC_Sanitary System - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 258308 | 258308 | 0 | 258308 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.7.1 | ECC_Surface Drainage or Storm Water System - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 566290 | 566290 | 566290 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.7.2 | ECC_Surface Drainage or Storm Water System - Surface drainage or storm water system work | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1982015 | 1982015 | 0 | 1982015 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.1.7.3 | ECC_Surface Drainage or Storm Water System - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 283145 | 283145 | 0 | 283145 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.2.1.1.2 | ECC_Wastewater Systems - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4009728 | 4009728 | 3408269 | 601459 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.2.1.2.1 | ECC_Wastewater Systems - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2985085 | 2985085 | 2985085 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.2.1.2.2 | ECC_Wastewater Systems - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2985085 | 2985085 | 2537322 | 447763 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.2.2.1 | ECC_Wastewater Systems - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 75558 | 75558 | 37779 | 37779 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.ML | Construction - WASTE WATER TREATMENT SYSTEM | ECC.II.5.2.3.1 | ECC_Wastewater Systems - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 314824 | 314824 | 0 | 314824 | 1 | 3500235911 | 26843480
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.1 | ECC_Combined Service Water Tank And Fire Water Tank - Tank Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17435772 | 17435772 | 17435772 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.2 | ECC_Combined Service Water Tank And Fire Water Tank - Bottom & Annular/Sketch Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17435772 | 17435772 | 17435772 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.3 | ECC_Combined Service Water Tank And Fire Water Tank - 1St Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17435772 | 17435772 | 17435772 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.4 | ECC_Combined Service Water Tank And Fire Water Tank - 2Nd Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17435772 | 17435772 | 17435772 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.5 | ECC_Combined Service Water Tank And Fire Water Tank - 3Rd Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11623848 | 11623848 | 11623848 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.6 | ECC_Combined Service Water Tank And Fire Water Tank - 4Th-5Th Course Shell Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11623848 | 11623848 | 11623848 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.7 | ECC_Combined Service Water Tank And Fire Water Tank - Roof Plate & Structure/Top Angle | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11623848 | 11623848 | 11623848 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.8 | ECC_Combined Service Water Tank And Fire Water Tank - Tank Accessory Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5811924 | 5811924 | 5811924 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.1.9 | ECC_Combined Service Water Tank And Fire Water Tank - Test , Clean Up & Boxing-Up | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5811924 | 5811924 | 5811924 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.1 | ECC_Service Water supply Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1585612 | 1585612 | 1585612 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.2 | ECC_Service Water supply Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3964030 | 3964030 | 3964030 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.3 | ECC_Service Water supply Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 792806 | 792806 | 792806 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.4 | ECC_Service Water supply Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 792806 | 792806 | 792806 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.5 | ECC_Service Water supply Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396403 | 396403 | 356763 | 39640 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.10.6 | ECC_Service Water supply Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396403 | 396403 | 396403 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.1 | ECC_Filtered Water Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21526 | 21526 | 21526 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.2 | ECC_Filtered Water Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53814 | 53814 | 53814 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.3 | ECC_Filtered Water Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.4 | ECC_Filtered Water Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.5 | ECC_Filtered Water Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.11.6 | ECC_Filtered Water Tank - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.1 | ECC_Demin Water Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21526 | 21526 | 21526 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.2 | ECC_Demin Water Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53814 | 53814 | 53814 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.3 | ECC_Demin Water Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.4 | ECC_Demin Water Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.5 | ECC_Demin Water Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.12.6 | ECC_Demin Water Tank - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.1 | ECC_Treated Water Tank - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21526 | 21526 | 21526 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.2 | ECC_Treated Water Tank - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53814 | 53814 | 53814 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.3 | ECC_Treated Water Tank - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.4 | ECC_Treated Water Tank - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10763 | 10763 | 10763 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.5 | ECC_Treated Water Tank - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.13.6 | ECC_Treated Water Tank - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5381 | 5381 | 5381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.1 | ECC_Raw Water Lifting Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 644316 | 644316 | 644316 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.2 | ECC_Raw Water Lifting Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1610790 | 1610790 | 1610790 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.3 | ECC_Raw Water Lifting Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 322158 | 322158 | 322158 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.4 | ECC_Raw Water Lifting Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 322158 | 322158 | 322158 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.5 | ECC_Raw Water Lifting Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161079 | 161079 | 144971 | 16108 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.2.6 | ECC_Raw Water Lifting Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161079 | 161079 | 161079 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.1 | ECC_Raw Water Transfer Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 644316 | 644316 | 644316 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.2 | ECC_Raw Water Transfer Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1610790 | 1610790 | 1610790 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.3 | ECC_Raw Water Transfer Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 322158 | 322158 | 322158 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.4 | ECC_Raw Water Transfer Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 322158 | 322158 | 322158 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.5 | ECC_Raw Water Transfer Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161079 | 161079 | 144971 | 16108 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.3.6 | ECC_Raw Water Transfer Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161079 | 161079 | 161079 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.1 | ECC_Sand Filter - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 666964 | 666964 | 666964 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.2 | ECC_Sand Filter - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1667410 | 1667410 | 1667410 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.3 | ECC_Sand Filter - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.4 | ECC_Sand Filter - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.5 | ECC_Sand Filter - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 150067 | 16674 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.4.6 | ECC_Sand Filter - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 166741 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.1 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 666964 | 666964 | 666964 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.2 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1667410 | 1667410 | 1667410 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.3 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.4 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.5 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 150067 | 16674 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.5.6 | ECC_Ultra Filter c/w pumps, tanks & dedicated control unit - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 166741 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.1 | ECC_Carbon Filter - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 666964 | 666964 | 666964 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.2 | ECC_Carbon Filter - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1667410 | 1667410 | 1667410 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.3 | ECC_Carbon Filter - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.4 | ECC_Carbon Filter - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 333482 | 333482 | 333482 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.5 | ECC_Carbon Filter - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 150067 | 16674 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.6.6 | ECC_Carbon Filter - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166741 | 166741 | 166741 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.1 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 967412 | 967412 | 967412 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.2 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2418530 | 2418530 | 2418530 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.3 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 483706 | 483706 | 483706 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.4 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 483706 | 483706 | 483706 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.5 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 241853 | 241853 | 217668 | 24185 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.7.6 | ECC_Reverse Osmosis Unit, c/w pump, tanks & control unit - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 241853 | 241853 | 241853 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.1 | ECC_Chemical Injection / Dosing Unit - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2074056 | 2074056 | 2074056 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.2 | ECC_Chemical Injection / Dosing Unit - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5185140 | 5185140 | 5185140 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.3 | ECC_Chemical Injection / Dosing Unit - Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1037028 | 1037028 | 1037028 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.4 | ECC_Chemical Injection / Dosing Unit - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1037028 | 1037028 | 1037028 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.5 | ECC_Chemical Injection / Dosing Unit - Internal Cleaning | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 518514 | 518514 | 466663 | 51851 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.8.6 | ECC_Chemical Injection / Dosing Unit - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 518514 | 518514 | 518514 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.1 | ECC_Treated Water (Fresh Water) Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1585612 | 1585612 | 1585612 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.2 | ECC_Treated Water (Fresh Water) Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3964030 | 3964030 | 3964030 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.3 | ECC_Treated Water (Fresh Water) Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 792806 | 792806 | 792806 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.4 | ECC_Treated Water (Fresh Water) Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 792806 | 792806 | 792806 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.5 | ECC_Treated Water (Fresh Water) Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396403 | 396403 | 356763 | 39640 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.1.9.6 | ECC_Treated Water (Fresh Water) Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396403 | 396403 | 396403 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.2.1.1.2 | ECC_Water Supply and Treatment Systems - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18004182 | 18004182 | 16203764 | 1800418 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.2.1.2.1 | ECC_Water Supply and Treatment Systems - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13403407 | 13403407 | 13403407 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.2.1.2.2 | ECC_Water Supply and Treatment Systems - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13403407 | 13403407 | 12063066 | 1340341 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.2.2.1 | ECC_Water Supply and Treatment Systems - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 169632 | 169632 | 127224 | 42408 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.MO | Construction - WATER TREATMENT PLANT SYSTEM | ECC.II.6.2.3.1 | ECC_Water Supply and Treatment Systems - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 706800 | 706800 | 0 | 706800 | 1 | 3500235911 | 4127521
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.1 | ECC_Motor Driven Fire Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2104711 | 2104711 | 2104711 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.2 | ECC_Motor Driven Fire Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5261778 | 5261778 | 0 | 5261778 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.3 | ECC_Motor Driven Fire Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1052356 | 1052356 | 0 | 1052356 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.4 | ECC_Motor Driven Fire Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1052356 | 1052356 | 0 | 1052356 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.5 | ECC_Motor Driven Fire Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 526178 | 526178 | 0 | 526178 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.1.6 | ECC_Motor Driven Fire Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 526178 | 526178 | 0 | 526178 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.1 | ECC_Diesel Driven Fire Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5521328 | 5521328 | 5521328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.2 | ECC_Diesel Driven Fire Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13803319 | 13803319 | 0 | 13803319 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.3 | ECC_Diesel Driven Fire Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2760664 | 2760664 | 0 | 2760664 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.4 | ECC_Diesel Driven Fire Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2760664 | 2760664 | 0 | 2760664 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.5 | ECC_Diesel Driven Fire Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1380332 | 1380332 | 0 | 1380332 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.2.6 | ECC_Diesel Driven Fire Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1380332 | 1380332 | 0 | 1380332 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.1 | ECC_Jockey Pump - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3680885 | 3680885 | 3680885 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.2 | ECC_Jockey Pump - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9202213 | 9202213 | 0 | 9202213 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.3 | ECC_Jockey Pump - Grouting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1840443 | 1840443 | 0 | 1840443 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.4 | ECC_Jockey Pump - First Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1840443 | 1840443 | 0 | 1840443 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.5 | ECC_Jockey Pump - Aux.Eq. & Piping Install | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 920221 | 920221 | 0 | 920221 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.3.6 | ECC_Jockey Pump - Second/Final Alignment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 920221 | 920221 | 0 | 920221 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.4.1 | ECC_Fire Water Loop, Hydrants And Hydrant Boxes - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3067404 | 3067404 | 0 | 3067404 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.4.2 | ECC_Fire Water Loop, Hydrants And Hydrant Boxes - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10735915 | 10735915 | 0 | 10735915 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.4.3 | ECC_Fire Water Loop, Hydrants And Hydrant Boxes - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1533702 | 1533702 | 0 | 1533702 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.5.1 | ECC_Local Fire Panels And A Main Fire Alarm Annunciator Panel (FAAP) - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1226962 | 1226962 | 0 | 1226962 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.5.2 | ECC_Local Fire Panels And A Main Fire Alarm Annunciator Panel (FAAP) - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4294366 | 4294366 | 0 | 4294366 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.5.3 | ECC_Local Fire Panels And A Main Fire Alarm Annunciator Panel (FAAP) - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 613481 | 613481 | 0 | 613481 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.6.1 | ECC_Fire Alarm & Detection System - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1840443 | 1840443 | 0 | 1840443 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.6.2 | ECC_Fire Alarm & Detection System - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6441549 | 5797394 | 0 | 5797394 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.6.3 | ECC_Fire Alarm & Detection System - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 920221 | 828199 | 0 | 828199 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.7.1 | ECC_CO2 Extinguisher - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3926278 | 3926278 | 0 | 3926278 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.7.2 | ECC_CO2 Extinguisher - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13741971 | 13741971 | 0 | 13741971 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.7.3 | ECC_CO2 Extinguisher - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1963139 | 1963139 | 0 | 1963139 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.8.1 | ECC_Dry Chemical Extinguisher - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 920451 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.8.2 | ECC_Dry Chemical Extinguisher - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3221580 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.8.3 | ECC_Dry Chemical Extinguisher - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 460226 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.9.1 | ECC_Portable Fire Protection Equipment - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 460226 | 460226 | 0 | 460226 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.9.2 | ECC_Portable Fire Protection Equipment - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1610790 | 1610790 | 0 | 1610790 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.1.9.3 | ECC_Portable Fire Protection Equipment - Finishing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 230113 | 230113 | 0 | 230113 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.2.1.1.2 | ECC_Fire Protection Systems - Smallbore Piping Works ( < 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 18004182 | 17644098 | 12602927 | 5041171 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.2.1.2.1 | ECC_Fire Protection Systems - Largebore Piping Works ( = 2") - Onsite Fabrication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13403407 | 13403407 | 13403407 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.2.1.2.2 | ECC_Fire Protection Systems - Largebore Piping Works ( = 2") - Piping Installation & Welding Works | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 13403407 | 13135339 | 9382385 | 3752954 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.2.2.1 | ECC_Fire Protection Systems - Ball Valve/Gate Valve/Check Valve/Globe Valve/Butterfly Valve size 2" - 6" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 169632 | 166239 | 67853 | 98386 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.GR | Construction - FIRE FIGHTING SYSTEM | ECC.II.7.2.3.1 | ECC_Fire Protection Systems - NDE works (e.g RT, penetrant test etc as per piping standard and CODE) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 706800 | 692664 | 0 | 692664 | 1 | 3500235911 | 106683256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.1.1 | ECC_Water Analysis Equipment - Conductivitymeter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 736177 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.1.2 | ECC_Water Analysis Equipment - pH Meter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2453923 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.1.3 | ECC_Water Analysis Equipment - Spectrofotometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 613481 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.1.4 | ECC_Water Analysis Equipment - Color Comparator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1533702 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.1 | ECC_Lubricating Oil Analysis - Hydrometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 613481 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.2 | ECC_Lubricating Oil Analysis - Quartz Tube Combustion Apparatus | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 15337022 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.3 | ECC_Lubricating Oil Analysis - Viscosimeter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1533702 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.4 | ECC_Lubricating Oil Analysis - Pensky Marten Closed Tester | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 12269617 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.5 | ECC_Lubricating Oil Analysis - Tensiometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 61348 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.6 | ECC_Lubricating Oil Analysis - Inductively Couplet Plasma Atomic Emission Spectrometry (ICP-AES) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 30674043 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.7 | ECC_Lubricating Oil Analysis - Potentiometric Titrator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3680885 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.8 | ECC_Lubricating Oil Analysis - Oxidation test apparatus | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 9202213 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.2.9 | ECC_Lubricating Oil Analysis - Total base number test apparatus | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1226962 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.3.1 | ECC_Insulation Oil Analysis - Hydrometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 613481 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.3.2 | ECC_Insulation Oil Analysis - Viscometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1533702 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.3.3 | ECC_Insulation Oil Analysis - Pensky Marren Closed Tester | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 12269617 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.3.4 | ECC_Insulation Oil Analysis - Tensiometer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 61348 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.3.5 | ECC_Insulation Oil Analysis - Oxidation test apparatus | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 9202213 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.4.1 | ECC_Fuel gas Analyzer Equipment - Gas Caloriemeter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 30674043 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.4.2 | ECC_Fuel gas Analyzer Equipment - Gas Chromatograph | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 42943660 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.4.3 | ECC_Fuel gas Analyzer Equipment - Combustion and Adsorption Apparatus | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 15337022 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.5.1 | ECC_Burnt Gas Analysis - Dew Point meter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1840443 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.KT | Construction - SAMPLING & LABORATORY EQUIPMENT SYSTEM | ECC.II.8.1.5.2 | ECC_Burnt Gas Analysis - Orsat Meter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 613481 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.1 | ECC_Workshop Equipment - Forklift | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1533702 | 1380332 | 1380332 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.10 | ECC_Workshop Equipment - Threading machine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6134809 | 5521328 | 5521328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.11 | ECC_Workshop Equipment - Storage & Racks | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8312666 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.12.1 | ECC_Overhead Crane - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30371078 | 30371078 | 30371078 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.12.2 | ECC_Overhead Crane - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 106298773 | 106298773 | 106298773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.12.3 | ECC_Overhead Crane - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15185539 | 15185539 | 15185539 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.2 | ECC_Workshop Equipment - Welding Machine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2453923 | 2208531 | 0 | 2208531 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.3 | ECC_Workshop Equipment - Lathe | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6134809 | 5521328 | 5521328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.4 | ECC_Workshop Equipment - Grinder | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2453923 | 2208531 | 0 | 2208531 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.5 | ECC_Workshop Equipment - Drilling Machine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1226962 | 1104266 | 0 | 1104266 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.6 | ECC_Workshop Equipment - Vises | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 613481 | 552133 | 0 | 552133 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.7 | ECC_Workshop Equipment - Hand Tools Set consist of 3 sets | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 920221 | 828199 | 0 | 828199 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.8 | ECC_Workshop Equipment - Workbench | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 981569 | 883412 | 0 | 883412 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0M.FT | Construction - CRANE, HOIST & CONVEYING SYSTEM | ECC.II.9.1.9 | ECC_Workshop Equipment - Sawing machine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 4907847 | 4417062 | 0 | 4417062 | 1 | 3500235911 | 12202134
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.1.1 | ECC_Electric Generator Control Panel A - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16695083 | 16695083 | 16695083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.1.2 | ECC_Electric Generator Control Panel A - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 58432791 | 58432791 | 58432791 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.1.3 | ECC_Electric Generator Control Panel A - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 8347542 | 6678034 | 2504263 | 4173771 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.2.1 | ECC_Electric Generator Control Panel B - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16695083 | 16695083 | 16695083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.2.2 | ECC_Electric Generator Control Panel B - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 58432791 | 58432791 | 58432791 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.2.3 | ECC_Electric Generator Control Panel B - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 8347542 | 6678034 | 1669508 | 5008526 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.3.1 | ECC_Electric Generator Control Panel C - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16695083 | 16695083 | 16695083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.3.2 | ECC_Electric Generator Control Panel C - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 58432791 | 58432791 | 58432791 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.3.3 | ECC_Electric Generator Control Panel C - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 8347542 | 6678034 | 1669508 | 5008526 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.4.1 | ECC_Electric Generator Control Panel D - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16695083 | 16695083 | 16695083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.4.2 | ECC_Electric Generator Control Panel D - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 58432791 | 58432791 | 58432791 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.4.3 | ECC_Electric Generator Control Panel D - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 8347542 | 6678034 | 834754 | 5843280 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.5.1 | ECC_Electric Generator Control Panel E - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16695083 | 16695083 | 16695083 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.5.2 | ECC_Electric Generator Control Panel E - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 58432791 | 58432791 | 58432791 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KE | Construction - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | ECC.III.1.1.5.3 | ECC_Electric Generator Control Panel E - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 8347542 | 6678034 | 834754 | 5843280 | 1 | 3500235911 | 197243619
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.1.2.1.1 | ECC_Busduct Installation - 1250A, 25kA, 11 kV 3P + N, Copper - Sandwich busduct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 52172135 | 49563528 | 36520495 | 13043033 | 1 | 3500235911 | 75601774
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.1.2.1.2 | ECC_Busduct Installation - 1000A, 25kA, 11 kV 3P + N, Copper - Sandwich busduct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 52172135 | 49563528 | 36520495 | 13043033 | 1 | 3500235911 | 75601774
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.1.2.1.3 | ECC_Busduct Installation - 3000A, 65kA, 0.4 kV 3P + N, Copper - Sandwich busduct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 104344270 | 99127057 | 52172135 | 46954922 | 1 | 3500235911 | 75601774
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.1.1 | ECC_MV Switchgears 11kV, 1250A, 25 kA IP 41,3ph, 4W Dead Front - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20294653 | 20294653 | 20294653 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.1.2 | ECC_MV Switchgears 11kV, 1250A, 25 kA IP 41,3ph, 4W Dead Front - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 71031286 | 71031286 | 71031286 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.1.3 | ECC_MV Switchgears 11kV, 1250A, 25 kA IP 41,3ph, 4W Dead Front - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10147327 | 10147327 | 10147327 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.2.1 | ECC_MV Switchgears 11kV, 1000A, 25 kA IP 41,3ph, 4W Dead Front - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20294653 | 20294653 | 20294653 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.2.2 | ECC_MV Switchgears 11kV, 1000A, 25 kA IP 41,3ph, 4W Dead Front - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 71031286 | 71031286 | 71031286 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.JQ | Construction - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | ECC.III.2.1.2.3 | ECC_MV Switchgears 11kV, 1000A, 25 kA IP 41,3ph, 4W Dead Front - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10147327 | 10147327 | 10147327 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.1.1 | ECC_Lighting System Installation - Non Hazardous Panel , IP 20, Dead Front, Metal Enclosed, Fixed Type, 26 kW, 100 A, 2k | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 710345 | 710345 | 390690 | 319655 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.1.1 | ECC_Lighting System Installation - Lighting Pole For Street Lighting, suitable for Flood light HPS 150W HDG steel materi | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6908037 | 6908037 | 3799420 | 3108617 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.1.2 | ECC_Lighting System Installation - Lighting Pole, stanchion type HPS 150 W 3m Height c/w stanchion, channel and angle | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 591948 | 591948 | 325571 | 266377 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.1 | ECC_Lighting System Installation - Wellglass HPS, Pendant Mounted, 150 W, 230V, 50 Hz, Industrial Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17640816 | 17640816 | 11466530 | 6174286 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.2 | ECC_Lighting System Installation - LED Ceiling Luminaires 20W ,Including fitting, outlet condulet, accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7867861 | 7867861 | 5114110 | 2753751 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.3 | ECC_Lighting System Installation - LED Pendant Luminaires 40W, Including fitting, outlet condulet, accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4130627 | 4130627 | 2684908 | 1445719 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.4 | ECC_Lighting System Installation - Emergency Lighting 20W, including 3 hours on self-contained battery power & fitting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 944143 | 944143 | 0 | 944143 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.5 | ECC_Lighting System Installation - Outdoor HPS Stanchion Mounted- 150W | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1701171 | 1701171 | 1105761 | 595410 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.JC | Construction - LIGHTING SYSTEM | ECC.III.2.10.2.2.6 | ECC_Lighting System Installation - Flooding Light 150 W, 220 V, 50 Hz | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9720975 | 9720975 | 6318634 | 3402341 | 1 | 3500235911 | 19010299
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.LQ | Construction - TELECOMMUNICATION SYSTEM | ECC.III.2.11.1.1 | ECC_Communication systems complete - Horn Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1860848 | 1860848 | 558254 | 1302594 | 1 | 3500235911 | 6326884
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.LQ | Construction - TELECOMMUNICATION SYSTEM | ECC.III.2.11.1.2 | ECC_Communication systems complete - Ceiling Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5582545 | 5582545 | 558255 | 5024290 | 1 | 3500235911 | 6326884
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.LQ | Construction - TELECOMMUNICATION SYSTEM | ECC.III.2.11.1.3 | ECC_Communication systems complete - Telephone Analog | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 3256485 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.LQ | Construction - TELECOMMUNICATION SYSTEM | ECC.III.2.11.1.4 | ECC_Communication systems complete - Hotline Telephone | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 465212 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.III.2.12.1.1 | ECC_Closed circuit TV system equipment complete - CCTV outdoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1866515 | 1866515 | 839932 | 1026583 | 1 | 3500235911 | 1026583
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.KW | Construction - SECURITY & SURVEILLANCE SYSTEM | ECC.III.2.12.1.2 | ECC_Closed circuit TV system equipment complete - CCTV indoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1119909 | 1119909 | 1119909 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.13.1.1 | ECC_70 kV Metering Panel and Tariff Metering, IP 41,3ph, 4W Dead Front - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 872955 | 872955 | 872955 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.13.1.2 | ECC_70 kV Metering Panel and Tariff Metering, IP 41,3ph, 4W Dead Front - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3055341 | 3055341 | 2749807 | 305534 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.13.1.3 | ECC_70 kV Metering Panel and Tariff Metering, IP 41,3ph, 4W Dead Front - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 436477 | 436477 | 0 | 436477 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.1.1 | ECC_LV Switchgears 0.4 kV, 3000A, 65 kA IP 41,3ph, 4W Dead Front - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19133197 | 19133197 | 19133197 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.1.2 | ECC_LV Switchgears 0.4 kV, 3000A, 65 kA IP 41,3ph, 4W Dead Front - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66966189 | 66966189 | 66966189 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.1.3 | ECC_LV Switchgears 0.4 kV, 3000A, 65 kA IP 41,3ph, 4W Dead Front - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.7 | 9566598 | 6696619 | 6696619 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.2.1 | ECC_LV Switchgears 0.4 kV, 400A, 10 kA IP 41,3ph, 4W Dead Front - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19133197 | 19133197 | 19133197 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.2.2 | ECC_LV Switchgears 0.4 kV, 400A, 10 kA IP 41,3ph, 4W Dead Front - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66966189 | 66966189 | 20089857 | 46876332 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.2.2.3 | ECC_LV Switchgears 0.4 kV, 400A, 10 kA IP 41,3ph, 4W Dead Front - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 9566598 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.3.1.1 | ECC_Low voltage motor control centers - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8947130 | 8947130 | 8947130 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.3.1.2 | ECC_Low voltage motor control centers - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31314957 | 31314957 | 31314957 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.2.3.1.3 | ECC_Low voltage motor control centers - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 4473565 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.4.1.1 | ECC_5 kVA UPS System, Parallel Redundant System - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8947130 | 8947130 | 8947130 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.4.1.2 | ECC_5 kVA UPS System, Parallel Redundant System - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31314957 | 31314957 | 31314957 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.4.1.3 | ECC_5 kVA UPS System, Parallel Redundant System - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 4473565 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AT | Construction - BLACK-START GENERATOR SYSTEM | ECC.III.2.5.1.1 | ECC_Black Start/Emergency Diesel Generator (EDG) - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8947130 | 8947130 | 0 | 8947130 | 1 | 3500235911 | 40262087
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AT | Construction - BLACK-START GENERATOR SYSTEM | ECC.III.2.5.1.2 | ECC_Black Start/Emergency Diesel Generator (EDG) - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31314957 | 31314957 | 0 | 31314957 | 1 | 3500235911 | 40262087
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AT | Construction - BLACK-START GENERATOR SYSTEM | ECC.III.2.5.1.3 | ECC_Black Start/Emergency Diesel Generator (EDG) - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 4473565 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.1.1 | ECC_110 VDC - 1 kVA DC System, Single System - Instrumentation & Control - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4473565 | 4473565 | 4473565 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.1.2 | ECC_110 VDC - 1 kVA DC System, Single System - Instrumentation & Control - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15657478 | 15657478 | 15657478 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.1.3 | ECC_110 VDC - 1 kVA DC System, Single System - Instrumentation & Control - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2236783 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.2.1 | ECC_110 VDC - 30 kVA DC System, Single System - Instrumentation & Control - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4473565 | 4473565 | 4473565 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.2.2 | ECC_110 VDC - 30 kVA DC System, Single System - Instrumentation & Control - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15657478 | 15657478 | 15657478 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.AS | Construction - BACKUP POWER SYSTEM | ECC.III.2.6.2.3 | ECC_110 VDC - 30 kVA DC System, Single System - Instrumentation & Control - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2236783 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.1 | ECC_Pulling, Laying , and Dress-up Cable - 3/C # 95 mm2, 11 kV Medium Voltage Power Cable (8.7/15 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2114585 | 2114585 | 2114585 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.10 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #10 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1958446 | 1958446 | 1762601 | 195845 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.11 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #16 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1144206 | 1144206 | 800944 | 343262 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.12 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #50 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 824854 | 824854 | 742369 | 82485 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.13 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #120 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2496195 | 2496195 | 2246576 | 249619 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.14 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #150 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4707874 | 4707874 | 4237087 | 470787 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.15 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #4 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2421037 | 2421037 | 2299985 | 121052 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.16 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #6 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1044140 | 1044140 | 991933 | 52207 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.17 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #10 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 236078 | 236078 | 165255 | 70823 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.18 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #16 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 269804 | 269804 | 188863 | 80941 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.19 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #25 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 562091 | 562091 | 393464 | 168627 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.2 | ECC_Pulling, Laying , and Dress-up Cable - 3/C # 120 mm2, 11 kV Medium Voltage Power Cable (8.7/15 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22258790 | 22258790 | 22258790 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.20 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #35 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3533302 | 3533302 | 3533302 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.21 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #150 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 843136 | 843136 | 843136 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.22 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #240 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22663496 | 22663496 | 22663496 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.23 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #4 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1045088 | 1045088 | 940579 | 104509 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.24 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #6 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 720508 | 720508 | 504356 | 216152 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.25 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #4 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 60294 | 60294 | 42206 | 18088 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.26 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #6 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 562237 | 562237 | 393566 | 168671 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.27 | ECC_Pulling, Laying , and Dress-up Cable - 4/C+E #10 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 200979 | 200979 | 140685 | 60294 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.28 | ECC_Pulling, Laying , and Dress-up Cable - 12/C+E #2.5 mm2 (0.6/1 kV), Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18562252 | 18562252 | 12993576 | 5568676 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.3 | ECC_Pulling, Laying , and Dress-up Cable - 3/C # 300 mm2, 11 kV Medium Voltage Power Cable (8.7/15 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 44517581 | 44517581 | 44517581 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.4 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #2.5 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - INDOOR | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 294530 | 294530 | 206171 | 88359 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.5 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #4 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - INDOOR LI | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 168795 | 168795 | 151916 | 16879 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.6 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #6 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - OUTDOOR L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1177692 | 1177692 | 824384 | 353308 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.7 | ECC_Pulling, Laying , and Dress-up Cable - 2/C+E #4 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2425584 | 2425584 | 2183026 | 242558 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.8 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #4 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4417358 | 4417358 | 3092151 | 1325207 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.1.9 | ECC_Pulling, Laying , and Dress-up Cable - 3/C+E #6 mm2 (0.6/1 kV), 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4112817 | 4112817 | 2878972 | 1233845 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.2.1 | ECC_Grounding Cables - 1C#120Sqmm, Soft Drawn Stranded Copper Wire with PVC insulated, Green/Yellow | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 580498 | 580498 | 580498 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.2.2 | ECC_Grounding Cables - 1C#70Sqmm, Soft Drawn Stranded Copper Wire with PVC insulated, Green/Yellow | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 829628 | 829628 | 829628 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.2.3 | ECC_Grounding Cables - 1C#35Sqmm, Soft Drawn Stranded Copper Wire with PVC insulated, Green/Yellow | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1693118 | 1693118 | 1693118 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.2.4 | ECC_Grounding Cables - 1C#120Sqmm, Grounding grid bare copper | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4527882 | 4527882 | 4527882 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.2.5 | ECC_Grounding Cables - 1C#120Sqmm, Soft Drawn Stranded Copper Wire with XLPE insulated, Green/Yellow | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 696597 | 696597 | 696597 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.1 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M20 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8860949 | 8860949 | 8860949 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.2 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M25 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 73102827 | 65792544 | 32896272 | 32896272 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.3 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M32 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2339290 | 2105361 | 1216431 | 888930 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.4 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M40 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 152054 | 152054 | 152054 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.5 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M63 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3725320 | 3725320 | 3725320 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.3.6 | ECC_Glanding, Termination, Splicing, and Install Marker Cable - Cable Glands M75 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6705576 | 6705576 | 6705576 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.4.1 | ECC_Install, Fabricate Support & Finishing Cable Ways - Cable Ladder, Heavy Duty, Hot-Dip Galvanized,150 Mm Height | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 101011648 | 101011648 | 90910483 | 10101165 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.4.2 | ECC_Install, Fabricate Support & Finishing Cable Ways - Cable Tray, Heavy Duty, Hot-Dip Galvanized, 150 Mm Height | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25252912 | 25252912 | 22727621 | 2525291 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.1.1 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Local Control Station (LCS) Type-A (Consist of ON-OFF push | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1383357 | 1383357 | 1245021 | 138336 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.1.2 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Local Control Station (LCS) Type-B (Consist of Ampere Meter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 461119 | 461119 | 415007 | 46112 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.2.1 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Junction Box - 4 x M25 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2760353 | 2760353 | 2208282 | 552071 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.2.2 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Condulet/Round Box, 4x1" hub cable entries, terminal blocks | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5441204 | 5441204 | 4352963 | 1088241 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.3.1 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Rigid Steel Conduit, Size 1-1/2", 3000 mm Lg. HD Galv with | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 666263 | 666263 | 266505 | 399758 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.3.2 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Heavy Duty Pvc Conduit, Dia. M20, 3000 mm Lg with Coupling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 266534 | 266534 | 106614 | 159920 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.3.3 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Cable Duct W30 x 30 x 5t, 1500mm PVC, including cover, join | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4987695 | 4987695 | 1995078 | 2992617 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.3.4 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Steel Angle, 50 mm X 50 mm X 5 mm Thk. X 3000 mm Lg Hot Dip | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46005875 | 46005875 | 36804700 | 9201175 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BB | Construction - CABLE & ACCESSORIES SYSTEM | ECC.III.2.7.5.3.5 | ECC_Install & Fabricate Support For LCS, JB, & Ladder Tray - Steel Channel Unp, 50 mm X 100 mm X 50 mm X 5 mm Thk. X 300 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27603525 | 27603525 | 22082820 | 5520705 | 1 | 3500235911 | 77742787
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.III.2.8.1.1 | ECC_Lightning Protection - Grounding rod steel copper clad coupling 20mm dia, 3 m | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16948552 | 16948552 | 15253697 | 1694855 | 1 | 3500235911 | 7305650
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.III.2.8.1.2 | ECC_Lightning Protection - Conventional Air Terminal C/W Bolt, class II as per NFPA 780, length min 600mm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5483751 | 5483751 | 2193500 | 3290251 | 1 | 3500235911 | 7305650
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.III.2.8.1.3 | ECC_Lightning Protection - Earthing Bus Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1218209 | 1218209 | 1096388 | 121821 | 1 | 3500235911 | 7305650
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.III.2.8.2.1 | ECC_Bulk Material - PVC conduit dia. 32 mm 3000mm Length | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2761280 | 2761280 | 1104512 | 1656768 | 1 | 3500235911 | 7305650
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA0E.GH | Construction - EARTHING & LIGHTNING SYSTEM | ECC.III.2.8.2.2 | ECC_Bulk Material - Rigid Steel Conduit for lightning protection down conductor, dia 52mm, 3m length | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 903258 | 903258 | 361303 | 541955 | 1 | 3500235911 | 7305650
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.2.9.1.1 | ECC_Install, Set Up, & Leveling Neutral Grounding Resistor - NGR 11 kV/v3 - 400 A/10 sec , 16.5 O | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4267976 | 4267976 | 4267976 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.2.9.1.2 | ECC_Install, Set Up, & Leveling Neutral Grounding Resistor - NGR 70 kV/v3 - 400 A/10 sec , 196 O | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1280393 | 1280393 | 0 | 1280393 | 1 | 3500235911 | 75601774
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.BA | Construction - BUSBAR AND CONNECTIONS SYSTEM | ECC.III.2.9.1.3 | ECC_Install, Set Up, & Leveling Neutral Grounding Resistor - NGR 70 kV/v3 - 400 A/10 sec , 327 O | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1280393 | 1280393 | 0 | 1280393 | 1 | 3500235911 | 75601774
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.1.1 | ECC_25000 kVA, 11/70 kV Power Transformer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34321558 | 34321558 | 34321558 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.1.2 | ECC_25000 kVA, 11/70 kV Power Transformer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120125452 | 120125452 | 120125452 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.1.3 | ECC_25000 kVA, 11/70 kV Power Transformer - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17160779 | 17160779 | 15444701 | 1716078 | 1 | 3500235911 | 18424200
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.2.1 | ECC_15000 kVA, 11/70 kV Power Transformer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34321558 | 34321558 | 34321558 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.2.2 | ECC_15000 kVA, 11/70 kV Power Transformer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120125452 | 120125452 | 108112907 | 12012545 | 1 | 3500235911 | 18424200
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.1.2.3 | ECC_15000 kVA, 11/70 kV Power Transformer - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 17160779 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.2.1.1 | ECC_2500 kVA, 11/0.4 kV Power Transformer - Preparation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13415935 | 13415935 | 13415935 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.2.1.2 | ECC_2500 kVA, 11/0.4 kV Power Transformer - Installation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46955771 | 46955771 | 42260194 | 4695577 | 1 | 3500235911 | 18424200
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.KG | Construction - POWER TRANSFORMER & AUXILIARIES SYSTEM | ECC.III.3.2.1.3 | ECC_2500 kVA, 11/0.4 kV Power Transformer - Test & Inspection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6707967 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.1 | ECC_Complete 20/70/150 KV Substation Equipment - New two (2) bays transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3327069 | 3327069 | 3160716 | 166353 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.2 | ECC_Complete 20/70/150 KV Substation Equipment - Modification of 400/230V AC distribution system | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2661655 | 2661655 | 798497 | 1863158 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.3 | ECC_Complete 20/70/150 KV Substation Equipment - Modification of metering and protection panels, control and monitoring | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2661655 | 2661655 | 2129324 | 532331 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.4 | ECC_Complete 20/70/150 KV Substation Equipment - Modification of 110V DC batteries, battery chargers, distribution syste | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2661655 | 2661655 | 2129324 | 532331 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.5 | ECC_Complete 20/70/150 KV Substation Equipment - Modification of 48V DC batteries, battery chargers, distribution system | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2661655 | 2661655 | 2129324 | 532331 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1E.FM | Construction - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | ECC.III.4.1.1.6 | ECC_Complete 20/70/150 KV Substation Equipment - Modification of uninterruptible AC power supply complete with necessary | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2661655 | 2661655 | 798497 | 1863158 | 1 | 3500235911 | 53108005
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.1.1.1.1 | ECC_Panel Installation (System & Marshalling Cabinet) c/w Base Frame and Support - PCS Panel, Free Standing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 36803056 | 33122750 | 33122750 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.1.1.1.2 | ECC_Panel Installation (System & Marshalling Cabinet) c/w Base Frame and Support - ESD/FGS Panel, Free Standing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 36803056 | 33122750 | 33122750 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.1.1.1.3 | ECC_Panel Installation (System & Marshalling Cabinet) c/w Base Frame and Support - Telecomunication Panel (CCTV, PABX, P | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 36803056 | 33122750 | 33122750 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.1.1.1.4 | ECC_Panel Installation (System & Marshalling Cabinet) c/w Base Frame and Support - Fire Alarm & Announcement Panel, Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 36803056 | 33122750 | 0 | 33122750 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.1 | ECC_Instrumentation & Power Cable - 1P # 1.5 sqmm + OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10659054 | 10659054 | 7461338 | 3197716 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.10 | ECC_Instrumentation & Power Cable - 10P # 1.5 sqmm + IS/OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 838904 | 838904 | 587233 | 251671 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.2 | ECC_Instrumentation & Power Cable - 1P # 2.5 sqmm + OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2915658 | 2915658 | 2332526 | 583132 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.3 | ECC_Instrumentation & Power Cable - 1T # 1.5 sqmm + OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2361360 | 2361360 | 1416816 | 944544 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.4 | ECC_Instrumentation & Power Cable - 2P # 1.5 sqmm + IS/OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2691122 | 2691122 | 1614673 | 1076449 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.5 | ECC_Instrumentation & Power Cable - 2P # 2.5 sqmm + OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 927973 | 927973 | 788777 | 139196 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.6 | ECC_Instrumentation & Power Cable - 2C # 2.5 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 126768 | 126768 | 76061 | 50707 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.7 | ECC_Instrumentation & Power Cable - 5P # 1.5 sqmm + IS/OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3974541 | 3974541 | 3577087 | 397454 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.8 | ECC_Instrumentation & Power Cable - 5P # 1.5 sqmm + OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1001714 | 1001714 | 851457 | 150257 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.1.9 | ECC_Instrumentation & Power Cable - 5T # 1.5 sqmm + IS/OS | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2064740 | 2064740 | 1755029 | 309711 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.2.1 | ECC_Grounding Cable - 1C # 4 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 432431 | 432431 | 129729 | 302702 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.3.1 | ECC_Communication Cable - Cable for PAGA System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 974372 | 974372 | 535905 | 438467 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.3.2 | ECC_Communication Cable - Cable for PABX System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1067169 | 853735 | 480226 | 373509 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.3.3 | ECC_Communication Cable - Cable for CCTV System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1902345 | 1902345 | 760938 | 1141407 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.3.4 | ECC_Communication Cable - Ethernet CAT6 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1275963 | 1275963 | 637982 | 637981 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.4.1 | ECC_Glanding Cable - M20 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 632264 | 632264 | 189679 | 442585 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.4.2 | ECC_Glanding Cable - M25 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 327939 | 327939 | 98382 | 229557 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.4.3 | ECC_Glanding Cable - M32 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 23614 | 21253 | 21253 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.5.1 | ECC_Termination Cable - Cable ferrule lug 1.5 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 337371 | 320502 | 185554 | 134948 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.5.2 | ECC_Termination Cable - Cable ferrule lug 2.5 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 34226 | 32515 | 18824 | 13691 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.5.3 | ECC_Termination Cable - Cable Fork lug 1.5 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 290921 | 276375 | 160007 | 116368 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.1.5.4 | ECC_Termination Cable - Cable Fork lug 2.5 sqmm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 34226 | 32515 | 18824 | 13691 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.2.1.1 | ECC_Junction Box Installation c/w Support - JB terminal 40P | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65295 | 65295 | 55501 | 9794 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.2.1.2 | ECC_Junction Box Installation c/w Support - JB terminal 20P | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 522364 | 522364 | 444009 | 78355 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.2.1.3 | ECC_Junction Box Installation c/w Support - JB terminal 10P | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 334313 | 334313 | 284166 | 50147 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.1.1 | ECC_Perforated Tray - 300W x 50H x 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 718002 | 718002 | 574402 | 143600 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.1.2 | ECC_Perforated Tray - 200W x 50H x 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 732655 | 732655 | 659390 | 73265 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.1.3 | ECC_Perforated Tray - 100W x 50H x 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 747607 | 747607 | 598086 | 149521 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.1.4 | ECC_Perforated Tray - 50W x 50H x 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1708817 | 1708817 | 1367054 | 341763 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.2.1 | ECC_Cable Duct W30 x 30 x 5t, 1500L PVC, including cover, joint plate, clamp, accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1025290 | 1025290 | 820232 | 205058 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.10.1.3.3.1 | ECC_Conduit HDG 1" dia. 3000L, including flexible, accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 623123 | 623123 | 311562 | 311561 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.11.1.1.1 | ECC_Set Up & Installation Stanchion c/w support - Steel C-Channel 100x50x5t, 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2163832 | 2163832 | 1839257 | 324575 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.11.1.1.2 | ECC_Set Up & Installation Stanchion c/w support - Steel Angle 50x50x5t, 3000L | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2885109 | 2885109 | 2452343 | 432766 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.11.1.1.3 | ECC_Set Up & Installation Stanchion c/w support - Steel Plate 2000x1000x5t | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.85 | 288516 | 245239 | 245239 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.1 | ECC_Installation Workstation, Computer and printer - Engineering Workstation Computer installation including Monitor 32" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 8221073 | 4932644 | 2466322 | 2466322 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.2 | ECC_Installation Workstation, Computer and printer - Operator Workstation Computer installation including 2 x Monitor 32 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 12331609 | 7398965 | 3699483 | 3699482 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.3 | ECC_Installation Workstation, Computer and printer - PMS Station Computer installation including Monitor 32", keyboard, | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 8221073 | 4932644 | 2466322 | 2466322 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.4 | ECC_Installation Workstation, Computer and printer - CCTV Console with 2 x Monitor 24", keyboard, mouse | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 4110536 | 2055268 | 0 | 2055268 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.5 | ECC_Installation Workstation, Computer and printer - Printer Laser | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 20552682 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.6 | ECC_Installation Workstation, Computer and printer - Log Printer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 8221073 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.7 | ECC_Installation Workstation, Computer and printer - LVS Monitor 53" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 10178471 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.3.1.1.8 | ECC_Installation Workstation, Computer and printer - GPS for time synchronization | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 4110536 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.4.1.1.1 | ECC_Diagnostic Software | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.95 | 44152768 | 41945130 | 39737491 | 2207639 | 1 | 3500235911 | 46017783
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.FN | Construction - CONTROL & MONITORING SYSTEM | ECC.IV.5.1.1.1 | ECC_Supervisory And Plant Management System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 70644428 | 63579985 | 63579985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.1 | ECC_Instrument Valve - Pressure Regulator Valve (Fuel gas line, 6") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2825777 | 2543199 | 0 | 2543199 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.2 | ECC_Instrument Valve - Pressure Regulator Valve (Diesel fuel line, 1.5") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 7064443 | 6357999 | 0 | 6357999 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.3 | ECC_Instrument Valve - Pressure Regulator Valve (Diesel fuel line, 1") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 7064443 | 6357999 | 0 | 6357999 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.4 | ECC_Instrument Valve - Shutdown Valve (Fuel gas line, 4") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1412889 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.5 | ECC_Instrument Valve - Shutdown Valve (Diesel fuel line, 6") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1412889 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.6.1.1.6 | ECC_Instrument Valve - Shutdown Valve (Diesel fuel line, 2") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 1412889 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.1 | ECC_Flow Instrument - Coriolis Flowmeter (diesel fuel line, 2") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 548018 | 548018 | 0 | 548018 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.2 | ECC_Flow Instrument - Coriolis Flowmeter (diesel fuel line, 1.5") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 548018 | 548018 | 0 | 548018 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.3 | ECC_Flow Instrument - Turbine Flowmeter (diesel fuel line, 6") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 109604 | 109604 | 0 | 109604 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.4 | ECC_Flow Instrument - Turbine Flowmeter (diesel fuel line, 2") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 109604 | 109604 | 0 | 109604 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.5 | ECC_Flow Instrument - Positive Displacement Flowmeter (lube oil line, 1.5") | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 548018 | 548018 | 0 | 548018 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.1.6 | ECC_Flow Instrument - Restriction Orifice, 150# dia 0.5" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 548018 | 548018 | 0 | 548018 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.2.1 | ECC_Pressure Instrument - Pressure Transmitter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 722796 | 578237 | 0 | 578237 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.2.2 | ECC_Pressure Instrument - Pressure Differential Transmitter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 361398 | 289118 | 0 | 289118 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.2.3 | ECC_Pressure Instrument - Pressure Gauge | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 24755774 | 19804619 | 0 | 19804619 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.2.4 | ECC_Pressure Instrument - Pressure Switch, Local | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1806991 | 1445593 | 0 | 1445593 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.3.1 | ECC_Level Instrument - Level Gauge, Gauge Glass Type, H = ?? | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6505167 | 6505167 | 0 | 6505167 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.3.2 | ECC_Level Instrument - Level Switch Tank, Local, Displacer Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1806991 | 1626292 | 0 | 1626292 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.3.3 | ECC_Level Instrument - Level Transmitter, DP Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2891185 | 2602067 | 0 | 2602067 | 1 | 3500235911 | 63587718
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.IR | Construction - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | ECC.IV.7.1.4.1 | ECC_Temperature Instrument - Temperature Gauge | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 2891185 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.1 | ECC_Fire and Gas System - Smoke Detector | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6873512 | 6186161 | 0 | 6186161 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.10 | ECC_Fire and Gas System - Indicator Lamp | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 572793 | 515514 | 0 | 515514 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.2 | ECC_Fire and Gas System - Gas Combustible Detector | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.88 | 1718378 | 1512173 | 0 | 1512173 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.3 | ECC_Fire and Gas System - Flame Detector | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2004774 | 1804297 | 0 | 1804297 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.4 | ECC_Fire and Gas System - Manual Call Point | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.67 | 4009549 | 2686398 | 0 | 2686398 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.5 | ECC_Fire and Gas System - Audible Lamp Alarm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2863963 | 2577567 | 0 | 2577567 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.6 | ECC_Fire and Gas System - Beacon / Strobe Light | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1145585 | 1031027 | 0 | 1031027 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.7 | ECC_Fire and Gas System - Sounder / Horn | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1145585 | 1031027 | 0 | 1031027 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.8 | ECC_Fire and Gas System - Heat Detector | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 286396 | 257756 | 0 | 257756 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.CA1I.GR | Construction - FIRE FIGHTING SYSTEM | ECC.IV.9.1.1.9 | ECC_Fire and Gas System - Push Button | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 572793 | 515514 | 0 | 515514 | 1 | 3500235911 | 18117434
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.1.1.1 | EXW_Steel Pile With 609 mm Diameter (Thickness 12 mm) - Gas Engine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13436640000 | 13436640000 | 13436640000 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.1.1 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 354851970 | 354851970 | 354851970 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JY | Procurement - PILING WORKS | EXW.1.11.2.2.1 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 Mm Diameter - Administration Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 106455591 | 106455591 | 106455591 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.3.1 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Central Control Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 106455591 | 106455591 | 106455591 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.4.1 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - HSD Storage And Facility | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 532277955 | 532277955 | 319366773 | 212911182 | 1 | 3500235911 | 239861256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.4.2 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Service And Fire Water Storage Tank Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6281 | 532277955 | 334323784 | 319366773 | 14957011 | 1 | 3500235911 | 239861256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.4.3 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Radiator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177425985 | 177425985 | 177425985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.4.4 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Lube Oil Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 532277955 | 532277955 | 532277955 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | EXW.1.11.2.4.5 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Emergency Diesel Generator (Edg) Including Hsd Fu | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177425985 | 177425985 | 177425985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JY | Procurement - PILING WORKS | EXW.1.11.2.5.1 | EXW_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Plant Water Facilities | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177425985 | 177425985 | 177425985 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.LR | Procurement - TEMPORARY FACILITIES & UTILITIES | EXW.I.1.A.1.1 | EXW_Material for deep well & temporary facilities | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1568994783 | 1568994783 | 1568994783 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | EXW.I.10.1.1.1 | EXW_Finished Grading | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 335393361 | 228067485 | 201236017 | 26831468 | 1 | 3500235911 | 28436634
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | EXW.I.10.2.1.1 | EXW_Enviromental Consideration And Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 335393361 | 201236017 | 201236017 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | EXW.I.10.3.1.1 | EXW_Site Landscaping | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 335393361 | 201236017 | 201236017 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.1 | EXW_Power Generation Package A - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1284348632 | 1284348632 | 1284348632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.2 | EXW_Power Generation Package A - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1225969148 | 1225969148 | 1225969148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.3 | EXW_Power Generation Package A - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35027690 | 35027690 | 35027690 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.4 | EXW_Power Generation Package A - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42967300 | 42967300 | 42967300 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.5 | EXW_Power Generation Package A - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2450537 | 2450537 | 2205483 | 245054 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.1.6 | EXW_Power Generation Package A - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 201385865 | 201385865 | 181247279 | 20138586 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.1 | EXW_Power Generation Package B - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1284348632 | 1284348632 | 1284348632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.2 | EXW_Power Generation Package B - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1225969148 | 1225969148 | 1225969148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.3 | EXW_Power Generation Package B - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35027690 | 35027690 | 35027690 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.4 | EXW_Power Generation Package B - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42967300 | 42967300 | 42967300 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.5 | EXW_Power Generation Package B - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2450537 | 2450537 | 2205483 | 245054 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.2.6 | EXW_Power Generation Package B - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 201385865 | 201385865 | 181247279 | 20138586 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.1 | EXW_Power Generation Package C - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1284348632 | 1284348632 | 1284348632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.2 | EXW_Power Generation Package C - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1225969148 | 1225969148 | 1225969148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.3 | EXW_Power Generation Package C - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35027690 | 35027690 | 35027690 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.4 | EXW_Power Generation Package C - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42967300 | 42967300 | 42967300 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.5 | EXW_Power Generation Package C - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2450537 | 2450537 | 2205483 | 245054 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.3.6 | EXW_Power Generation Package C - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 201385865 | 201385865 | 120831519 | 80554346 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.1 | EXW_Power Generation Package D - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1284348632 | 1284348632 | 1284348632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.2 | EXW_Power Generation Package D - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1225969148 | 1225969148 | 1225969148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.3 | EXW_Power Generation Package D - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35027690 | 35027690 | 35027690 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.4 | EXW_Power Generation Package D - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42967300 | 42967300 | 42967300 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.5 | EXW_Power Generation Package D - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2450537 | 2450537 | 2205483 | 245054 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.4.6 | EXW_Power Generation Package D - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 201385865 | 201385865 | 120831519 | 80554346 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.1 | EXW_Power Generation Package E - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1284348632 | 1284348632 | 1284348632 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.2 | EXW_Power Generation Package E - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1225969148 | 1225969148 | 1225969148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.3 | EXW_Power Generation Package E - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35027690 | 35027690 | 35027690 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.4 | EXW_Power Generation Package E - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42967300 | 42967300 | 42967300 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.5 | EXW_Power Generation Package E - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2450537 | 2450537 | 2205483 | 245054 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.2.A.5.6 | EXW_Power Generation Package E - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 201385865 | 120831519 | 120831519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.1.1 | EXW_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 216502986 | 216502986 | 216502986 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.1.2 | EXW_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 361658398 | 361658398 | 361658398 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.1.3 | EXW_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22119971 | 22119971 | 22119971 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.1.4 | EXW_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16626344 | 16626344 | 16626344 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.1.5 | EXW_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2970203 | 2970203 | 2970203 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.2.1 | EXW_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 69802549 | 64218345 | 50257835 | 13960510 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.2.2 | EXW_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 600654848 | 552602460 | 432471491 | 120130969 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.2.3 | EXW_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 270431878 | 270431878 | 243388690 | 27043188 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.3.1 | EXW_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1610303812 | 1610303812 | 1597421382 | 12882430 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.4.1 | EXW_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11888571 | 11888571 | 10699714 | 1188857 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.4.2 | EXW_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 27871249 | 26756399 | 24247987 | 2508412 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.4.3 | EXW_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 133961293 | 133961293 | 120565164 | 13396129 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.5.1 | EXW_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 3480678 | 2088407 | 2088407 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.5.2 | EXW_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2610468 | 2610468 | 1566281 | 1044187 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | EXW.I.2.B.5.3 | EXW_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 4148527 | 2489116 | 2489116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.1.1 | EXW_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 49087052 | 49087052 | 49087052 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.1.2 | EXW_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46855822 | 46855822 | 46855822 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.1.3 | EXW_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9575369 | 9575369 | 9575369 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.1.4 | EXW_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39933413 | 39933413 | 39933413 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.1.5 | EXW_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10249955 | 10249955 | 10249955 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.2.1 | EXW_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 146618300 | 146618300 | 131956470 | 14661830 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.2.2 | EXW_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64389870 | 64389870 | 56019187 | 8370683 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.3.1 | EXW_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45274760 | 45274760 | 45274760 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.4.1 | EXW_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 3301285 | 3037182 | 2575002 | 462180 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.4.2 | EXW_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.87 | 31440805 | 27353500 | 27353500 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.4.3 | EXW_Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33327568 | 33327568 | 28994984 | 4332584 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.4.4 | EXW_Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 17119518 | 16434737 | 14380395 | 2054342 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.5.1 | EXW_Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35731159 | 35731159 | 35731159 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.5.2 | EXW_Plumbing & Sanitary - Septictank + Leatching Pit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15044392 | 15044392 | 13539953 | 1504439 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.6.1 | EXW_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34593314 | 34593314 | 20755988 | 13837326 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.6.2 | EXW_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8648195 | 8648195 | 5188917 | 3459278 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.6.3 | EXW_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51538554 | 51538554 | 41746229 | 9792325 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | EXW.I.3.A.6.4 | EXW_Doors & Windows - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19969748 | 19969748 | 17972773 | 1996975 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.1.1 | EXW_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 68192202 | 68192202 | 68192202 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.1.2 | EXW_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 113911974 | 113911974 | 113911974 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.1.3 | EXW_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6967153 | 6967153 | 6967153 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.1.4 | EXW_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5236819 | 5236819 | 5236819 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.1.5 | EXW_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 935528 | 935528 | 935528 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.2.1 | EXW_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21985791 | 21985791 | 19787212 | 2198579 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.2.2 | EXW_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 189188969 | 181621410 | 113513381 | 68108029 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.2.3 | EXW_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85178249 | 85178249 | 76660424 | 8517825 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.3.1 | EXW_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 507199299 | 507199299 | 507199299 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.4.1 | EXW_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 3744557 | 3669666 | 2246734 | 1422932 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.4.2 | EXW_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 8778640 | 8427494 | 7637417 | 790077 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.4.3 | EXW_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42193947 | 42193947 | 37974552 | 4219395 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.5.1 | EXW_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1644470 | 1644470 | 986682 | 657788 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.5.2 | EXW_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1233333 | 1233333 | 740000 | 493333 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | EXW.I.4.A.5.3 | EXW_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1960000 | 1960000 | 1176000 | 784000 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.1 | EXW_Fuel Oil Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2821837873 | 2821837873 | 2821837873 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.2 | EXW_Fuel Oil Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2693572516 | 2693572516 | 2693572516 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.3 | EXW_Fuel Oil Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 192398037 | 192398037 | 192398037 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.4 | EXW_Fuel Oil Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56732754 | 56732754 | 56732754 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.5 | EXW_Fuel Oil Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5384067 | 5384067 | 4845660 | 538407 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.1.6 | EXW_Fuel Oil Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 94965698 | 94965698 | 85469128 | 9496570 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.1 | EXW_Fuel Oil Forwarding Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 143262538 | 143262538 | 143262538 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.2 | EXW_Fuel Oil Forwarding Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 136750605 | 136750605 | 136750605 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.3 | EXW_Fuel Oil Forwarding Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9767900 | 9767900 | 9767900 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.4 | EXW_Fuel Oil Forwarding Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14069723 | 14069723 | 14069723 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.5 | EXW_Fuel Oil Forwarding Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 273345 | 273345 | 246011 | 27334 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.2.6 | EXW_Fuel Oil Forwarding Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 62677360 | 62677360 | 56409624 | 6267736 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.1 | EXW_Fuel Oil Purification Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 223214611 | 223214611 | 223214611 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.2 | EXW_Fuel Oil Purification Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 372869862 | 372869862 | 372869862 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.3 | EXW_Fuel Oil Purification Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35766302 | 35766302 | 35766302 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.4 | EXW_Fuel Oil Purification Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65507420 | 65507420 | 65507420 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.5 | EXW_Fuel Oil Purification Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5064837 | 5064837 | 5064837 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.1.6 | EXW_Fuel Oil Purification Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 59470987 | 59470987 | 59470987 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.2.1 | EXW_Fuel Oil Purification Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 292424707 | 292424707 | 175454824 | 116969883 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.3.1 | EXW_Fuel Oil Purification Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 189438067 | 189438067 | 170494260 | 18943807 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | EXW.I.5.A.3.4.1 | EXW_Fuel Oil Purification Shelter - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 131554213 | 78932528 | 78932528 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.1 | EXW_Air Compressor Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 383353344 | 383353344 | 383353344 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.2 | EXW_Air Compressor Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 365928192 | 365928192 | 365928192 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.3 | EXW_Air Compressor Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26137728 | 26137728 | 26137728 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.4 | EXW_Air Compressor Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37648889 | 37648889 | 37648889 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.5 | EXW_Air Compressor Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 731438 | 731438 | 658294 | 73144 | 1 | 3500235911 | 17964549
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | EXW.I.5.B.1.6 | EXW_Air Compressor Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 167717088 | 167717088 | 150945379 | 16771709 | 1 | 3500235911 | 17964549
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.1 | EXW_Fuel Gas System Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 83276434 | 83276434 | 83276434 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.2 | EXW_Fuel Gas System Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 79491142 | 79491142 | 79491142 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.3 | EXW_Fuel Gas System Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5677939 | 5677939 | 5677939 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.4 | EXW_Fuel Gas System Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4382211 | 4382211 | 4382211 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.5 | EXW_Fuel Gas System Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 158891 | 158891 | 95335 | 63556 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.1.6 | EXW_Fuel Gas System Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30470582 | 30470582 | 18282349 | 12188233 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.1 | EXW_Gas Metering System Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22871018 | 22871018 | 22871018 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.2 | EXW_Gas Metering System Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 38204995 | 38204995 | 38204995 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.3 | EXW_Gas Metering System Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1599934 | 1599934 | 1599934 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.4 | EXW_Gas Metering System Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10061611 | 10061611 | 10061611 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.5 | EXW_Gas Metering System Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 900054 | 900054 | 540032 | 360022 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.1.6 | EXW_Gas Metering System Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10568376 | 10568376 | 10568376 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.2.1 | EXW_Gas Metering System Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51860767 | 51860767 | 31116460 | 20744307 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | EXW.I.5.C.2.3.1 | EXW_Gas Metering System Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41893427 | 41893427 | 25136056 | 16757371 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.1 | EXW_Combine Raw Water Storage & Fire Water Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1138679177 | 1138679177 | 1138679177 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.2 | EXW_Combine Raw Water Storage & Fire Water Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1086921033 | 1086921033 | 1086921033 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.3 | EXW_Combine Raw Water Storage & Fire Water Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 77637217 | 77637217 | 77637217 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.4 | EXW_Combine Raw Water Storage & Fire Water Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22674997 | 22674997 | 22674997 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.5 | EXW_Combine Raw Water Storage & Fire Water Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2172600 | 2172600 | 1955340 | 217260 | 1 | 3500235911 | 48420926
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | EXW.I.5.D.1.6 | EXW_Combine Raw Water Storage & Fire Water Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 451856816 | 451856816 | 406671134 | 45185682 | 1 | 3500235911 | 48420926
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.1 | EXW_Gas Engine Radiator - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 821944572 | 821944572 | 821944572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.2 | EXW_Gas Engine Radiator - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 784583455 | 784583455 | 784583455 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.3 | EXW_Gas Engine Radiator - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56041675 | 56041675 | 56041675 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.4 | EXW_Gas Engine Radiator - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 46648023 | 46648023 | 46648023 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.5 | EXW_Gas Engine Radiator - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1568270 | 1568270 | 1568270 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | EXW.I.5.H.1.6 | EXW_Gas Engine Radiator - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 359600750 | 359600750 | 359600750 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.1 | EXW_Lube Oil Storage Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1018587848 | 1018587848 | 1018587848 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.2 | EXW_Lube Oil Storage Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 972288400 | 972288400 | 972288400 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.3 | EXW_Lube Oil Storage Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 69449171 | 69449171 | 69449171 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.4 | EXW_Lube Oil Storage Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 88390645 | 88390645 | 88390645 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.5 | EXW_Lube Oil Storage Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1943466 | 1943466 | 1943466 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | EXW.I.5.I.1.6 | EXW_Lube Oil Storage Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 303132169 | 303132169 | 303132169 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.1 | EXW_Exhaust Stack - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 381376393 | 360019315 | 360019315 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.2 | EXW_Exhaust Stack - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 364041103 | 343654801 | 343654801 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.3 | EXW_Exhaust Stack - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15601762 | 15601762 | 15601762 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.4 | EXW_Exhaust Stack - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 19528736 | 18435127 | 18435127 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.5 | EXW_Exhaust Stack - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8004328 | 8004328 | 7203895 | 800433 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.1.6 | EXW_Exhaust Stack - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16678268 | 16678268 | 15010441 | 1667827 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.2.1 | EXW_Exhaust Structure - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 838678616 | 838678616 | 754810754 | 83867862 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.2.2 | EXW_Exhaust Structure - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 168170736 | 168170736 | 100902442 | 67268294 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.2.3 | EXW_Exhaust Structure - Steel Ladder | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13797395 | 13797395 | 9934124 | 3863271 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | EXW.I.5.J.2.4 | EXW_Exhaust Structure - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 137973953 | 137973953 | 137973953 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.1 | EXW_Circulating Cooling Water System - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 590445424 | 590445424 | 590445424 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.2 | EXW_Circulating Cooling Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 563606995 | 563606995 | 563606995 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.3 | EXW_Circulating Cooling Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 40257643 | 40257643 | 40257643 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.4 | EXW_Circulating Cooling Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18518516 | 18518516 | 18518516 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.5 | EXW_Circulating Cooling Water System - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1126570 | 1126570 | 1013913 | 112657 | 1 | 3500235911 | 27669213
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | EXW.I.5.K.1.6 | EXW_Circulating Cooling Water System - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 258319873 | 258319873 | 232487886 | 25831987 | 1 | 3500235911 | 27669213
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.1 | EXW_Emergency Diesel Generator (EDG) - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33042991 | 33042991 | 33042991 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.2 | EXW_Emergency Diesel Generator (EDG) - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31541036 | 31541036 | 31541036 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.3 | EXW_Emergency Diesel Generator (EDG) - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3068088 | 3068088 | 3068088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.4 | EXW_Emergency Diesel Generator (EDG) - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4357978 | 4357978 | 4357978 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.5 | EXW_Emergency Diesel Generator (EDG) - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63046 | 63046 | 37828 | 25218 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.5.L.1.6 | EXW_Emergency Diesel Generator (EDG) - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4485162 | 4485162 | 2691097 | 1794065 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.1.1 | EXW_Transformer Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 148226748 | 148226748 | 148226748 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.1.2 | EXW_Transformer Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 176861461 | 176861461 | 176861461 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.1.3 | EXW_Transformer Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10106369 | 10106369 | 10106369 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.1.4 | EXW_Transformer Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9210731 | 9210731 | 9210731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.1.5 | EXW_Transformer Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48378133 | 48378133 | 29026880 | 19351253 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.2.1 | EXW_Fire Blast Transformer - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 221452278 | 221452278 | 199307050 | 22145228 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.2.2 | EXW_Fire Blast Transformer - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 264232831 | 264232831 | 237809548 | 26423283 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.2.3 | EXW_Fire Blast Transformer - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4995425 | 4995425 | 4995425 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.I.6.A.2.4 | EXW_Fire Blast Transformer - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 69686872 | 69686872 | 62718185 | 6968687 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | EXW.I.6.B.1.1 | EXW_Emergency Diesel Generator (Edg)/Black Start Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 76558301 | 76558301 | 45934981 | 30623320 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.C.1.1 | EXW_Electrical Tray Support - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51038867 | 51038867 | 41341482 | 9697385 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.1.1 | EXW_Duct Bank - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18544961 | 18544961 | 15577767 | 2967194 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.1.2 | EXW_Duct Bank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22127510 | 22127510 | 18587108 | 3540402 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.1.3 | EXW_Duct Bank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3219857 | 3219857 | 2704680 | 515177 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.1.4 | EXW_Duct Bank - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34940242 | 34940242 | 29349803 | 5590439 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.1.5 | EXW_Duct Bank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3485022 | 3485022 | 2927418 | 557604 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.2.1 | EXW_Trench - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18544961 | 18544961 | 16690465 | 1854496 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.2.2 | EXW_Trench - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22127510 | 22127510 | 20357309 | 1770201 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.2.3 | EXW_Trench - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3219857 | 3219857 | 3026666 | 193191 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.2.4 | EXW_Trench - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 34940242 | 34940242 | 31446218 | 3494024 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | EXW.I.6.D.2.5 | EXW_Trench - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3485022 | 3485022 | 3206220 | 278802 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.1 | EXW_WTP Package - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 94881382 | 94881382 | 94881382 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.2 | EXW_WTP Package - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90568592 | 90568592 | 90568592 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.3 | EXW_WTP Package - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6469185 | 6469185 | 6469185 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.4 | EXW_WTP Package - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1907580 | 1907580 | 1907580 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.5 | EXW_WTP Package - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 181034 | 181034 | 162931 | 18103 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.1.6 | EXW_WTP Package - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4151060 | 4151060 | 3735954 | 415106 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.1 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6842407 | 6842407 | 6842407 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.2 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6531389 | 6531389 | 6531389 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.3 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 466528 | 466528 | 466528 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.4 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 515047 | 515047 | 515047 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.5 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13055 | 13055 | 11750 | 1305 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.2.6 | EXW_Treated Water (Fresh Water) Water Tank & Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 910705 | 910705 | 819635 | 91070 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.1 | EXW_WTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12187088 | 12187088 | 12187088 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.2 | EXW_WTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20357976 | 20357976 | 20357976 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.3 | EXW_WTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 881219 | 881219 | 881219 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.4 | EXW_WTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5713203 | 5713203 | 5713203 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.5 | EXW_WTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 425750 | 425750 | 425750 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.1.6 | EXW_WTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4999126 | 4999126 | 4999126 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.2.1 | EXW_WTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 53572111 | 53572111 | 32143267 | 21428844 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | EXW.I.7.A.3.3.1 | EXW_WTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66244456 | 66244456 | 59620010 | 6624446 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.1 | EXW_Waste Water Treatment Facilities - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 170886365 | 170886365 | 170886365 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.2 | EXW_Waste Water Treatment Facilities - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 163118803 | 163118803 | 163118803 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.3 | EXW_Waste Water Treatment Facilities - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11651343 | 11651343 | 11651343 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.4 | EXW_Waste Water Treatment Facilities - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4764105 | 4764105 | 4764105 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.5 | EXW_Waste Water Treatment Facilities - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 326051 | 326051 | 293446 | 32605 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.1.6 | EXW_Waste Water Treatment Facilities - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7476278 | 7476278 | 6728650 | 747628 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.1 | EXW_WWTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31704959 | 31704959 | 31704959 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.2 | EXW_WWTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52961692 | 52961692 | 52961692 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.3 | EXW_WWTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2292510 | 2292510 | 2292510 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.4 | EXW_WWTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14863014 | 14863014 | 14863014 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.5 | EXW_WWTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1107597 | 1107597 | 1107597 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.1.6 | EXW_WWTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13005329 | 13005329 | 13005329 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.2.1 | EXW_WWTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 139368943 | 139368943 | 83621366 | 55747577 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | EXW.I.7.B.2.3.1 | EXW_WWTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 172336310 | 172336310 | 155102679 | 17233631 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.1 | EXW_Motor Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8706125 | 8706125 | 8706125 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.2 | EXW_Motor Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8310392 | 8310392 | 8310392 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.3 | EXW_Motor Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 593599 | 593599 | 593599 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.4 | EXW_Motor Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 847910 | 847910 | 847910 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.5 | EXW_Motor Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16611 | 16611 | 9967 | 6644 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.1.6 | EXW_Motor Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2706345 | 2706345 | 1623807 | 1082538 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.1 | EXW_Diesel Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8706125 | 8706125 | 8706125 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.2 | EXW_Diesel Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8310392 | 8310392 | 8310392 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.3 | EXW_Diesel Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 593599 | 593599 | 593599 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.4 | EXW_Diesel Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 847910 | 847910 | 847910 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.5 | EXW_Diesel Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16611 | 16611 | 9967 | 6644 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.2.6 | EXW_Diesel Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2706345 | 2706345 | 1623807 | 1082538 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.1 | EXW_Fire Water Diesel Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 927890 | 927890 | 927890 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.2 | EXW_Fire Water Diesel Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 885713 | 885713 | 885713 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.3 | EXW_Fire Water Diesel Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63265 | 63265 | 63265 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.4 | EXW_Fire Water Diesel Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 258684 | 258684 | 258684 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.5 | EXW_Fire Water Diesel Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1770 | 1770 | 1062 | 708 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.3.6 | EXW_Fire Water Diesel Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 125294 | 125294 | 75176 | 50118 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.1 | EXW_Jockey Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 526033 | 526033 | 526033 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.2 | EXW_Jockey Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 502123 | 502123 | 502123 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.3 | EXW_Jockey Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35866 | 35866 | 35866 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.4 | EXW_Jockey Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 194876 | 194876 | 194876 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.5 | EXW_Jockey Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1004 | 1004 | 602 | 402 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.4.6 | EXW_Jockey Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 38490 | 38490 | 23094 | 15396 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.1 | EXW_Fire Water Pump Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12225805 | 12225805 | 12225805 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.2 | EXW_Fire Water Pump Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20422652 | 20422652 | 20422652 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.3 | EXW_Fire Water Pump Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 855252 | 855252 | 855252 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.4 | EXW_Fire Water Pump Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5378479 | 5378479 | 5378479 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.5 | EXW_Fire Water Pump Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 481128 | 481128 | 481128 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.1.6 | EXW_Fire Water Pump Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5649373 | 5649373 | 5649373 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.2.1 | EXW_Fire Water Pump Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27722406 | 27722406 | 16633444 | 11088962 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | EXW.I.7.C.5.3.1 | EXW_Fire Water Pump Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22394320 | 22394320 | 20154888 | 2239432 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.1.1 | EXW_Laboratory - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28813140 | 28813140 | 28813140 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.1.2 | EXW_Laboratory - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48131041 | 48131041 | 48131041 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.1.3 | EXW_Laboratory - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6353689 | 6353689 | 6353689 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.1.4 | EXW_Laboratory - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4452262 | 4452262 | 4452262 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.2.1 | EXW_Laboratory - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 11112456 | 10223460 | 6667474 | 3555986 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.3.1 | EXW_Laboratory - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22724678 | 22724678 | 20452210 | 2272468 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.4.1 | EXW_Laboratory - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 4912458 | 2947475 | 2947475 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.4.2 | EXW_Laboratory - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 39868132 | 23920879 | 23920879 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.4.3 | EXW_Laboratory - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 4799313 | 2879588 | 2879588 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.4.4 | EXW_Laboratory - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2465284 | 1479170 | 1479170 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.5.1 | EXW_Laboratory - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 22296910 | 20513157 | 13378146 | 7135011 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.6.1 | EXW_Laboratory - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 3597812 | 2158687 | 2158687 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.6.2 | EXW_Laboratory - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 5396635 | 3237981 | 3237981 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.A.6.3 | EXW_Laboratory - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 4288136 | 2572882 | 2572882 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.1.1 | EXW_Security Guardhouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12590192 | 12590192 | 12590192 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.1.2 | EXW_Security Guardhouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21031344 | 21031344 | 21031344 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.1.3 | EXW_Security Guardhouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2776308 | 2776308 | 2776308 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.1.4 | EXW_Security Guardhouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1945461 | 1945461 | 1945461 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.2.1 | EXW_Security Guardhouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4855700 | 4855700 | 4370130 | 485570 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.3.1 | EXW_Security Guardhouse - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9929777 | 9929777 | 8936799 | 992978 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.4.1 | EXW_Security Guardhouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2146548 | 2146548 | 1931893 | 214655 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.4.2 | EXW_Security Guardhouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 17420782 | 10452469 | 10452469 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.4.3 | EXW_Security Guardhouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2097108 | 1258265 | 1258265 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.4.4 | EXW_Security Guardhouse - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1077231 | 646339 | 646339 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.5.1 | EXW_Security Guardhouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19485719 | 19485719 | 19485719 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.6.1 | EXW_Security Guardhouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3144201 | 3144201 | 1886521 | 1257680 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.6.2 | EXW_Security Guardhouse - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2358114 | 2358114 | 1414868 | 943246 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.I.8.B.6.3 | EXW_Security Guardhouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3747488 | 3747488 | 3372739 | 374749 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.1 | EXW_Workshop - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55917360 | 55917360 | 55917360 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.2 | EXW_Workshop - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 93407408 | 93407408 | 93407408 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.3 | EXW_Workshop - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7441770 | 7441770 | 7441770 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.4 | EXW_Workshop - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15883565 | 15883565 | 15883565 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.5 | EXW_Workshop - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 413656 | 413656 | 372290 | 41366 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.1.6 | EXW_Workshop - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4857116 | 4857116 | 4857116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.2.1 | EXW_Workshop - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 4822041 | 4436278 | 3761192 | 675086 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.2.2 | EXW_Workshop - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35703755 | 35703755 | 21422253 | 14281502 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.3.1 | EXW_Workshop - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 44008648 | 44008648 | 39607783 | 4400865 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.4.1 | EXW_Workshop - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 324908 | 324908 | 194945 | 129963 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.4.2 | EXW_Workshop - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1925378 | 1155227 | 1155227 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.4.3 | EXW_Workshop - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 41258107 | 24754864 | 24754864 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.4.4 | EXW_Workshop - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 32395560 | 19437336 | 19437336 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.5.1 | EXW_Workshop - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 33863637 | 31154546 | 20318182 | 10836364 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.6.1 | EXW_Workshop - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 6830199 | 4098119 | 4098119 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.6.2 | EXW_Workshop - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 10928421 | 6557053 | 6557053 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.C.6.3 | EXW_Workshop - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 13025291 | 7815175 | 7815175 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.1 | EXW_Warehouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55917360 | 55917360 | 55917360 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.2 | EXW_Warehouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 93407408 | 93407408 | 93407408 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.3 | EXW_Warehouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7441770 | 7441770 | 7441770 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.4 | EXW_Warehouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15883565 | 15883565 | 15883565 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.5 | EXW_Warehouse - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 413656 | 413656 | 372290 | 41366 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.1.6 | EXW_Warehouse - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4857116 | 4857116 | 4857116 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.2.1 | EXW_Warehouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 4822041 | 4436278 | 3761192 | 675086 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.2.2 | EXW_Warehouse - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35703755 | 35703755 | 21422253 | 14281502 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.3.1 | EXW_Warehouse - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 44008648 | 44008648 | 39607783 | 4400865 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.4.1 | EXW_Warehouse - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 324908 | 324908 | 194945 | 129963 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.4.2 | EXW_Warehouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1925378 | 1155227 | 1155227 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.4.3 | EXW_Warehouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 41258107 | 24754864 | 24754864 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.4.4 | EXW_Warehouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 32395560 | 19437336 | 19437336 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.5.1 | EXW_Warehouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 33863637 | 31154546 | 20318182 | 10836364 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.6.1 | EXW_Warehouse - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 6830199 | 4098119 | 4098119 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.6.2 | EXW_Warehouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 10928421 | 6557053 | 6557053 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | EXW.I.8.D.6.3 | EXW_Warehouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 13025291 | 7815175 | 7815175 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.1 | EXW_Carpark - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52108921 | 52108921 | 46898029 | 5210892 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.2 | EXW_Carpark - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87045584 | 87045584 | 78341026 | 8704558 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.3 | EXW_Carpark - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9442144 | 9442144 | 8497930 | 944214 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.4 | EXW_Carpark - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10531869 | 10531869 | 9478682 | 1053187 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.5 | EXW_Carpark - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 676321 | 676321 | 608689 | 67632 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.1.6 | EXW_Carpark - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7941317 | 7941317 | 7147185 | 794132 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.2.1 | EXW_Carpark - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67052529 | 67052529 | 40231517 | 26821012 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.E.3.1 | EXW_Carpark - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67456430 | 67456430 | 60710787 | 6745643 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.1.1 | EXW_Mosque - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 168008286 | 168008286 | 168008286 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.1.2 | EXW_Mosque - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 160371546 | 160371546 | 160371546 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.1.3 | EXW_Mosque - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19933285 | 19933285 | 19933285 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.1.4 | EXW_Mosque - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 61208822 | 61208822 | 61208822 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.2.1 | EXW_Mosque - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65109594 | 65109594 | 58598635 | 6510959 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.3.1 | EXW_Mosque - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 233630962 | 233630962 | 210267866 | 23363096 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.4.1 | EXW_Mosque - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 34121606 | 31391878 | 27638501 | 3753377 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.4.2 | EXW_Mosque - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 111417487 | 111417487 | 96933214 | 14484273 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.4.3 | EXW_Mosque - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 82016424 | 78735767 | 71354289 | 7381478 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.4.4 | EXW_Mosque - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 42129737 | 40444548 | 36652871 | 3791677 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.5.1 | EXW_Mosque - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 68586544 | 68586544 | 68586544 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.6.1 | EXW_Mosque - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33201216 | 33201216 | 19920730 | 13280486 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.6.2 | EXW_Mosque - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16600351 | 16600351 | 9960211 | 6640140 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.F.6.3 | EXW_Mosque - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 65952731 | 65952731 | 53421712 | 12531019 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.1 | EXW_Storage - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28383124 | 28383124 | 28383124 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.2 | EXW_Storage - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47412718 | 47412718 | 47412718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.3 | EXW_Storage - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4793878 | 4793878 | 4793878 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.4 | EXW_Storage - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6700664 | 6700664 | 6700664 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.5 | EXW_Storage - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 518075 | 518075 | 466268 | 51807 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.1.6 | EXW_Storage - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6083206 | 6083206 | 6083206 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.2.1 | EXW_Storage - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 34927225 | 20956335 | 20956335 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.3.1 | EXW_Storage - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31003777 | 31003777 | 27903399 | 3100378 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.8.G.4.1 | EXW_Storage - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 21530401 | 12918241 | 12918241 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.9.A.1.1 | EXW_Pit & Pond - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8728461 | 8728461 | 8030184 | 698277 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.9.A.1.2 | EXW_Pit & Pond - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10414641 | 10414641 | 9581470 | 833171 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.9.A.1.3 | EXW_Pit & Pond - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 368559 | 368559 | 339074 | 29485 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | EXW.I.9.A.1.4 | EXW_Pit & Pond - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2939092 | 2939092 | 2703965 | 235127 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | EXW.I.9.B.1.1 | EXW_Lighting Pole Foundation - Concrete for Non Structural | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1742849 | 1742849 | 1385565 | 357284 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | EXW.I.9.B.1.2 | EXW_Lighting Pole Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2541654 | 2541654 | 2020615 | 521039 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | EXW.I.9.B.1.3 | EXW_Lighting Pole Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 180168 | 180168 | 143234 | 36934 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | EXW.I.9.B.1.4 | EXW_Lighting Pole Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1150133 | 1150133 | 914356 | 235777 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | EXW.I.9.B.1.5 | EXW_Lighting Pole Foundation - Anchor Bolt M12 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 933992 | 933992 | 742524 | 191468 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.1 | EXW_Lightning Protection - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 517707 | 517707 | 310624 | 207083 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.2 | EXW_Lightning Protection - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 617719 | 617719 | 370631 | 247088 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.3 | EXW_Lightning Protection - Anchor Bolt M16 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177677 | 177677 | 106606 | 71071 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.4 | EXW_Lightning Protection - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 26741 | 26741 | 16045 | 10696 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.5 | EXW_Lightning Protection - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5148 | 5148 | 3089 | 2059 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.I.9.C.1.6 | EXW_Lightning Protection - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 78726 | 78726 | 47236 | 31490 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | EXW.I.9.D.1.1 | EXW_Pipe Sleeper - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18766877 | 18766877 | 17265527 | 1501350 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | EXW.I.9.D.1.2 | EXW_Pipe Sleeper - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22392296 | 22392296 | 20600912 | 1791384 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | EXW.I.9.D.1.3 | EXW_Pipe Sleeper - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1395883 | 1395883 | 1284212 | 111671 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | EXW.I.9.D.1.4 | EXW_Pipe Sleeper - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5315214 | 5315214 | 4889997 | 425217 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | EXW.I.9.D.1.5 | EXW_Pipe Sleeper - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1085778 | 1085778 | 998916 | 86862 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | EXW.I.9.E.1.1 | EXW_Road & Paving - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 201722684 | 188408987 | 138704518 | 49704469 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | EXW.I.9.E.1.2 | EXW_Road & Paving - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 5756816 | 5376866 | 3958387 | 1418479 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | EXW.I.9.E.1.3 | EXW_Road & Paving - Kansteen, L = 60 cm, W = 45 cm, H = 24 cm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 46030281 | 42992282 | 31650421 | 11341861 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | EXW.I.9.E.1.4 | EXW_Road & Paving - Gravel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 6292765 | 5877443 | 4326905 | 1550538 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.1.1 | EXW_Open Ditch for Storm Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 117518152 | 70510891 | 70510891 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.1.2 | EXW_Open Ditch for Storm Water System - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 23703265 | 14221959 | 14221959 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.1.3 | EXW_Open Ditch for Storm Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8502 | 105549466 | 89738156 | 82001380 | 7736776 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.2.1 | EXW_Open Ditch & RC Pipe for Oily Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 5323586 | 3194152 | 3194152 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.2.2 | EXW_Open Ditch & RC Pipe for Oily Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.7158 | 4135951 | 2960514 | 2881931 | 78583 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.3.1 | EXW_Manhole for Storm Water System - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 883109 | 883109 | 529865 | 353244 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.3.2 | EXW_Manhole for Storm Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1053709 | 1053709 | 632225 | 421484 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.3.3 | EXW_Manhole for Storm Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 56624 | 56624 | 33974 | 22650 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.3.4 | EXW_Manhole for Storm Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 338684 | 338684 | 203210 | 135474 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.4.1 | EXW_Culvert for Storm Water System - RC Pipe 500 @2.4m | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1126958 | 1126958 | 676175 | 450783 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.5.1 | EXW_Around Building & Shelter - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8197 | 25958511 | 21278191 | 18996438 | 2281753 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | EXW.I.9.F.5.2 | EXW_Around Building & Shelter - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 43184926 | 25910956 | 25910956 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | EXW.II.1.1.1 | EXW_Lubrication And Hydraulic System - Urea Tank For SCR Unit #1 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9912 | 668712594 | 662827923 | 590606963 | 72220960 | 1 | 3500235911 | 91652683
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | EXW.II.1.2.1 | EXW_Charge Air System/Air Intake System - Intake Air Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50667839 | 50667839 | 44993041 | 5674798 | 1 | 3500235911 | 6306749
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | EXW.II.1.3.1 | EXW_Exhaust System - Exhaust Gas Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.998 | 135114237 | 134844009 | 108631847 | 26212162 | 1 | 3500235911 | 57286301
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | EXW.II.1.3.2 | EXW_Exhaust System - Exhaust Gas Stack | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 253339194 | 253339194 | 228005275 | 25333919 | 1 | 3500235911 | 57286301
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | EXW.II.1.4 | EXW_Ventilation And Air Conditioning System - Air Conditioning for Central Control Room | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9968 | 514394303 | 512748241 | 435589096 | 77159145 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | EXW.II.1.5.1 | EXW_All Necessary Pipe Works, Flange And Coupling - Piping specialty items | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9944 | 81397245 | 80941420 | 70693507 | 10247913 | 1 | 3500235911 | 91652683
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | EXW.II.2.1.1 | EXW_Fuel Oil Supply System - Daily storage tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3749659039 | 3749659039 | 3629669950 | 119989089 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | EXW.II.2.1.2 | EXW_Fuel Oil Supply System - Fuel Oil Pilot and Clean Leakage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 281224428 | 281224428 | 253101985 | 28122443 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | EXW.II.2.1.3 | EXW_Fuel Oil Supply System - Fuel Oil Dirty oil Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51377540 | 51377540 | 46239786 | 5137754 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.1.1 | EXW_Pumps - Treated Water (Fresh Water) Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85539438 | 85539438 | 76985494 | 8553944 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.1.2 | EXW_Pumps - Service Water supply Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 85539438 | 85539438 | 76985494 | 8553944 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.2.1 | EXW_Water Treatment Unit - Sand Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30827375 | 30827375 | 27744638 | 3082737 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.2.2 | EXW_Water Treatment Unit - Ultra Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 43754984 | 43754984 | 39379486 | 4375498 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.2.3 | EXW_Water Treatment Unit - Carbon Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30827375 | 30827375 | 27744638 | 3082737 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.2.4 | EXW_Water Treatment Unit - Reverse Osmosis Unit, | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50964612 | 50964612 | 45868151 | 5096461 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.2.5 | EXW_Water Treatment Unit - Chemical Injection / Dosing Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 109264149 | 109264149 | 98337734 | 10926415 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.3.1 | EXW_Combined Service Water Tank And Fire Water Tank - Combined service water tank and fire water tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1296101157 | 1296101157 | 1166491041 | 129610116 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.4.1 | EXW_Fresh Water Tank - Fresh water tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8573238 | 8573238 | 7715914 | 857324 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | EXW.II.3.5.1 | EXW_Water Supply And Treatment Systems - All Necessary Items Required For Complete And Fuctional System - Piping special | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20577955 | 20577955 | 18088022 | 2489933 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.1 | EXW_Waste Water Collection & Treatment System - Sanitary Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 7665701 | 4599421 | 4599421 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.2 | EXW_Waste Water Collection & Treatment System - Oily Water Pit - Power generation Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2800929 | 1680557 | 1680557 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.3 | EXW_Waste Water Collection & Treatment System - Oily Water Pit - Transformer Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2800929 | 1680557 | 1680557 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.4 | EXW_Waste Water Collection & Treatment System - Oily Water Pit - Fuel Station Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2800929 | 1680557 | 1680557 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.5 | EXW_Waste Water Collection & Treatment System - Skimming Pond | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45515097 | 45515097 | 45515097 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | EXW.II.3A.1.6 | EXW_Waste Water Collection & Treatment System - Nutralization Pond | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7002323 | 7002323 | 7002323 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | EXW.II.4.1.1 | EXW_Workshop And Machinery Equipment - Forklift | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 40722882 | 39093967 | 24433729 | 14660238 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | EXW.II.4.1.2 | EXW_Workshop And Machinery Equipment - Crane for Power Generation Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2123252784 | 2123252784 | 1910927506 | 212325278 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | EXW.II.4.1.3 | EXW_Workshop And Machinery Equipment - Crane Workshop Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1204406886 | 1204406886 | 1083966197 | 120440689 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | EXW.II.4.1.4 | EXW_Workshop And Machinery Equipment - Crane Warehouse Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1204406886 | 1204406886 | 1083966197 | 120440689 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | EXW.II.5.1.1 | EXW_Air Conditioning And Ventilation - Administration Building VAC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 61898781 | 61898781 | 52552065 | 9346716 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | EXW.II.5.1.2 | EXW_Air Conditioning And Ventilation - Ventilation System of Ware House | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 1503614 | 1022458 | 947277 | 75181 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | EXW.II.5.1.3 | EXW_Air Conditioning And Ventilation - Ventilation System of Work Shop and Air Condition System for workshop office & wa | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 17291562 | 11758262 | 10893684 | 864578 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | EXW.II.5.1.4 | EXW_Air Conditioning And Ventilation - VAC for Switchyard Control Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 502457717 | 502457717 | 426586602 | 75871115 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | EXW.II.5.1.5 | EXW_Air Conditioning And Ventilation - Ventilation For Power House | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1287594889 | 1287594889 | 1093168061 | 194426828 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | EXW.III.1.1.1 | EXW_Generator And Main Output System - Busduct 11 KV | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 2294186427 | 2248302698 | 1858291006 | 390011692 | 1 | 3500235911 | 2693824859
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | EXW.III.1.1.2 | EXW_Generator And Main Output System - Busduct 0.4 KV | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 9254442516 | 9069353666 | 6940831887 | 2128521779 | 1 | 3500235911 | 2693824859
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.JQ | Procurement - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | EXW.III.2.1.1 | EXW_Medium Voltage Switchgears (Bus Collector) - MV Switchgears 11kV, 1250A, 25 kA IP 41,3ph, 4W Dead Front | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2138137645 | 2138137645 | 1924323881 | 213813764 | 1 | 3500235911 | 406573408
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.JQ | Procurement - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | EXW.III.2.1.2 | EXW_Medium Voltage Switchgears (Bus Collector) - MV Switchgears 11kV, 1000A, 25 kA IP 41,3ph, 4W Dead Front | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1605486236 | 1605486236 | 1444937612 | 160548624 | 1 | 3500235911 | 406573408
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.JC | Procurement - LIGHTING SYSTEM | EXW.III.2.10.1 | EXW_Lighting And Small Power Installation - Lighting Poles | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 330301304 | 330301304 | 252680498 | 77620806 | 1 | 3500235911 | 219189276
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.JC | Procurement - LIGHTING SYSTEM | EXW.III.2.10.2 | EXW_Lighting And Small Power Installation - Lighting Fixture & Power Devices | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 595999448 | 595999448 | 468693966 | 127305482 | 1 | 3500235911 | 219189276
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | EXW.III.2.11.1 | EXW_Communication Systems - Horn Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52389245 | 52389245 | 31433547 | 20955698 | 1 | 3500235911 | 42587031
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | EXW.III.2.11.2 | EXW_Communication Systems - Ceiling Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 47150320 | 47150320 | 28290192 | 18860128 | 1 | 3500235911 | 42587031
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | EXW.III.2.11.3 | EXW_Communication Systems - Telephone Analog | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 91681179 | 55008707 | 55008707 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | EXW.III.2.11.4 | EXW_Communication Systems - Hotline Telephone | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 14734475 | 8840685 | 8840685 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.III.2.12.1 | EXW_Closed Circuit TV System Equipment - CCTV outdoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 42375873 | 42375873 | 31146267 | 11229606 | 1 | 3500235911 | 13370951
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | EXW.III.2.12.2 | EXW_Closed Circuit TV System Equipment - CCTV indoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12712762 | 12712762 | 11441486 | 1271276 | 1 | 3500235911 | 13370951
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.FN | Procurement - CONTROL & MONITORING SYSTEM | EXW.III.2.13.1 | EXW_Power Plant Metering And Protection Panels Complete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80514159 | 80514159 | 68356521 | 12157638 | 1 | 3500235911 | 13003817
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.2.2.1 | EXW_Low Voltage Switchgears - LV Normal Switchboard | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 1850410311 | 1802299643 | 1493281121 | 309018522 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.2.2.2 | EXW_Low Voltage Switchgears - LV Essential Switchboard | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 1678967208 | 1635314061 | 1354926537 | 280387524 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.2.3.1 | EXW_Low Voltage Motor Control Centers - LV Switchboard for EDG | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 3300838986 | 3215017172 | 2663777062 | 551240110 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.1.1 | EXW_Power & Control Cables - 11 kV Medium Voltage Power Cable (8.7/15 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 1169538315 | 1152463056 | 977734031 | 174729025 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.1.2 | EXW_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - INDOOR LIGHTING | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 25655376 | 25280808 | 21447894 | 3832914 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.1.3 | EXW_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - OUTDOOR LIGHTING CABLE | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 92913265 | 91556731 | 77675490 | 13881241 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.1.4 | EXW_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & CONTROL CABLE | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 2862475374 | 2820683234 | 2393029413 | 427653821 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.1.5 | EXW_Power & Control Cables - Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 1864959569 | 1837731159 | 1559106200 | 278624959 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.1 | EXW_Cable Accessories, Support & Bulk Material - Electrical Bulk Materials | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 102678289 | 101179186 | 85839050 | 15340136 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.2 | EXW_Cable Accessories, Support & Bulk Material - Cable Glands | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 780940330 | 769538601 | 652866116 | 116672485 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.3 | EXW_Cable Accessories, Support & Bulk Material - Cable Accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 86087473 | 84830596 | 71969127 | 12861469 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.4 | EXW_Cable Accessories, Support & Bulk Material - Miscellaneous Support | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 105346614 | 103808553 | 88069769 | 15738784 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.5 | EXW_Cable Accessories, Support & Bulk Material - Cable Ladder & Tray System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 1008312173 | 993590815 | 842948977 | 150641838 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.6 | EXW_Cable Accessories, Support & Bulk Material - Local Control Station | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 248951628 | 245316934 | 208123561 | 37193373 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | EXW.III.2.7.2.7 | EXW_Cable Accessories, Support & Bulk Material - Junction Box & Condulet | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 218591673 | 215400235 | 182742639 | 32657596 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.III.2.8.1 | EXW_Grounding And Lightning Protection System - Earthing Bus Bar,Min 10-Holes | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5458860 | 5458860 | 4475173 | 983687 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.III.2.8.2 | EXW_Grounding And Lightning Protection System - Grounding Rod | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 141176747 | 141176747 | 115736697 | 25440050 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.III.2.8.3 | EXW_Grounding And Lightning Protection System - Lightning Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27954516 | 27954516 | 22917112 | 5037404 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.III.2.8.4 | EXW_Grounding And Lightning Protection System - Grounding Cables | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 182847152 | 182847152 | 149898095 | 32949057 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | EXW.III.2.8.5 | EXW_Grounding And Lightning Protection System - Other Earthing Material | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 146425827 | 146425827 | 120039893 | 26385934 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.BI | Procurement - CATHODIC PROTECTION SYSTEM | EXW.III.2.9.1 | EXW_Cathodic Protection System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 125965776 | 125965776 | 99198049 | 26767727 | 1 | 3500235911 | 28630776
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.III.3.1.1 | EXW_Generator Transformer - 25000 kVA, 11/70 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3268995940 | 3268995940 | 3046704216 | 222291724 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.III.3.1.2 | EXW_Generator Transformer - 15000 kVA, 11/70 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3062080604 | 3062080604 | 2853859123 | 208221481 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | EXW.III.3.2.1 | EXW_Unit Auxiliary Transformer - 2500 kVA, 11/0.4 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1237375501 | 1237375501 | 1050531800 | 186843701 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.4.1.1 | EXW_Complete 20/70/150 KV Substation Equipment - Current Transformer for 70 kV, Class 0.2, 0.5, 5PX20, 5P20, Outdoor, 25 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20690653 | 20690653 | 17959487 | 2731166 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.4.1.2 | EXW_Complete 20/70/150 KV Substation Equipment - Current Transformer for 70 kV, Class 0.2, 0.5, 5PX20, 5P20, Outdoor, 20 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28313525 | 28313525 | 24576140 | 3737385 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.4.1.3 | EXW_Complete 20/70/150 KV Substation Equipment - Post Insulator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 146244803 | 146244803 | 126940489 | 19304314 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | EXW.III.4.1.4 | EXW_Complete 20/70/150 KV Substation Equipment - 70 KV Metering Panel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 111612461 | 111612461 | 96879616 | 14732845 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.1 | FOB_Gas Engine & Auxiliary - Engine 7L 51/60DF | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5981202.95 | 5981202.95 | 5383082.66 | 598120.29 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.10 | FOB_Gas Engine & Auxiliary - Adapter for Exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80000 | 80000 | 57600 | 22400 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.11 | FOB_Gas Engine & Auxiliary - Expansion joint for exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 300000 | 300000 | 216000 | 84000 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.2 | FOB_Gas Engine & Auxiliary - Oil mist eliminator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 100000 | 100000 | 90000 | 10000 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.3 | FOB_Gas Engine & Auxiliary - Gas Control Line | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 250000 | 250000 | 225000 | 25000 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.4 | FOB_Gas Engine & Auxiliary - Ventilation system for exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9997 | 80000 | 79976 | 70464 | 9512 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.5 | FOB_Gas Engine & Auxiliary - Flexible Coupling | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 140000 | 117600 | 92400 | 25200 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.6 | FOB_Gas Engine & Auxiliary - Flywheel cover | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 180000 | 151200 | 118800 | 32400 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.7 | FOB_Gas Engine & Auxiliary - Foundation Frame seating | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.99 | 110000 | 108900 | 96932 | 11968 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.8 | FOB_Gas Engine & Auxiliary - Flexible pipe connections for the Engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67829 | 67829 | 52906.62 | 14922.38 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.1.9 | FOB_Gas Engine & Auxiliary - Rubber Expansion joint for intake air duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 200000 | 200000 | 144000 | 56000 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.1 | FOB_Special Tools For Engine - Standard and special tools for the engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 80417.41 | 80417.41 | 80417.41 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.2 | FOB_Special Tools For Engine - Crank web deflection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 266.35 | 266.35 | 266.35 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.3 | FOB_Special Tools For Engine - Electric valve cone grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8953.28 | 8953.28 | 8953.28 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.4 | FOB_Special Tools For Engine - Electric valve seat grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10976.38 | 10976.38 | 10976.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.5 | FOB_Special Tools For Engine - Tool for ACC (adaptive combustion control) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2449.21 | 2449.21 | 2449.21 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.6 | FOB_Special Tools For Engine - Assembly and reversing device for cylinder heads | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3931.54 | 3931.54 | 3931.54 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.10.7 | FOB_Special Tools For Engine - Tools for Turbocharger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 76.66 | 76.66 | 76.66 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.1 | FOB_Electrical Generator - Control Panel | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 600000 | 600000 | 540000 | 60000 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.2 | FOB_Electrical Generator - "CoCoS-EDS" engine diagnosis system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 270000 | 259200 | 162000 | 97200 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.3 | FOB_Electrical Generator - Connecting cables; EDS-Databox/CoCoS-EDS-Hardware | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 60000 | 57600 | 36000 | 21600 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.4 | FOB_Electrical Generator - Remote access device | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 400000 | 400000 | 344000 | 56000 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.5 | FOB_Electrical Generator - Three phase synchronous alternator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2000000 | 2000000 | 1800000 | 200000 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.6 | FOB_Electrical Generator - Automatic voltage regulator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 270000 | 270000 | 232200 | 37800 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | FOB.II.1.2.7 | FOB_Electrical Generator - Grouting material for alternator seating | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 92100 | 77364 | 66312 | 11052 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.1 | FOB_Cooling System - LT/HT Cooling Water Radiator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 90909.09 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.10 | FOB_Cooling System - HT Cooling Water Temperature Control Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.11 | FOB_Cooling System - LT Cooling Water Temperature Control Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.2 | FOB_Cooling System - HT Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.3 | FOB_Cooling System - LT Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.4 | FOB_Cooling System - Nozzle Cooling Water Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.5 | FOB_Cooling System - Nozzle Cooling Water Cooler | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.6 | FOB_Cooling System - Nozzle Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.7 | FOB_Cooling System - Jacket Water Preheating Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.8 | FOB_Cooling System - Jacket Water Preheater | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | FOB.II.1.3.9 | FOB_Cooling System - Cooling Water Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 90909.09 | 90909.09 | 81818.18 | 9090.91 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.4.1 | FOB_Charge Air System/Air Intake System - Intake Air Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 500000 | 500000 | 450000 | 50000 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.4.2 | FOB_Charge Air System/Air Intake System - Intake Air Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 500000 | 500000 | 450000 | 50000 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | FOB.II.1.5.1 | FOB_Exhaust System - Exhaust Gas Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 500000 | 500000 | 450000 | 50000 | 1 | 3500235947 | 229164.38
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | FOB.II.1.5.2 | FOB_Exhaust System - Rupture Disc | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 500000 | 500000 | 330000 | 170000 | 1 | 3500235947 | 229164.38
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.1 | FOB_Lubrication System - LO Unloading Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 45454.55 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.10 | FOB_Lubrication System - LO Purifier Heater | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.11 | FOB_Lubrication System - Used LO Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.2 | FOB_Lubrication System - LO Receiving Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 45454.55 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.3 | FOB_Lubrication System - LO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 45454.55 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.4 | FOB_Lubrication System - LO Filter for LO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.5 | FOB_Lubrication System - Pre. Lube. Oil Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.6 | FOB_Lubrication System - LO Cooler | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.7 | FOB_Lubrication System - LO Auto. Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.8 | FOB_Lubrication System - LO Purifier | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.1.6.9 | FOB_Lubrication System - LO Purifier Feed Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45454.55 | 45454.55 | 40909.1 | 4545.45 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.1 | FOB_Fuel Oil System - FO Purifier | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.10 | FOB_Fuel Oil System - Pilot Oil Flow Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.11 | FOB_Fuel Oil System - Pilot Oil Safety Regulating Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.12 | FOB_Fuel Oil System - Clean Oil Drain Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.13 | FOB_Fuel Oil System - Clean Oil Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.14 | FOB_Fuel Oil System - Dirty Oil Drain Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.15 | FOB_Fuel Oil System - Dirty Oil Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.2 | FOB_Fuel Oil System - FO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 33333.33 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.3 | FOB_Fuel Oil System - FO Supply Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 33333.33 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.4 | FOB_Fuel Oil System - FO Flow meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 20000 | 13333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.5 | FOB_Fuel Oil System - FO Duplex Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.6 | FOB_Fuel Oil System - FO Pressure Safety Regulating Valve for FO | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.7 | FOB_Fuel Oil System - Pilot Oil Supply Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 33333.33 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.8 | FOB_Fuel Oil System - Pilot Oil Automatic Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | FOB.II.1.7.9 | FOB_Fuel Oil System - Pilot Oil Duplex Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 33333.33 | 33333.33 | 30000 | 3333.33 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.8.1 | FOB_Compressed Air & Starting System - Starting Air Compressorr | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 174525.36 | 174525.36 | 157072.82 | 17452.54 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.8.2 | FOB_Compressed Air & Starting System - Control Air Dryer and Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 174525.36 | 174525.36 | 157072.82 | 17452.54 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.8.3 | FOB_Compressed Air & Starting System - Starting Air Reservoir | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 174525.36 | 174525.36 | 157072.82 | 17452.54 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.8.4 | FOB_Compressed Air & Starting System - Control Air Compressor | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 174525.36 | 174525.36 | 157072.82 | 17452.54 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | FOB.II.1.8.5 | FOB_Compressed Air & Starting System - Control Air Reservoir | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 174525.36 | 174525.36 | 157072.82 | 17452.54 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.1 | FOB_Initial Spare Parts - set of spare part for turbocharger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 731.71 | 731.71 | 731.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.2 | FOB_Initial Spare Parts - set of engine standard spare parts | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11467.22 | 11467.22 | 11467.22 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.3 | FOB_Initial Spare Parts - spare parts für operating and monitoring the engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5091.8 | 5091.8 | 5091.8 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.4 | FOB_Initial Spare Parts - spare parts for ACC (adaptive combustion control) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3704.26 | 3704.26 | 3704.26 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.5 | FOB_Initial Spare Parts - spare parts for SACOS | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13494.76 | 13494.76 | 13494.76 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.6 | FOB_Initial Spare Parts - spares for oil mist detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2638.74 | 2638.74 | 2638.74 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | FOB.II.1.9.7 | FOB_Initial Spare Parts - spare parts for alternator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3044.7 | 3044.7 | 3044.7 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.2.1 | FOB_Fuel Supply System - Coalescing Filters Capacity 7500 nM3/Hr, CS, Press. 9 Bar | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 32403.34 | 32403.34 | 26246.71 | 6156.63 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.2.2 | FOB_Fuel Supply System - Piping For Fuel Supply System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.81 | 269671.7 | 218434.08 | 218434.08 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | FOB.II.2.3 | FOB_Fuel Supply System - Valve For Supply System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 269671.7 | 269671.7 | 241086.5 | 28585.2 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.1 | FOB_Wastewater Collection and Treatment System - Piping for Colling Water System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8685 | 3115.71 | 2705.99 | 2705.99 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.2 | FOB_Wastewater Collection and Treatment System - Sludge pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 937.6 | 843.84 | 843.84 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.3 | FOB_Wastewater Collection and Treatment System - Transfer pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 937.6 | 562.56 | 562.56 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.4 | FOB_Wastewater Collection and Treatment System - Air Blower | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 6750.7 | 4050.42 | 4050.42 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.5 | FOB_Wastewater Collection and Treatment System - Discharge Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 937.6 | 562.56 | 562.56 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.6 | FOB_Wastewater Collection and Treatment System - Acid/caustic measuring tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2596.42 | 1557.85 | 1557.85 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.7 | FOB_Wastewater Collection and Treatment System - Oil Separator including oil skimmer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 100479.74 | 60287.84 | 60287.84 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.8 | FOB_Wastewater Collection and Treatment System - Piping For Water Treatment System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 5705.69 | 5135.12 | 5135.12 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | FOB.II.3.9 | FOB_Wastewater Collection and Treatment System - Valve For Water Treatment System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5705.69 | 5705.69 | 4279.27 | 1426.42 | 1 | 3500235947 | 1764.5
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.1 | FOB_Fire Protection System - Electric motor driven fire water pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20252.09 | 20252.09 | 9113.44 | 11138.65 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.10 | FOB_Fire Protection System - Piping For Fire Protection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.88 | 25137.05 | 22120.6 | 22120.6 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.11 | FOB_Fire Protection System - Valve For Fire Protection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.992 | 25137.05 | 24935.95 | 18098.68 | 6837.27 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.2 | FOB_Fire Protection System - Diesel driven fire water pump. | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30378.13 | 30378.13 | 13670.16 | 16707.97 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.3 | FOB_Fire Protection System - Jockey Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11580.04 | 11580.04 | 5211.02 | 6369.02 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.4 | FOB_Fire Protection System - Fire water loop | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 16876.74 | 7594.53 | 7594.53 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.5 | FOB_Fire Protection System - Local fire panels and a main Fire Alarm Annunciator Panel (FAAP) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 6750.7 | 3037.82 | 3037.82 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.6 | FOB_Fire Protection System - Fire alarm & detection system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.968 | 10126.04 | 9802.01 | 4556.72 | 5245.29 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.7 | FOB_Fire Protection System - CO2 extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 21602.23 | 12961.34 | 12961.34 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.8 | FOB_Fire Protection System - Dry Chemical extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 5064.29 | 3038.57 | 3038.57 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.II.4.9 | FOB_Fire Protection System - Fire extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2532.14 | 1519.28 | 1519.28 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.1 | FOB_Laboratory and Instruments - Conductivitymeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 810.08 | 364.54 | 364.54 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.10 | FOB_Laboratory and Instruments - Inductively Couplet Plasma Atomic Emission Spectrometry (ICP-AES) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 33753.48 | 15189.07 | 15189.07 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.11 | FOB_Laboratory and Instruments - Potentiometric Titrator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 4050.42 | 1822.69 | 1822.69 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.12 | FOB_Laboratory and Instruments - Oxidation test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 10126.04 | 4556.72 | 4556.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.13 | FOB_Laboratory and Instruments - Total base number test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1350.14 | 607.56 | 607.56 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.14 | FOB_Laboratory and Instruments - Hydrometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 675.07 | 303.78 | 303.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.15 | FOB_Laboratory and Instruments - Viscometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1687.67 | 759.45 | 759.45 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.16 | FOB_Laboratory and Instruments - Pensky Marren Closed Tester | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 13501.39 | 6075.63 | 6075.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.17 | FOB_Laboratory and Instruments - Tensiometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 67.51 | 30.38 | 30.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.18 | FOB_Laboratory and Instruments - Oxidation test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 10126.04 | 4556.72 | 4556.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.19 | FOB_Laboratory and Instruments - Gas Caloriemeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 33753.48 | 15189.07 | 15189.07 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.2 | FOB_Laboratory and Instruments - pH Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2700.28 | 1215.13 | 1215.13 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.20 | FOB_Laboratory and Instruments - Gas Chromatograph | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 47254.87 | 21264.69 | 21264.69 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.21 | FOB_Laboratory and Instruments - Combustion and Adsorption Apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 16876.74 | 7594.53 | 7594.53 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.22 | FOB_Laboratory and Instruments - Dew Point meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2025.21 | 911.34 | 911.34 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.23 | FOB_Laboratory and Instruments - Orsat Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 675.07 | 303.78 | 303.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.3 | FOB_Laboratory and Instruments - Spectrofotometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 675.07 | 303.78 | 303.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.4 | FOB_Laboratory and Instruments - Color Comparator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1687.67 | 759.45 | 759.45 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.5 | FOB_Laboratory and Instruments - Hydrometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 675.07 | 303.78 | 303.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.6 | FOB_Laboratory and Instruments - Quartz Tube Combustion Apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 16876.74 | 7594.53 | 7594.53 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.7 | FOB_Laboratory and Instruments - Viscosimeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1687.67 | 759.45 | 759.45 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.8 | FOB_Laboratory and Instruments - Pensky Marten Closed Tester | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 13501.39 | 6075.63 | 6075.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | FOB.II.5.9 | FOB_Laboratory and Instruments - Tensiometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 67.51 | 30.38 | 30.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.1 | FOB_Workshop and Machinery Equipment - Welding Machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2700.28 | 1215.13 | 1215.13 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.10 | FOB_Workshop and Machinery Equipment - Storage & Racks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 9147.19 | 8232.47 | 8232.47 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.2 | FOB_Workshop and Machinery Equipment - Lathe | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6750.7 | 6075.63 | 6075.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.3 | FOB_Workshop and Machinery Equipment - Grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2700.28 | 1215.13 | 1215.13 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.4 | FOB_Workshop and Machinery Equipment - Drilling Machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1350.14 | 607.56 | 607.56 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.5 | FOB_Workshop and Machinery Equipment - Vises | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 675.07 | 405.04 | 405.04 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.6 | FOB_Workshop and Machinery Equipment - Hand Tools Set consist of 3 sets | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1012.6 | 911.34 | 911.34 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.7 | FOB_Workshop and Machinery Equipment - Workbench | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1080.11 | 648.07 | 648.07 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.8 | FOB_Workshop and Machinery Equipment - Sawing machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 5400.56 | 3240.34 | 3240.34 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | FOB.II.6.9 | FOB_Workshop and Machinery Equipment - Threading machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 6750.7 | 6075.63 | 6075.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | FOB.III.1.1 | FOB_Neutral Earthing System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 36982.34 | 33284.11 | 33284.11 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | FOB.III.1.2 | FOB_Medium Voltage Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 36982.34 | 36242.69 | 29955.7 | 6286.99 | 1 | 3500235947 | 79454.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | FOB.III.1.3 | FOB_Low Voltage Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 298363.63 | 292396.36 | 223772.72 | 68623.64 | 1 | 3500235947 | 79454.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | FOB.III.1.4 | FOB_Uninterruptible AC power supply | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 46504.78 | 20927.15 | 20927.15 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AT | Procurement - BLACK-START GENERATOR SYSTEM | FOB.III.1.5 | FOB_Black Start/Emergency Diesel Generator (EDG) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 39162.61 | 37596.11 | 17623.17 | 19972.94 | 1 | 3500235947 | 21184.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | FOB.III.1.6 | FOB_DC System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 95567.54 | 91744.84 | 83143.76 | 8601.08 | 1 | 3500235947 | 9122.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | FOB.III.2.1 | FOB_48 V DC System for Switchyard | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 28697.6 | 22958.08 | 22958.08 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | FOB.III.2.2 | FOB_110 V Uninterruptible AC power supply for Switchyard | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 13504.75 | 10803.8 | 10803.8 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | FOB.IV.1.1 | FOB_Control System - PLC control system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 137522.2 | 132021.31 | 110361.57 | 21659.74 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | FOB.IV.1.2 | FOB_Control System - Power plant operation control desks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.7 | 70947.96 | 49663.57 | 44988.1 | 4675.47 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | FOB.IV.1.3 | FOB_Control System - Diagnostic Software License | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 82492.96 | 80843.1 | 71768.88 | 9074.22 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | FOB.IV.1.4 | FOB_Control System - Supervisory and Plant management system License | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 65994.37 | 63354.6 | 57415.1 | 5939.5 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.2.1 | FOB_Instrument Valve - Shutdown valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 9899.16 | 4454.62 | 4454.62 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.2.2 | FOB_Instrument Valve - Pressure Regulating Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 9899.16 | 9503.19 | 4454.62 | 5048.57 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.2.3 | FOB_Instrument Valve - Pressure Safety Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 9899.16 | 9503.19 | 4454.62 | 5048.57 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.2.4 | FOB_Instrument Valve - Deluge Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 9899.16 | 4454.62 | 4454.62 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.1 | FOB_Field Instruments - Pressure Transmitters | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.10 | FOB_Field Instruments - Sight Flow Glass | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.11 | FOB_Field Instruments - Orifice Plate | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.2 | FOB_Field Instruments - Differential Pressure Transmitters | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.3 | FOB_Field Instruments - Temperature Transmitters and Well | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.4 | FOB_Field Instruments - Level Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.5 | FOB_Field Instruments - Pressure Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.6 | FOB_Field Instruments - Pressure Switch | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.7 | FOB_Field Instruments - Temperature Gauge and Well | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.8 | FOB_Field Instruments - Level Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.3.9 | FOB_Field Instruments - Flow Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 42255.27 | 35477.52 | 19014.87 | 16462.65 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.4 | FOB_Analyzer Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 6479.17 | 2915.63 | 2915.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.IV.5.1 | FOB_Fire and Gas Detector - Smoke Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 2615.76 | 2511.13 | 1177.09 | 1334.04 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.IV.5.2 | FOB_Fire and Gas Detector - Manual Call Point | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.868 | 2615.76 | 2270.48 | 1177.09 | 1093.39 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.IV.5.3 | FOB_Fire and Gas Detector - Combustible Gas Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.952 | 2615.76 | 2490.2 | 1177.09 | 1313.11 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.IV.5.4 | FOB_Fire and Gas Detector - Heat Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 2615.76 | 2511.13 | 1177.09 | 1334.04 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | FOB.IV.5.5 | FOB_Fire and Gas Detector - Flame Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 2615.76 | 2511.13 | 1177.09 | 1334.04 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.6 | FOB_Junction Box | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 44850.03 | 40365.03 | 40365.03 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | FOB.IV.7 | FOB_Cable Gland & Accessories | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 4986.13 | 2243.76 | 2243.76 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.1.1.1 | INL_Steel Pile With 609 mm Diameter (Thickness 12 mm) - Gas Engine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 574560000 | 574560000 | 574560000 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.1.1 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18676419 | 18676419 | 18676419 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JY | Procurement - PILING WORKS | INL.1.11.2.2.1 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 Mm Diameter - Administration Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5602926 | 5602926 | 5602926 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.3.1 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Central Control Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5602926 | 5602926 | 5602926 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.4.1 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - HSD Storage And Facility | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28014629 | 28014629 | 16808777 | 11205852 | 1 | 3500235911 | 239861256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.4.2 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Service And Fire Water Storage Tank Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6281 | 28014629 | 17595988 | 16808777 | 787211 | 1 | 3500235911 | 239861256
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.4.3 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Gas Engine Radiator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9338210 | 9338210 | 9338210 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.4.4 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Lube Oil Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28014629 | 28014629 | 28014629 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.JY | Procurement - PILING WORKS | INL.1.11.2.4.5 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Emergency Diesel Generator (Edg) Including Hsd Fu | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9338210 | 9338210 | 9338210 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JY | Procurement - PILING WORKS | INL.1.11.2.5.1 | INL_Circular Hollow Pre-Stressed Concrete Piles With 400 mm Diameter - Plant Water Facilities | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9338210 | 9338210 | 9338210 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.LR | Procurement - TEMPORARY FACILITIES & UTILITIES | INL.I.1.A.1.1 | INL_Material for deep well & temporary facilities | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67005249 | 67005249 | 67005249 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | INL.I.10.1.1.1 | INL_Finished Grading | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 20064578 | 13643913 | 12038747 | 1605166 | 1 | 3500235911 | 28436634
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | INL.I.10.2.1.1 | INL_Enviromental Consideration And Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 20064578 | 12038747 | 12038747 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JB | Procurement - LANDSCAPING | INL.I.10.3.1.1 | INL_Site Landscaping | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 20064578 | 12038747 | 12038747 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.1 | INL_Power Generation Package A - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120276961 | 120276961 | 120276961 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.2 | INL_Power Generation Package A - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114809826 | 114809826 | 114809826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.3 | INL_Power Generation Package A - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3280281 | 3280281 | 3280281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.4 | INL_Power Generation Package A - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4023811 | 4023811 | 4023811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.5 | INL_Power Generation Package A - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229488 | 229488 | 206539 | 22949 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.1.6 | INL_Power Generation Package A - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18859427 | 18859427 | 16973484 | 1885943 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.1 | INL_Power Generation Package B - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120276961 | 120276961 | 120276961 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.2 | INL_Power Generation Package B - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114809826 | 114809826 | 114809826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.3 | INL_Power Generation Package B - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3280281 | 3280281 | 3280281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.4 | INL_Power Generation Package B - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4023811 | 4023811 | 4023811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.5 | INL_Power Generation Package B - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229488 | 229488 | 206539 | 22949 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.2.6 | INL_Power Generation Package B - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18859427 | 18859427 | 16973484 | 1885943 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.1 | INL_Power Generation Package C - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120276961 | 120276961 | 120276961 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.2 | INL_Power Generation Package C - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114809826 | 114809826 | 114809826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.3 | INL_Power Generation Package C - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3280281 | 3280281 | 3280281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.4 | INL_Power Generation Package C - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4023811 | 4023811 | 4023811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.5 | INL_Power Generation Package C - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229488 | 229488 | 206539 | 22949 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.3.6 | INL_Power Generation Package C - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18859427 | 18859427 | 11315656 | 7543771 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.1 | INL_Power Generation Package D - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120276961 | 120276961 | 120276961 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.2 | INL_Power Generation Package D - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114809826 | 114809826 | 114809826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.3 | INL_Power Generation Package D - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3280281 | 3280281 | 3280281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.4 | INL_Power Generation Package D - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4023811 | 4023811 | 4023811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.5 | INL_Power Generation Package D - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229488 | 229488 | 206539 | 22949 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.4.6 | INL_Power Generation Package D - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18859427 | 18859427 | 11315656 | 7543771 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.1 | INL_Power Generation Package E - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 120276961 | 120276961 | 120276961 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.2 | INL_Power Generation Package E - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114809826 | 114809826 | 114809826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.3 | INL_Power Generation Package E - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3280281 | 3280281 | 3280281 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.4 | INL_Power Generation Package E - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4023811 | 4023811 | 4023811 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.5 | INL_Power Generation Package E - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 229488 | 229488 | 206539 | 22949 | 1 | 3500235911 | 221585307
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.2.A.5.6 | INL_Power Generation Package E - Epoxy Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 18859427 | 11315656 | 11315656 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.1.1 | INL_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12952078 | 12952078 | 12952078 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.1.2 | INL_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 21635858 | 21635858 | 21635858 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.1.3 | INL_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1323305 | 1323305 | 1323305 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.1.4 | INL_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 994655 | 994655 | 994655 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.1.5 | INL_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 177689 | 177689 | 177689 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.2.1 | INL_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 4175869 | 3841799 | 3006626 | 835173 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.2.2 | INL_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 35933585 | 33058898 | 25872181 | 7186717 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.2.3 | INL_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16178321 | 16178321 | 14560489 | 1617832 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.3.1 | INL_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 96334841 | 96334841 | 95564162 | 770679 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.4.1 | INL_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 711222 | 711222 | 640100 | 71122 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.4.2 | INL_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 1667370 | 1600675 | 1450612 | 150063 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.4.3 | INL_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8014103 | 8014103 | 7212693 | 801410 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.5.1 | INL_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 208228 | 124937 | 124937 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.5.2 | INL_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 156169 | 156169 | 93701 | 62468 | 1 | 3500235911 | 203650146
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DU | Procurement - CIVIL WORKS FOR POWER HOUSE FOR GAS ENGINE GENERATOR SYSTEM | INL.I.2.B.5.3 | INL_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 248182 | 148909 | 148909 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.1.1 | INL_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2588071 | 2588071 | 2588071 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.1.2 | INL_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2470431 | 2470431 | 2470431 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.1.3 | INL_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 504853 | 504853 | 504853 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.1.4 | INL_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2105454 | 2105454 | 2105454 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.1.5 | INL_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 540420 | 540420 | 540420 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.2.1 | INL_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7730319 | 7730319 | 6957287 | 773032 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.2.2 | INL_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3394898 | 3394898 | 2953561 | 441337 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.3.1 | INL_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2387071 | 2387071 | 2387071 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.4.1 | INL_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 174057 | 160132 | 135764 | 24368 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.4.2 | INL_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.87 | 1657688 | 1442189 | 1442189 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.4.3 | INL_Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1757166 | 1757166 | 1528734 | 228432 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.4.4 | INL_Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 902611 | 866507 | 758193 | 108314 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.5.1 | INL_Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1883894 | 1883894 | 1883894 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.5.2 | INL_Plumbing & Sanitary - Septictank + Leatching Pit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 793202 | 793202 | 713882 | 79320 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.6.1 | INL_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1823902 | 1823902 | 1094341 | 729561 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.6.2 | INL_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 455968 | 455968 | 273581 | 182387 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.6.3 | INL_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2717324 | 2717324 | 2201032 | 516292 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AP | Procurement - ADMINISTRATION BUILDING | INL.I.3.A.6.4 | INL_Doors & Windows - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1052887 | 1052887 | 947598 | 105289 | 1 | 3500235911 | 63660294
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.1.1 | INL_Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4079531 | 4079531 | 4079531 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.1.2 | INL_Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6814672 | 6814672 | 6814672 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.1.3 | INL_Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 416803 | 416803 | 416803 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.1.4 | INL_Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 313288 | 313288 | 313288 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.1.5 | INL_Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55967 | 55967 | 55967 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.2.1 | INL_Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1315278 | 1315278 | 1183750 | 131528 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.2.2 | INL_Substructure - Double Skin Insulated Metal Siding c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 11318044 | 10865322 | 6790826 | 4074496 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.2.3 | INL_Substructure - Double Skin Insulated Metal Roofing c/w Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5095705 | 5095705 | 4586135 | 509570 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.3.1 | INL_Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30342699 | 30342699 | 30342699 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.4.1 | INL_Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 224014 | 219534 | 134408 | 85126 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.4.2 | INL_Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 525174 | 504167 | 456901 | 47266 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.4.3 | INL_Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2524211 | 2524211 | 2271790 | 252421 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.5.1 | INL_Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 98379 | 98379 | 59027 | 39352 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.5.2 | INL_Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 73783 | 73783 | 44270 | 29513 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.FL | Procurement - CONTROL & MONITORING BUILDING | INL.I.4.A.5.3 | INL_Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 117255 | 117255 | 70353 | 46902 | 1 | 3500235911 | 92408132
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.1 | INL_Fuel Oil Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 188774700 | 188774700 | 188774700 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.2 | INL_Fuel Oil Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 180194032 | 180194032 | 180194032 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.3 | INL_Fuel Oil Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12871002 | 12871002 | 12871002 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.4 | INL_Fuel Oil Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3795296 | 3795296 | 3795296 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.5 | INL_Fuel Oil Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 360182 | 360182 | 324164 | 36018 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.1.6 | INL_Fuel Oil Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6352995 | 6352995 | 5717696 | 635299 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.1 | INL_Fuel Oil Forwarding Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9583946 | 9583946 | 9583946 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.2 | INL_Fuel Oil Forwarding Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9148312 | 9148312 | 9148312 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.3 | INL_Fuel Oil Forwarding Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 653451 | 653451 | 653451 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.4 | INL_Fuel Oil Forwarding Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 941233 | 941233 | 941233 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.5 | INL_Fuel Oil Forwarding Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18286 | 18286 | 16457 | 1829 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.2.6 | INL_Fuel Oil Forwarding Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4192977 | 4192977 | 3773679 | 419298 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.1 | INL_Fuel Oil Purification Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 14932563 | 14932563 | 14932563 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.2 | INL_Fuel Oil Purification Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24944167 | 24944167 | 24944167 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.3 | INL_Fuel Oil Purification Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2392686 | 2392686 | 2392686 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.4 | INL_Fuel Oil Purification Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4382301 | 4382301 | 4382301 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.5 | INL_Fuel Oil Purification Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 338826 | 338826 | 338826 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.1.6 | INL_Fuel Oil Purification Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3978477 | 3978477 | 3978477 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.2.1 | INL_Fuel Oil Purification Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19562565 | 19562565 | 11737539 | 7825026 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.3.1 | INL_Fuel Oil Purification Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12672987 | 12672987 | 11405688 | 1267299 | 1 | 3500235911 | 162428506
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DH | Procurement - CIVIL WORKS FOR LIQUID FUEL HANDLING SYSTEM | INL.I.5.A.3.4.1 | INL_Fuel Oil Purification Shelter - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 8800685 | 5280411 | 5280411 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.1 | INL_Air Compressor Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25481930 | 25481930 | 25481930 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.2 | INL_Air Compressor Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24323660 | 24323660 | 24323660 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.3 | INL_Air Compressor Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1737404 | 1737404 | 1737404 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.4 | INL_Air Compressor Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2502564 | 2502564 | 2502564 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.5 | INL_Air Compressor Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 48620 | 48620 | 43758 | 4862 | 1 | 3500235911 | 17964549
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EF | Procurement - CIVIL WORKS FOR SERVICE & CONTROL AIR SYSTEM | INL.I.5.B.1.6 | INL_Air Compressor Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11148344 | 11148344 | 10033510 | 1114834 | 1 | 3500235911 | 17964549
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.1 | INL_Fuel Gas System Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5535479 | 5535479 | 5535479 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.2 | INL_Fuel Gas System Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5283866 | 5283866 | 5283866 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.3 | INL_Fuel Gas System Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 377419 | 377419 | 377419 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.4 | INL_Fuel Gas System Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 291291 | 291291 | 291291 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.5 | INL_Fuel Gas System Foundation - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10562 | 10562 | 6337 | 4225 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.1.6 | INL_Fuel Gas System Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2025414 | 2025414 | 1215248 | 810166 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.1 | INL_Gas Metering System Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1520262 | 1520262 | 1520262 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.2 | INL_Gas Metering System Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2539529 | 2539529 | 2539529 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.3 | INL_Gas Metering System Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 106349 | 106349 | 106349 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.4 | INL_Gas Metering System Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 668807 | 668807 | 668807 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.5 | INL_Gas Metering System Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 59828 | 59828 | 35897 | 23931 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.1.6 | INL_Gas Metering System Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 702492 | 702492 | 702492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.2.1 | INL_Gas Metering System Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3447244 | 3447244 | 2068346 | 1378898 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CV | Procurement - CIVIL WORKS FOR GASEOUS FUEL HANDLING SYSTEM | INL.I.5.C.2.3.1 | INL_Gas Metering System Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2784703 | 2784703 | 1670822 | 1113881 | 1 | 3500235911 | 53444590
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.1 | INL_Combine Raw Water Storage & Fire Water Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 75689291 | 75689291 | 75689291 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.2 | INL_Combine Raw Water Storage & Fire Water Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 72248868 | 72248868 | 72248868 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.3 | INL_Combine Raw Water Storage & Fire Water Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5160633 | 5160633 | 5160633 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.4 | INL_Combine Raw Water Storage & Fire Water Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1507233 | 1507233 | 1507233 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.5 | INL_Combine Raw Water Storage & Fire Water Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 144415 | 144415 | 129974 | 14441 | 1 | 3500235911 | 48420926
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EB | Procurement - CIVIL WORKS FOR RAW WATER SYSTEM | INL.I.5.D.1.6 | INL_Combine Raw Water Storage & Fire Water Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30035433 | 30035433 | 27031890 | 3003543 | 1 | 3500235911 | 48420926
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.1 | INL_Gas Engine Radiator - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 54635584 | 54635584 | 54635584 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.2 | INL_Gas Engine Radiator - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52152148 | 52152148 | 52152148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.3 | INL_Gas Engine Radiator - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3725153 | 3725153 | 3725153 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.4 | INL_Gas Engine Radiator - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3100747 | 3100747 | 3100747 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.5 | INL_Gas Engine Radiator - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 104245 | 104245 | 104245 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.EA | Procurement - CIVIL WORKS FOR RADIATOR SYSTEM | INL.I.5.H.1.6 | INL_Gas Engine Radiator - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 23903068 | 23903068 | 23903068 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.1 | INL_Lube Oil Storage Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67706684 | 67706684 | 67706684 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.2 | INL_Lube Oil Storage Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64629108 | 64629108 | 64629108 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.3 | INL_Lube Oil Storage Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4616365 | 4616365 | 4616365 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.4 | INL_Lube Oil Storage Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5875426 | 5875426 | 5875426 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.5 | INL_Lube Oil Storage Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 129184 | 129184 | 129184 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CP | Procurement - CIVIL WORKS FOR GAS ENGINE MODULE & AUXILIARY SYSTEM | INL.I.5.I.1.6 | INL_Lube Oil Storage Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20149538 | 20149538 | 20149538 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.1 | INL_Exhaust Stack - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 25350519 | 23930890 | 23930890 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.2 | INL_Exhaust Stack - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 24198223 | 22843123 | 22843123 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.3 | INL_Exhaust Stack - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1037067 | 1037067 | 1037067 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.4 | INL_Exhaust Stack - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.944 | 1298097 | 1225404 | 1225404 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.5 | INL_Exhaust Stack - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 532057 | 532057 | 478851 | 53206 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.1.6 | INL_Exhaust Stack - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1108623 | 1108623 | 997761 | 110862 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.2.1 | INL_Exhaust Structure - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55747915 | 55747915 | 50173124 | 5574791 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.2.2 | INL_Exhaust Structure - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11178499 | 11178499 | 6707099 | 4471400 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.2.3 | INL_Exhaust Structure - Steel Ladder | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 917128 | 917128 | 660332 | 256796 | 1 | 3500235911 | 167934742
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.CL | Procurement - CIVIL WORKS FOR EXHAUST SYSTEM | INL.I.5.J.2.4 | INL_Exhaust Structure - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9171284 | 9171284 | 9171284 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.1 | INL_Circulating Cooling Water System - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 39247574 | 39247574 | 39247574 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.2 | INL_Circulating Cooling Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 37463593 | 37463593 | 37463593 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.3 | INL_Circulating Cooling Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2675971 | 2675971 | 2675971 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.4 | INL_Circulating Cooling Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1230947 | 1230947 | 1230947 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.5 | INL_Circulating Cooling Water System - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 74884 | 74884 | 67396 | 7488 | 1 | 3500235911 | 27669213
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.BU | Procurement - CIVIL WORKS FOR CIRCULATING WATER SYSTEM | INL.I.5.K.1.6 | INL_Circulating Cooling Water System - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 17170814 | 17170814 | 15453733 | 1717081 | 1 | 3500235911 | 27669213
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.1 | INL_Emergency Diesel Generator (EDG) - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2196405 | 2196405 | 2196405 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.2 | INL_Emergency Diesel Generator (EDG) - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2096568 | 2096568 | 2096568 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.3 | INL_Emergency Diesel Generator (EDG) - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 203939 | 203939 | 203939 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.4 | INL_Emergency Diesel Generator (EDG) - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 289680 | 289680 | 289680 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.5 | INL_Emergency Diesel Generator (EDG) - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4191 | 4191 | 2515 | 1676 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.5.L.1.6 | INL_Emergency Diesel Generator (EDG) - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 298134 | 298134 | 178880 | 119254 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.1.1 | INL_Transformer Foundation - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8867519 | 8867519 | 8867519 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.1.2 | INL_Transformer Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10580563 | 10580563 | 10580563 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.1.3 | INL_Transformer Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 604604 | 604604 | 604604 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.1.4 | INL_Transformer Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 551023 | 551023 | 551023 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.1.5 | INL_Transformer Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2894174 | 2894174 | 1736504 | 1157670 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.2.1 | INL_Fire Blast Transformer - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13248165 | 13248165 | 11923349 | 1324816 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.2.2 | INL_Fire Blast Transformer - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15807469 | 15807469 | 14226722 | 1580747 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.2.3 | INL_Fire Blast Transformer - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 298846 | 298846 | 298846 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DX | Procurement - CIVIL WORKS FOR POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.I.6.A.2.4 | INL_Fire Blast Transformer - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4168949 | 4168949 | 3752054 | 416895 | 1 | 3500235911 | 79368579
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BP | Procurement - CIVIL WORKS FOR BLACK-START GENERATOR SYSTEM | INL.I.6.B.1.1 | INL_Emergency Diesel Generator (Edg)/Black Start Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4580025 | 4580025 | 2748015 | 1832010 | 1 | 3500235911 | 34395543
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.C.1.1 | INL_Electrical Tray Support - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3053350 | 3053350 | 2473214 | 580136 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.1.1 | INL_Duct Bank - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1109434 | 1109434 | 931925 | 177509 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.1.2 | INL_Duct Bank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1323757 | 1323757 | 1111956 | 211801 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.1.3 | INL_Duct Bank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 192625 | 192625 | 161805 | 30820 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.1.4 | INL_Duct Bank - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2090266 | 2090266 | 1755823 | 334443 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.1.5 | INL_Duct Bank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 208488 | 208488 | 175130 | 33358 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.2.1 | INL_Trench - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1109434 | 1109434 | 998491 | 110943 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.2.2 | INL_Trench - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1323757 | 1323757 | 1217856 | 105901 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.2.3 | INL_Trench - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 192625 | 192625 | 181068 | 11557 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.2.4 | INL_Trench - PVC Pipe Dia. 4" | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2090266 | 2090266 | 1881239 | 209027 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.BR | Procurement - CIVIL WORKS FOR CABLE LAYING PROTECTION | INL.I.6.D.2.5 | INL_Trench - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 208488 | 208488 | 191809 | 16679 | 1 | 3500235911 | 32281089
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.1 | INL_WTP Package - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5676185 | 5676185 | 5676185 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.2 | INL_WTP Package - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5418177 | 5418177 | 5418177 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.3 | INL_WTP Package - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 387013 | 387013 | 387013 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.4 | INL_WTP Package - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 114119 | 114119 | 114119 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.5 | INL_WTP Package - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10830 | 10830 | 9747 | 1083 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.1.6 | INL_WTP Package - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 248333 | 248333 | 223500 | 24833 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.1 | INL_Treated Water (Fresh Water) Water Tank & Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 409340 | 409340 | 409340 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.2 | INL_Treated Water (Fresh Water) Water Tank & Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 390734 | 390734 | 390734 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.3 | INL_Treated Water (Fresh Water) Water Tank & Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 27910 | 27910 | 27910 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.4 | INL_Treated Water (Fresh Water) Water Tank & Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30812 | 30812 | 30812 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.5 | INL_Treated Water (Fresh Water) Water Tank & Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 781 | 781 | 703 | 78 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.2.6 | INL_Treated Water (Fresh Water) Water Tank & Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 54482 | 54482 | 49034 | 5448 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.1 | INL_WTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 729081 | 729081 | 729081 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.2 | INL_WTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1217896 | 1217896 | 1217896 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.3 | INL_WTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52718 | 52718 | 52718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.4 | INL_WTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 341787 | 341787 | 341787 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.5 | INL_WTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25470 | 25470 | 25470 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.1.6 | INL_WTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 299068 | 299068 | 299068 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.2.1 | INL_WTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3204899 | 3204899 | 1922939 | 1281960 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.ES | Procurement - CIVIL WORKS FOR WATER TREATMENT PLANT SYSTEM | INL.I.7.A.3.3.1 | INL_WTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3963009 | 3963009 | 3566708 | 396301 | 1 | 3500235911 | 30288577
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.1 | INL_Waste Water Treatment Facilities - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10223109 | 10223109 | 10223109 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.2 | INL_Waste Water Treatment Facilities - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9758422 | 9758422 | 9758422 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.3 | INL_Waste Water Treatment Facilities - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 697030 | 697030 | 697030 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.4 | INL_Waste Water Treatment Facilities - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 285008 | 285008 | 285008 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.5 | INL_Waste Water Treatment Facilities - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19506 | 19506 | 17555 | 1951 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.1.6 | INL_Waste Water Treatment Facilities - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 447261 | 447261 | 402535 | 44726 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.1 | INL_WWTP Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1896718 | 1896718 | 1896718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.2 | INL_WWTP Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3168381 | 3168381 | 3168381 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.3 | INL_WWTP Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 137147 | 137147 | 137147 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.4 | INL_WWTP Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 889165 | 889165 | 889165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.5 | INL_WWTP Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 66261 | 66261 | 66261 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.1.6 | INL_WWTP Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 778031 | 778031 | 778031 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.2.1 | INL_WWTP Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8337610 | 8337610 | 5002566 | 3335044 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.EP | Procurement - CIVIL WORKS FOR WASTE WATER TREATMENT SYSTEM | INL.I.7.B.2.3.1 | INL_WWTP Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10309850 | 10309850 | 9278865 | 1030985 | 1 | 3500235911 | 78174147
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.1 | INL_Motor Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 520835 | 520835 | 520835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.2 | INL_Motor Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 497161 | 497161 | 497161 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.3 | INL_Motor Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35512 | 35512 | 35512 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.4 | INL_Motor Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50725 | 50725 | 50725 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.5 | INL_Motor Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 994 | 994 | 596 | 398 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.1.6 | INL_Motor Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161904 | 161904 | 97142 | 64762 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.1 | INL_Diesel Driven Fire Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 520835 | 520835 | 520835 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.2 | INL_Diesel Driven Fire Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 497161 | 497161 | 497161 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.3 | INL_Diesel Driven Fire Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35512 | 35512 | 35512 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.4 | INL_Diesel Driven Fire Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 50725 | 50725 | 50725 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.5 | INL_Diesel Driven Fire Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 994 | 994 | 596 | 398 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.2.6 | INL_Diesel Driven Fire Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 161904 | 161904 | 97142 | 64762 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.1 | INL_Fire Water Diesel Daily Tank - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55510 | 55510 | 55510 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.2 | INL_Fire Water Diesel Daily Tank - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52987 | 52987 | 52987 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.3 | INL_Fire Water Diesel Daily Tank - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3785 | 3785 | 3785 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.4 | INL_Fire Water Diesel Daily Tank - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15476 | 15476 | 15476 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.5 | INL_Fire Water Diesel Daily Tank - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 106 | 106 | 64 | 42 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.3.6 | INL_Fire Water Diesel Daily Tank - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7496 | 7496 | 4498 | 2998 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.1 | INL_Jockey Pump - Concrete for machinery equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 31469 | 31469 | 31469 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.2 | INL_Jockey Pump - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30039 | 30039 | 30039 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.3 | INL_Jockey Pump - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2146 | 2146 | 2146 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.4 | INL_Jockey Pump - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11658 | 11658 | 11658 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.5 | INL_Jockey Pump - Anchor Bolt for equipment foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 60 | 60 | 36 | 24 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.4.6 | INL_Jockey Pump - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2303 | 2303 | 1382 | 921 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.1 | INL_Fire Water Pump Shelter - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 731397 | 731397 | 731397 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.2 | INL_Fire Water Pump Shelter - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1221765 | 1221765 | 1221765 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.3 | INL_Fire Water Pump Shelter - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 51165 | 51165 | 51165 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.4 | INL_Fire Water Pump Shelter - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 321762 | 321762 | 321762 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.5 | INL_Fire Water Pump Shelter - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28783 | 28783 | 28783 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.1.6 | INL_Fire Water Pump Shelter - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 337968 | 337968 | 337968 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.2.1 | INL_Fire Water Pump Shelter - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1658466 | 1658466 | 995080 | 663386 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GR | Procurement - FIRE FIGHTING SYSTEM | INL.I.7.C.5.3.1 | INL_Fire Water Pump Shelter - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1339718 | 1339718 | 1205746 | 133972 | 1 | 3500235911 | 16505045
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.1.1 | INL_Laboratory - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1723718 | 1723718 | 1723718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.1.2 | INL_Laboratory - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2879392 | 2879392 | 2879392 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.1.3 | INL_Laboratory - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 380103 | 380103 | 380103 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.1.4 | INL_Laboratory - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 266352 | 266352 | 266352 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.2.1 | INL_Laboratory - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 664792 | 611609 | 398875 | 212734 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.3.1 | INL_Laboratory - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1359482 | 1359482 | 1223534 | 135948 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.4.1 | INL_Laboratory - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 293883 | 176330 | 176330 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.4.2 | INL_Laboratory - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2385072 | 1431043 | 1431043 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.4.3 | INL_Laboratory - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 287114 | 172268 | 172268 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.4.4 | INL_Laboratory - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 147483 | 88490 | 88490 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.5.1 | INL_Laboratory - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 1333891 | 1227180 | 800335 | 426845 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.6.1 | INL_Laboratory - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 215236 | 129142 | 129142 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.6.2 | INL_Laboratory - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 322848 | 193709 | 193709 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.A.6.3 | INL_Laboratory - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 256534 | 153920 | 153920 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.1.1 | INL_Security Guardhouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 753196 | 753196 | 753196 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.1.2 | INL_Security Guardhouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1258179 | 1258179 | 1258179 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.1.3 | INL_Security Guardhouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 166090 | 166090 | 166090 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.1.4 | INL_Security Guardhouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 116385 | 116385 | 116385 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.2.1 | INL_Security Guardhouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 290487 | 290487 | 261438 | 29049 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.3.1 | INL_Security Guardhouse - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 594039 | 594039 | 534635 | 59404 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.4.1 | INL_Security Guardhouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 128415 | 128415 | 115574 | 12841 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.4.2 | INL_Security Guardhouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1042181 | 625309 | 625309 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.4.3 | INL_Security Guardhouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 125457 | 75274 | 75274 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.4.4 | INL_Security Guardhouse - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 64444 | 38666 | 38666 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.5.1 | INL_Security Guardhouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1165714 | 1165714 | 1165714 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.6.1 | INL_Security Guardhouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 188099 | 188099 | 112859 | 75240 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.6.2 | INL_Security Guardhouse - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 141072 | 141072 | 84643 | 56429 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.I.8.B.6.3 | INL_Security Guardhouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 224190 | 224190 | 201771 | 22419 | 1 | 3500235911 | 4524260
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.1 | INL_Workshop - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3345201 | 3345201 | 3345201 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.2 | INL_Workshop - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5588006 | 5588006 | 5588006 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.3 | INL_Workshop - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 445197 | 445197 | 445197 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.4 | INL_Workshop - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 950219 | 950219 | 950219 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.5 | INL_Workshop - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24747 | 24747 | 22272 | 2475 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.1.6 | INL_Workshop - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 290572 | 290572 | 290572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.2.1 | INL_Workshop - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 288474 | 265396 | 225010 | 40386 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.2.2 | INL_Workshop - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2135942 | 2135942 | 1281565 | 854377 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.3.1 | INL_Workshop - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2632774 | 2632774 | 2369497 | 263277 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.4.1 | INL_Workshop - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19437 | 19437 | 11662 | 7775 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.4.2 | INL_Workshop - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 115184 | 69110 | 69110 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.4.3 | INL_Workshop - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2468226 | 1480936 | 1480936 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.4.4 | INL_Workshop - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1938033 | 1162820 | 1162820 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.5.1 | INL_Workshop - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 2025859 | 1863790 | 1215515 | 648275 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.6.1 | INL_Workshop - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 408610 | 245166 | 245166 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.6.2 | INL_Workshop - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 653782 | 392269 | 392269 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.C.6.3 | INL_Workshop - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 779225 | 467535 | 467535 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.1 | INL_Warehouse - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3345201 | 3345201 | 3345201 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.2 | INL_Warehouse - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5588006 | 5588006 | 5588006 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.3 | INL_Warehouse - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 445197 | 445197 | 445197 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.4 | INL_Warehouse - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 950219 | 950219 | 950219 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.5 | INL_Warehouse - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 24747 | 24747 | 22272 | 2475 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.1.6 | INL_Warehouse - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 290572 | 290572 | 290572 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.2.1 | INL_Warehouse - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 288474 | 265396 | 225010 | 40386 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.2.2 | INL_Warehouse - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2135942 | 2135942 | 1281565 | 854377 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.3.1 | INL_Warehouse - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2632774 | 2632774 | 2369497 | 263277 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.4.1 | INL_Warehouse - Finishing - Concrete for Fireproofing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19437 | 19437 | 11662 | 7775 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.4.2 | INL_Warehouse - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 115184 | 69110 | 69110 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.4.3 | INL_Warehouse - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2468226 | 1480936 | 1480936 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.4.4 | INL_Warehouse - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1938033 | 1162820 | 1162820 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.5.1 | INL_Warehouse - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 2025859 | 1863790 | 1215515 | 648275 | 1 | 3500235911 | 78102414
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.6.1 | INL_Warehouse - Doors & Windows - Double Door (1800mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 408610 | 245166 | 245166 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.6.2 | INL_Warehouse - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 653782 | 392269 | 392269 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JA | Procurement - LABORATORY, WORKSHOP & WAREHOUSE FACILITIES | INL.I.8.D.6.3 | INL_Warehouse - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 779225 | 467535 | 467535 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.1 | INL_Carpark - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3117365 | 3117365 | 2805629 | 311736 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.2 | INL_Carpark - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5207416 | 5207416 | 4686674 | 520742 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.3 | INL_Carpark - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 564867 | 564867 | 508380 | 56487 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.4 | INL_Carpark - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 630059 | 630059 | 567053 | 63006 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.5 | INL_Carpark - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 40460 | 40460 | 36414 | 4046 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.1.6 | INL_Carpark - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 475081 | 475081 | 427573 | 47508 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.2.1 | INL_Carpark - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4011352 | 4011352 | 2406811 | 1604541 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.E.3.1 | INL_Carpark - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4035515 | 4035515 | 3631964 | 403551 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.1.1 | INL_Mosque - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10050930 | 10050930 | 10050930 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.1.2 | INL_Mosque - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9594070 | 9594070 | 9594070 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.1.3 | INL_Mosque - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1192489 | 1192489 | 1192489 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.1.4 | INL_Mosque - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3661758 | 3661758 | 3661758 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.2.1 | INL_Mosque - Substructure - Buiding Wall | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3895117 | 3895117 | 3505605 | 389512 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.3.1 | INL_Mosque - Structural Framing - Light Steel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13976742 | 13976742 | 12579068 | 1397674 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.4.1 | INL_Mosque - Finishing - Building Painting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.92 | 2041291 | 1877988 | 1653446 | 224542 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.4.2 | INL_Mosque - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6665442 | 6665442 | 5798935 | 866507 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.4.3 | INL_Mosque - Finishing - Floor Tile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 4906552 | 4710290 | 4268700 | 441590 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.4.4 | INL_Mosque - Finishing - Ceiling | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 2520370 | 2419555 | 2192722 | 226833 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.5.1 | INL_Mosque - Plumbing & Sanitary - Sanitary Plumbing ( include fitting and acc) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4103123 | 4103123 | 4103123 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.6.1 | INL_Mosque - Doors & Windows - Single Door (1200mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1986230 | 1986230 | 1191738 | 794492 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.6.2 | INL_Mosque - Doors & Windows - Single Door (900mm x 2100mm) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 993100 | 993100 | 595860 | 397240 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.F.6.3 | INL_Mosque - Doors & Windows - Windows | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3945557 | 3945557 | 3195901 | 749656 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.1 | INL_Storage - Foundation - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1697992 | 1697992 | 1697992 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.2 | INL_Storage - Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2836419 | 2836419 | 2836419 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.3 | INL_Storage - Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 286789 | 286789 | 286789 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.4 | INL_Storage - Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 400861 | 400861 | 400861 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.5 | INL_Storage - Foundation - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30993 | 30993 | 27894 | 3099 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.1.6 | INL_Storage - Foundation - Anchor Bolt M24 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 363922 | 363922 | 363922 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.2.1 | INL_Storage - Substructure - Roofing 0.55 mm thk. | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2089487 | 1253692 | 1253692 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.3.1 | INL_Storage - Structural Framing - Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1854770 | 1854770 | 1669293 | 185477 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.8.G.4.1 | INL_Storage - Finishing - Floor Finish Epoxy Coating | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1288035 | 772821 | 772821 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.9.A.1.1 | INL_Pit & Pond - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 522172 | 522172 | 480398 | 41774 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.9.A.1.2 | INL_Pit & Pond - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 623046 | 623046 | 573202 | 49844 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.9.A.1.3 | INL_Pit & Pond - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22049 | 22049 | 20285 | 1764 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.HQ | Procurement - GENERAL SERVICES FACILITIES | INL.I.9.A.1.4 | INL_Pit & Pond - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 175828 | 175828 | 161762 | 14066 | 1 | 3500235911 | 155821707
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | INL.I.9.B.1.1 | INL_Lighting Pole Foundation - Concrete for Non Structural | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 104264 | 104264 | 82890 | 21374 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | INL.I.9.B.1.2 | INL_Lighting Pole Foundation - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 152052 | 152052 | 120881 | 31171 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | INL.I.9.B.1.3 | INL_Lighting Pole Foundation - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10778 | 10778 | 8569 | 2209 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | INL.I.9.B.1.4 | INL_Lighting Pole Foundation - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 68806 | 68806 | 54701 | 14105 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.JC | Procurement - LIGHTING SYSTEM | INL.I.9.B.1.5 | INL_Lighting Pole Foundation - Anchor Bolt M12 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55875 | 55875 | 44421 | 11454 | 1 | 3500235911 | 1422815
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.1 | INL_Lightning Protection - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 30971 | 30971 | 18583 | 12388 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.2 | INL_Lightning Protection - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 36954 | 36954 | 22172 | 14782 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.3 | INL_Lightning Protection - Anchor Bolt M16 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10629 | 10629 | 6377 | 4252 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.4 | INL_Lightning Protection - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1600 | 1600 | 960 | 640 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.5 | INL_Lightning Protection - Non-Shrink Grout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 308 | 308 | 185 | 123 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.I.9.C.1.6 | INL_Lightning Protection - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4710 | 4710 | 2826 | 1884 | 1 | 3500235911 | 603556
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | INL.I.9.D.1.1 | INL_Pipe Sleeper - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1122710 | 1122710 | 1032893 | 89817 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | INL.I.9.D.1.2 | INL_Pipe Sleeper - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1339597 | 1339597 | 1232429 | 107168 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | INL.I.9.D.1.3 | INL_Pipe Sleeper - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 83507 | 83507 | 76826 | 6681 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | INL.I.9.D.1.4 | INL_Pipe Sleeper - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 317977 | 317977 | 292539 | 25438 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1C.DO | Procurement - CIVIL WORKS FOR OUTDOOR PIPING SYSTEM | INL.I.9.D.1.5 | INL_Pipe Sleeper - Steel Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 64956 | 64956 | 59760 | 5196 | 1 | 3500235911 | 4150784
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | INL.I.9.E.1.1 | INL_Road & Paving - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 12067861 | 11271382 | 8297861 | 2973521 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | INL.I.9.E.1.2 | INL_Road & Paving - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 344396 | 321666 | 236807 | 84859 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | INL.I.9.E.1.3 | INL_Road & Paving - Kansteen, L = 60 cm, W = 45 cm, H = 24 cm | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 2753716 | 2571971 | 1893455 | 678516 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.AN | Procurement - ACCESS ROAD & ROAD WORKS | INL.I.9.E.1.4 | INL_Road & Paving - Gravel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.934 | 376458 | 351612 | 258853 | 92759 | 1 | 3500235911 | 67845002
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.1.1 | INL_Open Ditch for Storm Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 7030408 | 4218245 | 4218245 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.1.2 | INL_Open Ditch for Storm Water System - Heavy Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1418024 | 850814 | 850814 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.1.3 | INL_Open Ditch for Storm Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8502 | 6314393 | 5368497 | 4905652 | 462845 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.2.1 | INL_Open Ditch & RC Pipe for Oily Water System - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 318478 | 191087 | 191087 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.2.2 | INL_Open Ditch & RC Pipe for Oily Water System - U-Ditch U400x600 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.7158 | 247429 | 177110 | 172409 | 4701 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.3.1 | INL_Manhole for Storm Water System - Concrete for general foundation & structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 52831 | 52831 | 31699 | 21132 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.3.2 | INL_Manhole for Storm Water System - Reinforcement Steel Bar | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63037 | 63037 | 37822 | 25215 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.3.3 | INL_Manhole for Storm Water System - Lean Concrete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3387 | 3387 | 2032 | 1355 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.3.4 | INL_Manhole for Storm Water System - Concrete Formwork | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20261 | 20261 | 12157 | 8104 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.4.1 | INL_Culvert for Storm Water System - RC Pipe 500 @2.4m | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 67419 | 67419 | 40451 | 26968 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.5.1 | INL_Around Building & Shelter - U-Ditch U300x400 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8197 | 1552942 | 1272947 | 1136443 | 136504 | 1 | 3500235911 | 12167571
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0C.GG | Procurement - DRAINAGE TUNNEL AND CHANNELS | INL.I.9.F.5.2 | INL_Around Building & Shelter - Light Duty Steel Grating, complete with framing and accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 2583496 | 1550098 | 1550098 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | INL.II.1.1.1 | INL_Lubrication And Hydraulic System - Urea Tank For SCR Unit #1 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9912 | 74468454 | 73813132 | 65770539 | 8042593 | 1 | 3500235911 | 91652683
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | INL.II.1.2.1 | INL_Charge Air System/Air Intake System - Intake Air Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5642417 | 5642417 | 5010466 | 631951 | 1 | 3500235911 | 6306749
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | INL.II.1.3.1 | INL_Exhaust System - Exhaust Gas Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.998 | 15046447 | 15016354 | 12097343 | 2919011 | 1 | 3500235911 | 57286301
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | INL.II.1.3.2 | INL_Exhaust System - Exhaust Gas Stack | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 28212087 | 28212087 | 25390878 | 2821209 | 1 | 3500235911 | 57286301
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | INL.II.1.4 | INL_Ventilation And Air Conditioning System - Air Conditioning for Central Control Room | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9968 | 57283426 | 57100119 | 48507605 | 8592514 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | INL.II.1.5.1 | INL_All Necessary Pipe Works, Flange And Coupling - Piping specialty items | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9944 | 9064473 | 9013712 | 7872495 | 1141217 | 1 | 3500235911 | 91652683
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | INL.II.2.1.1 | INL_Fuel Oil Supply System - Daily storage tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 467785199 | 467785199 | 452816073 | 14969126 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | INL.II.2.1.2 | INL_Fuel Oil Supply System - Fuel Oil Pilot and Clean Leakage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 35083890 | 35083890 | 31575501 | 3508389 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | INL.II.2.1.3 | INL_Fuel Oil Supply System - Fuel Oil Dirty oil Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6409557 | 6409557 | 5768601 | 640956 | 1 | 3500235911 | 172367757
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.1.1 | INL_Pumps - Treated Water (Fresh Water) Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9525751 | 9525751 | 8573176 | 952575 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.1.2 | INL_Pumps - Service Water supply Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9525751 | 9525751 | 8573176 | 952575 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.2.1 | INL_Water Treatment Unit - Sand Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3432965 | 3432965 | 3089669 | 343296 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.2.2 | INL_Water Treatment Unit - Ultra Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4872595 | 4872595 | 4385336 | 487259 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.2.3 | INL_Water Treatment Unit - Carbon Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3432965 | 3432965 | 3089669 | 343296 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.2.4 | INL_Water Treatment Unit - Reverse Osmosis Unit, | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5675466 | 5675466 | 5107919 | 567547 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.2.5 | INL_Water Treatment Unit - Chemical Injection / Dosing Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12167757 | 12167757 | 10950981 | 1216776 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.3.1 | INL_Combined Service Water Tank And Fire Water Tank - Combined service water tank and fire water tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 343700556 | 343700556 | 309330500 | 34370056 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.MO | Procurement - WATER TREATMENT PLANT SYSTEM | INL.II.3.4.1 | INL_Fresh Water Tank - Fresh water tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 954724 | 954724 | 859252 | 95472 | 1 | 3500235911 | 215957961
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.1 | INL_Waste Water Collection & Treatment System - Sanitary Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 853660 | 512196 | 512196 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.2 | INL_Waste Water Collection & Treatment System - Oily Water Pit - Power generation Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 311914 | 187148 | 187148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.3 | INL_Waste Water Collection & Treatment System - Oily Water Pit - Transformer Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 311914 | 187148 | 187148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.4 | INL_Waste Water Collection & Treatment System - Oily Water Pit - Fuel Station Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 311914 | 187148 | 187148 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.5 | INL_Waste Water Collection & Treatment System - Skimming Pond | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5068603 | 5068603 | 5068603 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | INL.II.3A.1.6 | INL_Waste Water Collection & Treatment System - Nutralization Pond | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 779785 | 779785 | 779785 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | INL.II.4.1.1 | INL_Workshop And Machinery Equipment - Forklift | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 4534938 | 4353540 | 2720963 | 1632577 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | INL.II.4.1.2 | INL_Workshop And Machinery Equipment - Crane for Power Generation Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 210361350 | 210361350 | 189325215 | 21036135 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | INL.II.4.1.3 | INL_Workshop And Machinery Equipment - Crane Workshop Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 119326658 | 119326658 | 107393992 | 11932666 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | INL.II.4.1.4 | INL_Workshop And Machinery Equipment - Crane Warehouse Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 119326658 | 119326658 | 107393992 | 11932666 | 1 | 3500235911 | 514400938
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | INL.II.5.1.1 | INL_Air Conditioning And Ventilation - Administration Building VAC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6893106 | 6893106 | 5852247 | 1040859 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | INL.II.5.1.2 | INL_Air Conditioning And Ventilation - Ventilation System of Ware House | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 167444 | 113862 | 105490 | 8372 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.IC | Procurement - HVAC SYSTEM | INL.II.5.1.3 | INL_Air Conditioning And Ventilation - Ventilation System of Work Shop and Air Condition System for workshop office & wa | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.68 | 1925604 | 1309411 | 1213131 | 96280 | 1 | 3500235911 | 11431986
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | INL.II.5.1.4 | INL_Air Conditioning And Ventilation - VAC for Switchyard Control Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 55954157 | 55954157 | 47505079 | 8449078 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.IC | Procurement - HVAC SYSTEM | INL.II.5.1.5 | INL_Air Conditioning And Ventilation - Ventilation For Power House | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 143387759 | 143387759 | 121736207 | 21651552 | 1 | 3500235911 | 386150232
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | INL.III.1.1.1 | INL_Generator And Main Output System - Busduct 11 KV | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 159676703 | 156483169 | 129338129 | 27145040 | 1 | 3500235911 | 2693824859
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | INL.III.1.1.2 | INL_Generator And Main Output System - Busduct 0.4 KV | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 644114555 | 631232264 | 483085916 | 148146348 | 1 | 3500235911 | 2693824859
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.JQ | Procurement - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | INL.III.2.1.1 | INL_Medium Voltage Switchgears (Bus Collector) - MV Switchgears 11kV, 1250A, 25 kA IP 41,3ph, 4W Dead Front | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 183970387 | 183970387 | 165573348 | 18397039 | 1 | 3500235911 | 406573408
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.JQ | Procurement - MV SWITCHGEAR AND MV POWER CABLES SYSTEM | INL.III.2.1.2 | INL_Medium Voltage Switchgears (Bus Collector) - MV Switchgears 11kV, 1000A, 25 kA IP 41,3ph, 4W Dead Front | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 138139808 | 138139808 | 124325827 | 13813981 | 1 | 3500235911 | 406573408
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.JC | Procurement - LIGHTING SYSTEM | INL.III.2.10.1 | INL_Lighting And Small Power Installation - Lighting Poles | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 22989162 | 22989162 | 17586709 | 5402453 | 1 | 3500235911 | 219189276
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.JC | Procurement - LIGHTING SYSTEM | INL.III.2.10.2 | INL_Lighting And Small Power Installation - Lighting Fixture & Power Devices | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41481907 | 41481907 | 32621372 | 8860535 | 1 | 3500235911 | 219189276
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | INL.III.2.11.1 | INL_Communication Systems - Horn Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3646322 | 3646322 | 2187793 | 1458529 | 1 | 3500235911 | 42587031
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | INL.III.2.11.2 | INL_Communication Systems - Ceiling Speaker | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3281690 | 3281690 | 1969014 | 1312676 | 1 | 3500235911 | 42587031
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | INL.III.2.11.3 | INL_Communication Systems - Telephone Analog | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 6381063 | 3828638 | 3828638 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.LQ | Procurement - TELECOMMUNICATION SYSTEM | INL.III.2.11.4 | INL_Communication Systems - Hotline Telephone | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1025528 | 615317 | 615317 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.III.2.12.1 | INL_Closed Circuit TV System Equipment - CCTV outdoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2949385 | 2949385 | 2167798 | 781587 | 1 | 3500235911 | 13370951
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.KW | Procurement - SECURITY & SURVEILLANCE SYSTEM | INL.III.2.12.2 | INL_Closed Circuit TV System Equipment - CCTV indoor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 884816 | 884816 | 796334 | 88482 | 1 | 3500235911 | 13370951
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.FN | Procurement - CONTROL & MONITORING SYSTEM | INL.III.2.13.1 | INL_Power Plant Metering And Protection Panels Complete | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5603832 | 5603832 | 4757653 | 846179 | 1 | 3500235911 | 13003817
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.2.2.1 | INL_Low Voltage Switchgears - LV Normal Switchboard | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 258966037 | 252232920 | 208985592 | 43247328 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.2.2.2 | INL_Low Voltage Switchgears - LV Essential Switchboard | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 234972472 | 228863188 | 189622785 | 39240403 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.2.3.1 | INL_Low Voltage Motor Control Centers - LV Switchboard for EDG | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.974 | 229740304 | 223767056 | 185400425 | 38366631 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | INL.III.2.4.1 | INL_Uninterruptible Ac Power Supply - UPS Inland Transporation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 38700280 | 23220168 | 23220168 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AT | Procurement - BLACK-START GENERATOR SYSTEM | INL.III.2.5.1 | INL_Black Start/Emergency Diesel Generator (EDG) - EDG Inland Transporation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 32590277 | 31286666 | 19554166 | 11732500 | 1 | 3500235911 | 11732500
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | INL.III.2.6.1 | INL_Batteries, Battery Chargers And DC Distribution Panels - Battery Inland Transporation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 79529248 | 76348078 | 47717549 | 28630529 | 1 | 3500235911 | 28630529
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.1.1 | INL_Power & Control Cables - 11 kV Medium Voltage Power Cable (8.7/15 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 66541319 | 65569816 | 55628543 | 9941273 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.1.2 | INL_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - INDOOR LIGHTING | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 1459672 | 1438361 | 1220286 | 218075 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.1.3 | INL_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - OUTDOOR LIGHTING CABLE | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 5286335 | 5209155 | 4419376 | 789779 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.1.4 | INL_Power & Control Cables - 600 V Low Voltage Power Cable (0.6/1 kV) - POWER & CONTROL CABLE | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 162861605 | 160483826 | 136152302 | 24331524 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.1.5 | INL_Power & Control Cables - Control Cable (0.6/1 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 106107571 | 104558400 | 88705929 | 15852471 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.1 | INL_Cable Accessories, Support & Bulk Material - Electrical Bulk Materials | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 5841920 | 5756628 | 4883845 | 872783 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.2 | INL_Cable Accessories, Support & Bulk Material - Cable Glands | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 44431891 | 43783185 | 37145061 | 6638124 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.3 | INL_Cable Accessories, Support & Bulk Material - Cable Accessories | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 4897979 | 4826469 | 4094710 | 731759 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.4 | INL_Cable Accessories, Support & Bulk Material - Miscellaneous Support | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 5993735 | 5906226 | 5010762 | 895464 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.5 | INL_Cable Accessories, Support & Bulk Material - Cable Ladder & Tray System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 57368297 | 56530720 | 47959896 | 8570824 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.6 | INL_Cable Accessories, Support & Bulk Material - Local Control Station | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 14164196 | 13957399 | 11841268 | 2116131 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BB | Procurement - CABLE & ACCESSORIES SYSTEM | INL.III.2.7.2.7 | INL_Cable Accessories, Support & Bulk Material - Junction Box & Condulet | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9854 | 12436855 | 12255277 | 10397211 | 1858066 | 1 | 3500235911 | 1352643914
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.III.2.8.1 | INL_Grounding And Lightning Protection System - Earthing Bus Bar,Min 10-Holes | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 379940 | 379940 | 311475 | 68465 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.III.2.8.2 | INL_Grounding And Lightning Protection System - Grounding Rod | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9825983 | 9825983 | 8055341 | 1770642 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.III.2.8.3 | INL_Grounding And Lightning Protection System - Lightning Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1945650 | 1945650 | 1595044 | 350606 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.III.2.8.4 | INL_Grounding And Lightning Protection System - Grounding Cables | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 12726268 | 12726268 | 10432995 | 2293273 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.GH | Procurement - EARTHING & LIGHTNING SYSTEM | INL.III.2.8.5 | INL_Grounding And Lightning Protection System - Other Earthing Material | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 10191322 | 10191322 | 8354846 | 1836476 | 1 | 3500235911 | 97115594
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0E.BI | Procurement - CATHODIC PROTECTION SYSTEM | INL.III.2.9.1 | INL_Cathodic Protection System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 8767291 | 8767291 | 6904242 | 1863049 | 1 | 3500235911 | 28630776
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.III.3.1.1 | INL_Generator Transformer - 25000 kVA, 11/70 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 227524009 | 227524009 | 212052376 | 15471633 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.III.3.1.2 | INL_Generator Transformer - 15000 kVA, 11/70 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 213122582 | 213122582 | 198630246 | 14492336 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KG | Procurement - POWER TRANSFORMER & AUXILIARIES SYSTEM | INL.III.3.2.1 | INL_Unit Auxiliary Transformer - 2500 kVA, 11/0.4 kV Power Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 86122051 | 86122051 | 73117621 | 13004430 | 1 | 3500235911 | 660325305
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.4.1.1 | INL_Complete 20/70/150 KV Substation Equipment - Current Transformer for 70 kV, Class 0.2, 0.5, 5PX20, 5P20, Outdoor, 25 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 18571142 | 18571142 | 16119751 | 2451391 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.4.1.2 | INL_Complete 20/70/150 KV Substation Equipment - Current Transformer for 70 kV, Class 0.2, 0.5, 5PX20, 5P20, Outdoor, 20 | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 25413142 | 25413142 | 22058607 | 3354535 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.4.1.3 | INL_Complete 20/70/150 KV Substation Equipment - Post Insulator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 131263764 | 131263764 | 113936947 | 17326817 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.FM | Procurement - CONTROL & MONITORING EQUIPMENT AND PROTECTION SYSTEM | INL.III.4.1.4 | INL_Complete 20/70/150 KV Substation Equipment - 70 KV Metering Panel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 100179093 | 100179093 | 86955453 | 13223640 | 1 | 3500235911 | 1338362611
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | INL.IV.1.1.1 | INL_Distributed Digital Control System And PLC Control System - PLC Control System Inland Transportation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 87419780 | 87419780 | 78677802 | 8741978 | 1 | 3500235911 | 18492646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | INL.IV.2.1.1 | INL_Power Plant Operation Control Desks - Power plant operation control desks Inland Transportation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 97506678 | 97506678 | 87756010 | 9750668 | 1 | 3500235911 | 18492646
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | INL.IV.3.1.1 | INL_Field Instruments Inland Transportation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9195 | 392195015 | 360623316 | 235317009 | 125306307 | 1 | 3500235911 | 137296845
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | INL.IV.4.1.1 | INL_Instrument Cable, Cable Tray, Junction Box, Gland And Accessories Inland Transportation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9976 | 58277189 | 58137324 | 47140418 | 10996906 | 1 | 3500235911 | 137296845
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | INL.IV.5.1.1 | INL_Instrument Installation Bulk Material And Accessories Inland Transportation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6852632 | 6852632 | 5859000 | 993632 | 1 | 3500235911 | 137296845
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.1 | MFI_Gas Engine & Auxiliary - Engine 7L 51/60DF | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 559273.6 | 559273.6 | 503346.24 | 55927.36 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.10 | MFI_Gas Engine & Auxiliary - Adapter for Exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6391.7 | 6391.7 | 4602.02 | 1789.68 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.11 | MFI_Gas Engine & Auxiliary - Expansion joint for exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 23968.87 | 23968.87 | 17257.59 | 6711.28 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.2 | MFI_Gas Engine & Auxiliary - Oil mist eliminator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7989.62 | 7989.62 | 7190.66 | 798.96 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.3 | MFI_Gas Engine & Auxiliary - Gas Control Line | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19974.06 | 19974.06 | 17976.65 | 1997.41 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.4 | MFI_Gas Engine & Auxiliary - Ventilation system for exhaust gas duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9997 | 6391.7 | 6389.78 | 5629.81 | 759.97 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.5 | MFI_Gas Engine & Auxiliary - Flexible Coupling | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 11185.47 | 9395.79 | 7382.41 | 2013.38 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.6 | MFI_Gas Engine & Auxiliary - Flywheel cover | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 14381.32 | 12080.31 | 9491.67 | 2588.64 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.7 | MFI_Gas Engine & Auxiliary - Foundation Frame seating | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.99 | 8788.59 | 8700.7 | 7744.51 | 956.19 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.8 | MFI_Gas Engine & Auxiliary - Flexible pipe connections for the Engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5419.28 | 5419.28 | 4227.04 | 1192.24 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.1.9 | MFI_Gas Engine & Auxiliary - Rubber Expansion joint for intake air duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 15979.25 | 15979.25 | 11505.06 | 4474.19 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.1 | MFI_Special Tools For Engine - Standard and special tools for the engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6031.31 | 6031.31 | 6031.31 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.2 | MFI_Special Tools For Engine - Crank web deflection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 19.98 | 19.98 | 19.98 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.3 | MFI_Special Tools For Engine - Electric valve cone grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 671.5 | 671.5 | 671.5 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.4 | MFI_Special Tools For Engine - Electric valve seat grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 823.23 | 823.23 | 823.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.5 | MFI_Special Tools For Engine - Tool for ACC (adaptive combustion control) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 183.69 | 183.69 | 183.69 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.6 | MFI_Special Tools For Engine - Assembly and reversing device for cylinder heads | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 294.87 | 294.87 | 294.87 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.10.7 | MFI_Special Tools For Engine - Tools for Turbocharger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 5.75 | 5.75 | 5.75 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.1 | MFI_Electrical Generator - Control Panel | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 13539.05 | 13539.05 | 12185.15 | 1353.9 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.2 | MFI_Electrical Generator - "CoCoS-EDS" engine diagnosis system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 6092.57 | 5848.87 | 3655.54 | 2193.33 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.3 | MFI_Electrical Generator - Connecting cables; EDS-Databox/CoCoS-EDS-Hardware | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 1353.9 | 1299.74 | 812.34 | 487.4 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.4 | MFI_Electrical Generator - Remote access device | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 9026.03 | 9026.03 | 7762.39 | 1263.64 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.5 | MFI_Electrical Generator - Three phase synchronous alternator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 45130.17 | 45130.17 | 40617.15 | 4513.02 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.6 | MFI_Electrical Generator - Automatic voltage regulator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6092.57 | 6092.57 | 5239.61 | 852.96 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.KE | Procurement - POWER GENERATOR, EXCITATION & AUXILIARIES SYSTEM | MFI.II.1.2.7 | MFI_Electrical Generator - Grouting material for alternator seating | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.84 | 2078.24 | 1745.72 | 1496.33 | 249.39 | 1 | 3500235947 | 494565.64
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.1 | MFI_Cooling System - LT/HT Cooling Water Radiator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 7573.87 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.10 | MFI_Cooling System - HT Cooling Water Temperature Control Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.11 | MFI_Cooling System - LT Cooling Water Temperature Control Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.2 | MFI_Cooling System - HT Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.3 | MFI_Cooling System - LT Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.4 | MFI_Cooling System - Nozzle Cooling Water Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.5 | MFI_Cooling System - Nozzle Cooling Water Cooler | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.6 | MFI_Cooling System - Nozzle Cooling Water Expansion Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.7 | MFI_Cooling System - Jacket Water Preheating Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.8 | MFI_Cooling System - Jacket Water Preheater | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.FR | Procurement - COOLING WATER SYSTEM | MFI.II.1.3.9 | MFI_Cooling System - Cooling Water Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7573.87 | 7573.87 | 6816.48 | 757.39 | 1 | 3500235947 | 98483
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.4.1 | MFI_Charge Air System/Air Intake System - Intake Air Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41656.27 | 41656.27 | 37490.64 | 4165.63 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.4.2 | MFI_Charge Air System/Air Intake System - Intake Air Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 41656.27 | 41656.27 | 37490.64 | 4165.63 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | MFI.II.1.5.1 | MFI_Exhaust System - Exhaust Gas Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20828.14 | 20828.14 | 18745.33 | 2082.81 | 1 | 3500235947 | 229164.38
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.GP | Procurement - EXHAUST SYSTEM | MFI.II.1.5.2 | MFI_Exhaust System - Rupture Disc | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 20828.14 | 20828.14 | 13746.57 | 7081.57 | 1 | 3500235947 | 229164.38
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.1 | MFI_Lubrication System - LO Unloading Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3786.93 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.10 | MFI_Lubrication System - LO Purifier Heater | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.11 | MFI_Lubrication System - Used LO Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.2 | MFI_Lubrication System - LO Receiving Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3786.93 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.3 | MFI_Lubrication System - LO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3786.93 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.4 | MFI_Lubrication System - LO Filter for LO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.5 | MFI_Lubrication System - Pre. Lube. Oil Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.6 | MFI_Lubrication System - LO Cooler | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.7 | MFI_Lubrication System - LO Auto. Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.8 | MFI_Lubrication System - LO Purifier | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.1.6.9 | MFI_Lubrication System - LO Purifier Feed Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3786.93 | 3786.93 | 3408.24 | 378.69 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.1 | MFI_Fuel Oil System - FO Purifier | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.10 | MFI_Fuel Oil System - Pilot Oil Flow Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.11 | MFI_Fuel Oil System - Pilot Oil Safety Regulating Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.12 | MFI_Fuel Oil System - Clean Oil Drain Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.13 | MFI_Fuel Oil System - Clean Oil Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.14 | MFI_Fuel Oil System - Dirty Oil Drain Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.15 | MFI_Fuel Oil System - Dirty Oil Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.2 | MFI_Fuel Oil System - FO Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2777.08 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.3 | MFI_Fuel Oil System - FO Supply Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2777.08 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.4 | MFI_Fuel Oil System - FO Flow meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 1666.25 | 1110.83 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.5 | MFI_Fuel Oil System - FO Duplex Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.6 | MFI_Fuel Oil System - FO Pressure Safety Regulating Valve for FO | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.7 | MFI_Fuel Oil System - Pilot Oil Supply Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2777.08 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.8 | MFI_Fuel Oil System - Pilot Oil Automatic Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.JF | Procurement - LIQUID FUEL HANDLING SYSTEM | MFI.II.1.7.9 | MFI_Fuel Oil System - Pilot Oil Duplex Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2777.08 | 2777.08 | 2499.37 | 277.71 | 1 | 3500235947 | 54165.6
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.8.1 | MFI_Compressed Air & Starting System - Starting Air Compressorr | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16059.91 | 16059.91 | 14453.92 | 1605.99 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.8.2 | MFI_Compressed Air & Starting System - Control Air Dryer and Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16059.91 | 16059.91 | 14453.92 | 1605.99 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.8.3 | MFI_Compressed Air & Starting System - Starting Air Reservoir | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16059.91 | 16059.91 | 14453.92 | 1605.99 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.8.4 | MFI_Compressed Air & Starting System - Control Air Compressor | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16059.91 | 16059.91 | 14453.92 | 1605.99 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.KZ | Procurement - SERVICE & CONTROL AIR SYSTEM | MFI.II.1.8.5 | MFI_Compressed Air & Starting System - Control Air Reservoir | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 16059.91 | 16059.91 | 14453.92 | 1605.99 | 1 | 3500235947 | 203623.91
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.1 | MFI_Initial Spare Parts - set of spare part for turbocharger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 54.88 | 54.88 | 54.88 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.2 | MFI_Initial Spare Parts - set of engine standard spare parts | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 860.04 | 860.04 | 860.04 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.3 | MFI_Initial Spare Parts - spare parts für operating and monitoring the engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 381.89 | 381.89 | 381.89 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.4 | MFI_Initial Spare Parts - spare parts for ACC (adaptive combustion control) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 277.82 | 277.82 | 277.82 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.5 | MFI_Initial Spare Parts - spare parts for SACOS | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1012.11 | 1012.11 | 1012.11 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.6 | MFI_Initial Spare Parts - spares for oil mist detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 197.91 | 197.91 | 197.91 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.JJ | Procurement - MANDATORY SPARE PARTS & SPECIAL TOOLS SYSTEM FOR MECHANICAL | MFI.II.1.9.7 | MFI_Initial Spare Parts - spare parts for alternator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 228.35 | 228.35 | 228.35 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.2.1 | MFI_Fuel Supply System - Coalescing Filters Capacity 7500 nM3/Hr, CS, Press. 9 Bar | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7680 | 7680 | 6220.8 | 1459.2 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.2.2 | MFI_Fuel Supply System - Piping For Fuel Supply System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.81 | 11915.59 | 9651.63 | 9651.63 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1M.HH | Procurement - GAS ENGINE & AUXILIARIES SYSTEM | MFI.II.2.3 | MFI_Fuel Supply System - Valve For Supply System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11915.59 | 11915.59 | 10652.54 | 1263.05 | 1 | 3500235947 | 1045589.17
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.1 | MFI_Wastewater Collection and Treatment System - Piping for Colling Water System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8685 | 738.46 | 641.35 | 641.35 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.2 | MFI_Wastewater Collection and Treatment System - Sludge pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 222.22 | 200 | 200 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.3 | MFI_Wastewater Collection and Treatment System - Transfer pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 222.22 | 133.33 | 133.33 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.4 | MFI_Wastewater Collection and Treatment System - Air Blower | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1600 | 960 | 960 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.5 | MFI_Wastewater Collection and Treatment System - Discharge Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 222.22 | 133.33 | 133.33 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.6 | MFI_Wastewater Collection and Treatment System - Acid/caustic measuring tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 615.38 | 369.23 | 369.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.7 | MFI_Wastewater Collection and Treatment System - Oil Separator including oil skimmer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 24017.16 | 14410.3 | 14410.3 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.8 | MFI_Wastewater Collection and Treatment System - Piping For Water Treatment System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1352.32 | 1217.09 | 1217.09 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.ML | Procurement - WASTE WATER TREATMENT SYSTEM | MFI.II.3.9 | MFI_Wastewater Collection and Treatment System - Valve For Water Treatment System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 1352.32 | 1352.32 | 1014.24 | 338.08 | 1 | 3500235947 | 1764.5
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.1 | MFI_Fire Protection System - Electric motor driven fire water pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 4800 | 4800 | 2160 | 2640 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.10 | MFI_Fire Protection System - Piping For Fire Protection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.88 | 5957.8 | 5242.86 | 5242.86 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.11 | MFI_Fire Protection System - Valve For Fire Protection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.992 | 5957.8 | 5910.14 | 4289.62 | 1620.52 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.2 | MFI_Fire Protection System - Diesel driven fire water pump. | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7200 | 7200 | 3240 | 3960 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.3 | MFI_Fire Protection System - Jockey Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 2744.62 | 2744.62 | 1235.08 | 1509.54 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.4 | MFI_Fire Protection System - Fire water loop | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 4000 | 1800 | 1800 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.5 | MFI_Fire Protection System - Local fire panels and a main Fire Alarm Annunciator Panel (FAAP) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1600 | 720 | 720 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.6 | MFI_Fire Protection System - Fire alarm & detection system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.968 | 2400 | 2323.2 | 1080 | 1243.2 | 1 | 3500235947 | 57271.46
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.7 | MFI_Fire Protection System - CO2 extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 5120 | 3072 | 3072 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.8 | MFI_Fire Protection System - Dry Chemical extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1200.3 | 720.18 | 720.18 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.II.4.9 | MFI_Fire Protection System - Fire extinguisher | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 600.15 | 360.09 | 360.09 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.1 | MFI_Laboratory and Instruments - Conductivitymeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 192 | 86.4 | 86.4 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.10 | MFI_Laboratory and Instruments - Inductively Couplet Plasma Atomic Emission Spectrometry (ICP-AES) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 8000 | 3600 | 3600 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.11 | MFI_Laboratory and Instruments - Potentiometric Titrator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 960 | 432 | 432 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.12 | MFI_Laboratory and Instruments - Oxidation test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2400 | 1080 | 1080 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.13 | MFI_Laboratory and Instruments - Total base number test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 320 | 144 | 144 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.14 | MFI_Laboratory and Instruments - Hydrometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 160 | 72 | 72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.15 | MFI_Laboratory and Instruments - Viscometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 400 | 180 | 180 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.16 | MFI_Laboratory and Instruments - Pensky Marren Closed Tester | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 3200 | 1440 | 1440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.17 | MFI_Laboratory and Instruments - Tensiometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 16 | 7.2 | 7.2 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.18 | MFI_Laboratory and Instruments - Oxidation test apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2400 | 1080 | 1080 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.19 | MFI_Laboratory and Instruments - Gas Caloriemeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 8000 | 3600 | 3600 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.2 | MFI_Laboratory and Instruments - pH Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 640 | 288 | 288 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.20 | MFI_Laboratory and Instruments - Gas Chromatograph | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 11200 | 5040 | 5040 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.21 | MFI_Laboratory and Instruments - Combustion and Adsorption Apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 4000 | 1800 | 1800 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.22 | MFI_Laboratory and Instruments - Dew Point meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 480 | 216 | 216 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.23 | MFI_Laboratory and Instruments - Orsat Meter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 160 | 72 | 72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.3 | MFI_Laboratory and Instruments - Spectrofotometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 160 | 72 | 72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.4 | MFI_Laboratory and Instruments - Color Comparator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 400 | 180 | 180 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.5 | MFI_Laboratory and Instruments - Hydrometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 160 | 72 | 72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.6 | MFI_Laboratory and Instruments - Quartz Tube Combustion Apparatus | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 4000 | 1800 | 1800 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.7 | MFI_Laboratory and Instruments - Viscosimeter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 400 | 180 | 180 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.8 | MFI_Laboratory and Instruments - Pensky Marten Closed Tester | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 3200 | 1440 | 1440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.KT | Procurement - SAMPLING & LABORATORY EQUIPMENT SYSTEM | MFI.II.5.9 | MFI_Laboratory and Instruments - Tensiometer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 16 | 7.2 | 7.2 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.1 | MFI_Workshop and Machinery Equipment - Welding Machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 640 | 288 | 288 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.10 | MFI_Workshop and Machinery Equipment - Storage & Racks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2168 | 1951.2 | 1951.2 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.2 | MFI_Workshop and Machinery Equipment - Lathe | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1600 | 1440 | 1440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.3 | MFI_Workshop and Machinery Equipment - Grinder | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 640 | 288 | 288 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.4 | MFI_Workshop and Machinery Equipment - Drilling Machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 320 | 144 | 144 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.5 | MFI_Workshop and Machinery Equipment - Vises | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 160 | 96 | 96 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.6 | MFI_Workshop and Machinery Equipment - Hand Tools Set consist of 3 sets | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 240 | 216 | 216 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.7 | MFI_Workshop and Machinery Equipment - Workbench | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 256 | 153.6 | 153.6 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.8 | MFI_Workshop and Machinery Equipment - Sawing machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.6 | 1280 | 768 | 768 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA0M.FT | Procurement - CRANE, HOIST & CONVEYING SYSTEM | MFI.II.6.9 | MFI_Workshop and Machinery Equipment - Threading machine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 1600 | 1440 | 1440 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | MFI.III.1.1 | MFI_Neutral Earthing System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 2243.41 | 2019.07 | 2019.07 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | MFI.III.1.2 | MFI_Medium Voltage Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 2243.41 | 2198.54 | 1817.16 | 381.38 | 1 | 3500235947 | 79454.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.BA | Procurement - BUSBAR AND CONNECTIONS SYSTEM | MFI.III.1.3 | MFI_Low Voltage Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 18099.25 | 17737.27 | 13574.44 | 4162.83 | 1 | 3500235947 | 79454.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | MFI.III.1.4 | MFI_Uninterruptible AC power supply | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 2821.06 | 1269.48 | 1269.48 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AT | Procurement - BLACK-START GENERATOR SYSTEM | MFI.III.1.5 | MFI_Black Start/Emergency Diesel Generator (EDG) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 2375.67 | 2280.64 | 1069.05 | 1211.59 | 1 | 3500235947 | 21184.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | MFI.III.1.6 | MFI_DC System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 5797.29 | 5565.4 | 5043.64 | 521.76 | 1 | 3500235947 | 9122.84
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | MFI.III.2.1 | MFI_48 V DC System for Switchyard | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 1740.85 | 1392.68 | 1392.68 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1E.AS | Procurement - BACKUP POWER SYSTEM | MFI.III.2.2 | MFI_110 V Uninterruptible AC power supply for Switchyard | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 819.22 | 655.38 | 655.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | MFI.IV.1.1 | MFI_Control System - PLC control system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 8148.62 | 7822.68 | 6539.27 | 1283.41 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | MFI.IV.1.2 | MFI_Control System - Power plant operation control desks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.7 | 4203.89 | 2942.72 | 2665.69 | 277.03 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | MFI.IV.1.3 | MFI_Control System - Diagnostic Software License | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.98 | 4887.97 | 4790.21 | 4252.53 | 537.68 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.FN | Procurement - CONTROL & MONITORING SYSTEM | MFI.IV.1.4 | MFI_Control System - Supervisory and Plant management system License | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 3910.37 | 3753.96 | 3402.02 | 351.94 | 1 | 3500235947 | 43798.99
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.2.1 | MFI_Instrument Valve - Shutdown valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 586.56 | 263.95 | 263.95 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.2.2 | MFI_Instrument Valve - Pressure Regulating Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 586.56 | 563.1 | 263.95 | 299.15 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.2.3 | MFI_Instrument Valve - Pressure Safety Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 586.56 | 563.1 | 263.95 | 299.15 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.2.4 | MFI_Instrument Valve - Deluge Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 586.56 | 263.95 | 263.95 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.1 | MFI_Field Instruments - Pressure Transmitters | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.10 | MFI_Field Instruments - Sight Flow Glass | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.11 | MFI_Field Instruments - Orifice Plate | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.2 | MFI_Field Instruments - Differential Pressure Transmitters | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.3 | MFI_Field Instruments - Temperature Transmitters and Well | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.4 | MFI_Field Instruments - Level Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.5 | MFI_Field Instruments - Pressure Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.6 | MFI_Field Instruments - Pressure Switch | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.7 | MFI_Field Instruments - Temperature Gauge and Well | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.8 | MFI_Field Instruments - Level Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.3.9 | MFI_Field Instruments - Flow Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8396 | 1559.4 | 1309.27 | 701.73 | 607.54 | 1 | 3500235947 | 198467.53
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.4 | MFI_Analyzer Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 1905.94 | 857.67 | 857.67 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.IV.5.1 | MFI_Fire and Gas Detector - Smoke Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 1905.94 | 1829.7 | 857.67 | 972.03 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.IV.5.2 | MFI_Fire and Gas Detector - Manual Call Point | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.868 | 1905.94 | 1654.36 | 857.67 | 796.69 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.IV.5.3 | MFI_Fire and Gas Detector - Combustible Gas Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.952 | 1905.94 | 1814.45 | 857.67 | 956.78 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.IV.5.4 | MFI_Fire and Gas Detector - Heat Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 1905.94 | 1829.7 | 857.67 | 972.03 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.GR | Procurement - FIRE FIGHTING SYSTEM | MFI.IV.5.5 | MFI_Fire and Gas Detector - Flame Detector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.96 | 1905.94 | 1829.7 | 857.67 | 972.03 | 1 | 3500235947 | 11078.18
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.6 | MFI_Junction Box | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 376.17 | 338.55 | 338.55 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.PA1I.IR | Procurement - INSTRUMENTATION, CONTROL, PROTECTION EQUIPMENT & CABLE SYSTEM | MFI.IV.7 | MFI_Cable Gland & Accessories | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.45 | 295.44 | 132.95 | 132.95 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0004-CAL-007 | USD_ - Calculation for Pressure Regulating Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0004-CAL-007 | USD_ - Calculation for Pressure Regulating Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-003 | USD_ - Instrument & Telecom Power Consumption & Heat Dissipation List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-003 | USD_ - Instrument & Telecom Power Consumption & Heat Dissipation List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-004 | USD_ - Sizing Calculation for Flow Element (Orifice Plate, RO) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-004 | USD_ - Sizing Calculation for Flow Element (Orifice Plate, RO) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-005 | USD_ - Sizing Calculation for Pressure Safety Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-005 | USD_ - Sizing Calculation for Pressure Safety Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-006 | USD_ - Sizing Calculation for Thermowell | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0005-CAL-006 | USD_ - Sizing Calculation for Thermowell | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.0007-DWG-001 | USD_ - Standard Drawing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.0007-DWG-001 | USD_ - Standard Drawing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-008 | USD_ - Instrument and F&G Typical Installation Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-008 | USD_ - Instrument and F&G Typical Installation Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-009 | USD_ - Telecommunication Typical Installation Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-009 | USD_ - Telecommunication Typical Installation Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-010 | USD_ - Cause & Effect for Emergency shutdown system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-010 | USD_ - Cause & Effect for Emergency shutdown system | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-011 | USD_ - Cause & Effect for Fire & Gas system | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 396.73 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-011 | USD_ - Cause & Effect for Fire & Gas system | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6394716 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-018 | USD_ - Instrument Wiring Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0007-DWG-018 | USD_ - Instrument Wiring Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.0008-LST-001 | USD_ - Equipment List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.0008-LST-001 | USD_ - Equipment List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0008-LST-002 | USD_ - Instrument Index | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0008-LST-002 | USD_ - Instrument Index | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0008-LST-003 | USD_ - Instrument I/O List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.0008-LST-003 | USD_ - Instrument I/O List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.000C-SOW-001 | USD_ - Scope of Work for Soil Investigation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.000C-SOW-001 | USD_ - Scope of Work for Soil Investigation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.020F-VDR-022 | USD_ - VDR for Bulk Material | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.020F-VDR-022 | USD_ - VDR for Bulk Material | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.1000-SPC-001 | USD_ - Mechanical Design Criteria | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.1000-SPC-001 | USD_ - Mechanical Design Criteria | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-015 | USD_ - Interconnection Diagram for Motors & associated panels | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-015 | USD_ - Interconnection Diagram for Motors & associated panels | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-016 | USD_ - 70 kV Switchgear A Tariff Metering, Metering and Protection, and Synchronouz Panel Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-016 | USD_ - 70 kV Switchgear A Tariff Metering, Metering and Protection, and Synchronouz Panel Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-017 | USD_ - 70 kV Switchgear B Tariff Metering, Metering and Protection, and Synchronouz Panel Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-017 | USD_ - 70 kV Switchgear B Tariff Metering, Metering and Protection, and Synchronouz Panel Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-018 | USD_ - 11 kV Switchgear MV-SWG-001 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-018 | USD_ - 11 kV Switchgear MV-SWG-001 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-019 | USD_ - 11 kV Switchgear MV-SWG-002 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-019 | USD_ - 11 kV Switchgear MV-SWG-002 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-020 | USD_ - 0.4 kV Switchgear LV-SWG-001 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-020 | USD_ - 0.4 kV Switchgear LV-SWG-001 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-021 | USD_ - 0.4 kV Switchgear LV-SWG-002 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-021 | USD_ - 0.4 kV Switchgear LV-SWG-002 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-022 | USD_ - 0.4 kV Switchgear LV-SWG-003 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-022 | USD_ - 0.4 kV Switchgear LV-SWG-003 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-023 | USD_ - 0.4 kV Switchgear LV-SWG-004 Interconnection Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-023 | USD_ - 0.4 kV Switchgear LV-SWG-004 Interconnection Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-024 | USD_ - Interconnection Diagram for AC - DC UPS & associated package equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-024 | USD_ - Interconnection Diagram for AC - DC UPS & associated package equipment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-025 | USD_ - Interconnection Diagram for Lighting Circuits Block Diagram (Lighting & Small Power) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2101-DIA-025 | USD_ - Interconnection Diagram for Lighting Circuits Block Diagram (Lighting & Small Power) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-CAL-003 | USD_ - Voltage Drop and Cable Sizing calculation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-CAL-003 | USD_ - Voltage Drop and Cable Sizing calculation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-001 | USD_ - Load Flow Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-001 | USD_ - Load Flow Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-002 | USD_ - Short Circuit Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-002 | USD_ - Short Circuit Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-003 | USD_ - Motor Starting Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-003 | USD_ - Motor Starting Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-004 | USD_ - Protection Coordination Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-004 | USD_ - Protection Coordination Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-005 | USD_ - Neutral Earthing Selection Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-005 | USD_ - Neutral Earthing Selection Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-006 | USD_ - Illumination Study | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2105-SDY-006 | USD_ - Illumination Study | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-DWG-014 | USD_ - Symbol and Legend | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-DWG-014 | USD_ - Symbol and Legend | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-DWG-026 | USD_ - Typical Installation Details | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-DWG-026 | USD_ - Typical Installation Details | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-LAY-010 | USD_ - Electrical Equipment Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2107-LAY-010 | USD_ - Electrical Equipment Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2108-LST-001 | USD_ - Electrical Load List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2108-LST-001 | USD_ - Electrical Load List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2108-LST-002 | USD_ - Electrical Equipment List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.2108-LST-002 | USD_ - Electrical Equipment List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2415-RPT-001 | USD_ - Process Simulation and Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2415-RPT-001 | USD_ - Process Simulation and Report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2445-RPT-002 | USD_ - Equipment sizing report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2445-RPT-002 | USD_ - Equipment sizing report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2465-RPT-004 | USD_ - Utility Demand report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2465-RPT-004 | USD_ - Utility Demand report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2475-RPT-005 | USD_ - Fire Water Demand Calculation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.2475-RPT-005 | USD_ - Fire Water Demand Calculation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3207-KEY-002 | USD_ - Equipment Layout Index | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3207-KEY-002 | USD_ - Equipment Layout Index | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3207-PLT-001 | USD_ - Overall Plot Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3207-PLT-001 | USD_ - Overall Plot Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-003 | USD_ - Equipment Layout1 - Power Island | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-003 | USD_ - Equipment Layout1 - Power Island | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-004 | USD_ - Equipment Layout2 - Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-004 | USD_ - Equipment Layout2 - Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-005 | USD_ - Equipment Layout3 - Waste Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-005 | USD_ - Equipment Layout3 - Waste Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-006 | USD_ - Equipment Layout4 - Diesel System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-006 | USD_ - Equipment Layout4 - Diesel System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-007 | USD_ - Equipment Layout5 - Fire Water | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.3407-PLT-007 | USD_ - Equipment Layout5 - Fire Water | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.4001-DWG-003 | USD_ - Fire & Gas System Block Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.4001-DWG-003 | USD_ - Fire & Gas System Block Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.4001-DWG-004 | USD_ - Telecommunication System Block Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.4001-DWG-004 | USD_ - Telecommunication System Block Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-001 | USD_ - Overall One Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-001 | USD_ - Overall One Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-002 | USD_ - 11 kV Switchgear MV-SWG-001 Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-002 | USD_ - 11 kV Switchgear MV-SWG-001 Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-003 | USD_ - 11 kV Switchgear MV-SWG-002 Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-003 | USD_ - 11 kV Switchgear MV-SWG-002 Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-004 | USD_ - 0.4 kV Switchgear LV-SWG-001 Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-004 | USD_ - 0.4 kV Switchgear LV-SWG-001 Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-005 | USD_ - 0.4 kV Switchgear LV-SWG-002 Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-005 | USD_ - 0.4 kV Switchgear LV-SWG-002 Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-008 | USD_ - One Line Diagram for AC UPS System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-008 | USD_ - One Line Diagram for AC UPS System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-009 | USD_ - One Line Diagram for DC UPS System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-009 | USD_ - One Line Diagram for DC UPS System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-027 | USD_ - 70 kV Switchgear A Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-027 | USD_ - 70 kV Switchgear A Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-028 | USD_ - 70 kV Switchgear B Metering and Relay Single Line Diagram | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.4201-SLD-028 | USD_ - 70 kV Switchgear B Metering and Relay Single Line Diagram | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-KEY-001 | USD_ - Piping Plan and Section - Key Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-KEY-001 | USD_ - Piping Plan and Section - Key Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-002 | USD_ - Piping Plan and Section 1 - Power Island | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-002 | USD_ - Piping Plan and Section 1 - Power Island | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-004 | USD_ - Piping Plan and Section 3 - Waste Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-004 | USD_ - Piping Plan and Section 3 - Waste Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-005 | USD_ - Piping Plan and Section 4 - Diesel System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-005 | USD_ - Piping Plan and Section 4 - Diesel System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-006 | USD_ - Piping Plan and Section 5 - Fire Water | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-006 | USD_ - Piping Plan and Section 5 - Fire Water | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-007 | USD_ - Fire Water Ring | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-007 | USD_ - Fire Water Ring | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-03 | USD_ - Piping Plan and Section 2 - Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4207-LAY-03 | USD_ - Piping Plan and Section 2 - Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-001 | USD_ - Standard Drawing For Piping Arrangement | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-001 | USD_ - Standard Drawing For Piping Arrangement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-002 | USD_ - Piping Standard Drawing for Hook-Up & Drawing Index | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-002 | USD_ - Piping Standard Drawing for Hook-Up & Drawing Index | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-003 | USD_ - Piping Support Standard Drawings | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4307-STD-003 | USD_ - Piping Support Standard Drawings | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4417-ISO-001 | USD_ - Isometric drawing (225 sheets) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4417-ISO-001 | USD_ - Isometric drawing (225 sheets) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4427-LAY-008 | USD_ - Piping Support Location Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.4427-LAY-008 | USD_ - Piping Support Location Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5003-SPC-002 | USD_ - Specification for Power Plant Control System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5003-SPC-002 | USD_ - Specification for Power Plant Control System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5007-DWG-001 | USD_ - Overall Control System Architecture | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5007-DWG-001 | USD_ - Overall Control System Architecture | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5007-DWG-022 | USD_ - Central Control Room Equipment Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5007-DWG-022 | USD_ - Central Control Room Equipment Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5007-DWG-030 | USD_ - 70 KV Gunung Sitoli Substation Outdoor Installation General Layout (New Incoming Bay) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5007-DWG-030 | USD_ - 70 KV Gunung Sitoli Substation Outdoor Installation General Layout (New Incoming Bay) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5007-DWG-031 | USD_ - 70 KV Gunung Sitoli Substation Indoor Installation Control Building Layout (New Incoming Bay) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5007-DWG-031 | USD_ - 70 KV Gunung Sitoli Substation Indoor Installation Control Building Layout (New Incoming Bay) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.500F-VDR-001 | USD_ - VDR for Power Plant Controll System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.500F-VDR-001 | USD_ - VDR for Power Plant Controll System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5104-DTS-016 | USD_ - Datasheet for Raw Water Lifting Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5104-DTS-016 | USD_ - Datasheet for Raw Water Lifting Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.510F-VDR-001 | USD_ - VDR for Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.510F-VDR-001 | USD_ - VDR for Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5113-SPC-002 | USD_ - Specification for Piping Flexibility Analysis | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5113-SPC-002 | USD_ - Specification for Piping Flexibility Analysis | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5123-SPC-007 | USD_ - Specification for Black Start/Emergency Diesel Engine Generator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5123-SPC-007 | USD_ - Specification for Black Start/Emergency Diesel Engine Generator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5124-DTS-008 | USD_ - Data Sheet Black Start/Emergency Diesel Engine Generator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5124-DTS-008 | USD_ - Data Sheet Black Start/Emergency Diesel Engine Generator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5124-DTS-023 | USD_ - Data Sheet for Generator Control Panel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5124-DTS-023 | USD_ - Data Sheet for Generator Control Panel | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5125-CAL-007 | USD_ - Emergency Diesel Generator Sizing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5125-CAL-007 | USD_ - Emergency Diesel Generator Sizing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.512F-VDR-001 | USD_ - VDR Generator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.512F-VDR-001 | USD_ - VDR Generator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.512F-VDR-008 | USD_ - VDR Black Start/Emergency Diesel Engine Generator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 191841492 | 153473194 | 153473194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.512F-VDR-008 | USD_ - VDR Black Start/Emergency Diesel Engine Generator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11901.72 | 9521.38 | 9521.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-001 | USD_ - Review and Analysis of Soil Investigation Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-001 | USD_ - Review and Analysis of Soil Investigation Report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-002 | USD_ - Deep Well Logging Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-002 | USD_ - Deep Well Logging Report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-003 | USD_ - Water Soil's Chemical Test Result | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5206-RPT-003 | USD_ - Water Soil's Chemical Test Result | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5207-DWG-029 | USD_ - Soil Investigation Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.5207-DWG-029 | USD_ - Soil Investigation Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5213-SPC-013 | USD_ - Specification for Generator Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5213-SPC-013 | USD_ - Specification for Generator Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5213-SPC-014 | USD_ - Specification for Switchyard Equipment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5213-SPC-014 | USD_ - Specification for Switchyard Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-014 | USD_ - Data Sheet Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-014 | USD_ - Data Sheet Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-015 | USD_ - Data Sheet 70 KV/150 KV Circuit Breakers | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-015 | USD_ - Data Sheet 70 KV/150 KV Circuit Breakers | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-016 | USD_ - Data Sheet 70 KV/150 KV Disconnector And Earthing Switches | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-016 | USD_ - Data Sheet 70 KV/150 KV Disconnector And Earthing Switches | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-017 | USD_ - Data Sheet 70 KV/150 KV Current Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-017 | USD_ - Data Sheet 70 KV/150 KV Current Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-018 | USD_ - Data Sheet 70 KV/150 KV Voltage Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-018 | USD_ - Data Sheet 70 KV/150 KV Voltage Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-019 | USD_ - Data Sheet 70 KV/150 KV Surge Arresters | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-019 | USD_ - Data Sheet 70 KV/150 KV Surge Arresters | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-020 | USD_ - Data Sheet 70 KV/150 KV Tariff Metering, Control, Protection and Relay Panels | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5214-DTS-020 | USD_ - Data Sheet 70 KV/150 KV Tariff Metering, Control, Protection and Relay Panels | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5215-CAL-002 | USD_ - Generator Transformer Sizing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5215-CAL-002 | USD_ - Generator Transformer Sizing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5215-CAL-006 | USD_ - Unit Auxiliary Transformer Sizing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5215-CAL-006 | USD_ - Unit Auxiliary Transformer Sizing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.521F-VDR-016 | USD_ - VDR Generator Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.521F-VDR-016 | USD_ - VDR Generator Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.72 | 11901.72 | 11901.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.521F-VDR-018 | USD_ - VDR for Switchyard Equipment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.521F-VDR-018 | USD_ - VDR for Switchyard Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.72 | 11901.72 | 11901.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.522F-VDR-019 | USD_ - VDR For Generator Control Panel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.522F-VDR-019 | USD_ - VDR For Generator Control Panel | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5303-SPC-019 | USD_ - Specification for NER | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5303-SPC-019 | USD_ - Specification for NER | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5304-DTS-025 | USD_ - Datasheet for Ner | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5304-DTS-025 | USD_ - Datasheet for Ner | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.530F-VDR-021 | USD_ - VDR For Ner | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 127894328 | 127894328 | 127894328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.530F-VDR-021 | USD_ - VDR For Ner | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7934.48 | 7934.48 | 7934.48 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5404-DTS-050 | USD_ - Datasheet for Ventilation For Power House (Generator Side) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5404-DTS-050 | USD_ - Datasheet for Ventilation For Power House (Generator Side) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5404-DTS-051 | USD_ - Datasheet for Ventilation For Power House (Annex Side) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5404-DTS-051 | USD_ - Datasheet for Ventilation For Power House (Annex Side) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.540F-VDR-011 | USD_ - VDR for Fan/Blower | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.71 | 11901.71 | 11901.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.540F-VDR-011 | USD_ - VDR for Fan/Blower | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-005 | USD_ - VDR Stack & Ducting | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 7934.47 | 6347.58 | 6347.58 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-005 | USD_ - VDR Stack & Ducting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 127894328 | 102315462 | 102315462 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-001 | USD_ - Generator Engine | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11901.71 | 9521.37 | 9521.37 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-001 | USD_ - Generator Engine | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 191841492 | 153473194 | 153473194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-002 | USD_ - Alternator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-002 | USD_ - Alternator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-003 | USD_ - Fuel Oil Purifier Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-003 | USD_ - Fuel Oil Purifier Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-004 | USD_ - Fuel Oil Supply Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-004 | USD_ - Fuel Oil Supply Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-005 | USD_ - Pilot Oil Supply Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-005 | USD_ - Pilot Oil Supply Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-006 | USD_ - Clean And Pilot Oil Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-006 | USD_ - Clean And Pilot Oil Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-007 | USD_ - Dirty Oil Drain Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-007 | USD_ - Dirty Oil Drain Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-008 | USD_ - LO Unloading Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-008 | USD_ - LO Unloading Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-009 | USD_ - Portable LO Receiving Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-009 | USD_ - Portable LO Receiving Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-010 | USD_ - LO Transfer Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-010 | USD_ - LO Transfer Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-011 | USD_ - Lube Oil Unit With Temp. Control Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-011 | USD_ - Lube Oil Unit With Temp. Control Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-012 | USD_ - LO Purfier Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-012 | USD_ - LO Purfier Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-013 | USD_ - Portable Used LO Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-013 | USD_ - Portable Used LO Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-014 | USD_ - Water Cooling Radiator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-014 | USD_ - Water Cooling Radiator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-015 | USD_ - Cooling Water Expansion Tank (LT&HT) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-015 | USD_ - Cooling Water Expansion Tank (LT&HT) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-016 | USD_ - Cooling Water System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-016 | USD_ - Cooling Water System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-019 | USD_ - Compressed Air System Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-019 | USD_ - Compressed Air System Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-020 | USD_ - Starting Air Receiver Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-020 | USD_ - Starting Air Receiver Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-021 | USD_ - Intake Air Filter with Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-021 | USD_ - Intake Air Filter with Silencer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-022 | USD_ - Exhaust Gas Silencer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-022 | USD_ - Exhaust Gas Silencer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-023 | USD_ - Rupture Disc | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-023 | USD_ - Rupture Disc | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-024 | USD_ - CW Maintenance Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.550F-VDR-013-024 | USD_ - CW Maintenance Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.23 | 3173.78 | 3173.78 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-029 | USD_ - Datasheet for Air Intake Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-029 | USD_ - Datasheet for Air Intake Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-030 | USD_ - Datasheet for Exhaust Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-030 | USD_ - Datasheet for Exhaust Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-031 | USD_ - Datasheet for Exhaust Stack | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.5514-DTS-031 | USD_ - Datasheet for Exhaust Stack | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5523-SPC-002 | USD_ - Specification for Medium Voltage Switchgear | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5523-SPC-002 | USD_ - Specification for Medium Voltage Switchgear | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5524-DTS-002 | USD_ - Data Sheet Medium Voltage Switchgear | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5524-DTS-002 | USD_ - Data Sheet Medium Voltage Switchgear | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.552F-VDR-002 | USD_ - VDR Medium Voltage Switchgear | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.72 | 11901.72 | 11901.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.552F-VDR-002 | USD_ - VDR Medium Voltage Switchgear | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5543-SPC-003 | USD_ - Specification for 400 V SWG/MCC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5543-SPC-003 | USD_ - Specification for 400 V SWG/MCC | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5544-DTS-004 | USD_ - Data Sheet 400 V SWG/MCC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5544-DTS-004 | USD_ - Data Sheet 400 V SWG/MCC | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.554F-VDR-004 | USD_ - VDR 400V SWG/MCC | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11901.72 | 9521.38 | 9521.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.554F-VDR-004 | USD_ - VDR 400V SWG/MCC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 191841492 | 153473194 | 153473194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5573-SPC-018 | USD_ - Specification for Power Distribution Board | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5573-SPC-018 | USD_ - Specification for Power Distribution Board | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5574-DTS-024 | USD_ - Data Sheet for Power Distribution Board | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5574-DTS-024 | USD_ - Data Sheet for Power Distribution Board | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5577-DWG-021 | USD_ - Main Cable Way Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.5577-DWG-021 | USD_ - Main Cable Way Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.557F-VDR-020 | USD_ - VDR For Power Distribution Board | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.557F-VDR-020 | USD_ - VDR For Power Distribution Board | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.72 | 11901.72 | 11901.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.55A3-SPC-004 | USD_ - Specification for Low Voltage Motors | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.55A3-SPC-004 | USD_ - Specification for Low Voltage Motors | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.55AF-VDR-005 | USD_ - VDR Low Voltage Motor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.55AF-VDR-005 | USD_ - VDR Low Voltage Motor | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.72 | 11901.72 | 11901.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5613-SPC-005 | USD_ - Specification for DC Battery and Charger | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5613-SPC-005 | USD_ - Specification for DC Battery and Charger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5613-SPC-006 | USD_ - Specification for Uninterruptible Ac Power Supply | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5613-SPC-006 | USD_ - Specification for Uninterruptible Ac Power Supply | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5614-DTS-006 | USD_ - Data Sheet DC Battery and Charger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5614-DTS-006 | USD_ - Data Sheet DC Battery and Charger | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5614-DTS-007 | USD_ - Data Sheet Uninterruptible AC Power Supply | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5614-DTS-007 | USD_ - Data Sheet Uninterruptible AC Power Supply | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.561F-VDR-007 | USD_ - VDR AC UPS and DC Battery Charger | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11901.72 | 9521.38 | 9521.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.561F-VDR-007 | USD_ - VDR AC UPS and DC Battery Charger | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 191841492 | 153473194 | 153473194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5701-DWG-029 | USD_ - Isometric for Busduct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5701-DWG-029 | USD_ - Isometric for Busduct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5704-DTS-003 | USD_ - Data Sheet Bus Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.5704-DTS-003 | USD_ - Data Sheet Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.570F-VDR-003 | USD_ - VDR Bus Duct | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 7934.48 | 6347.58 | 6347.58 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.570F-VDR-003 | USD_ - VDR Bus Duct | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 127894328 | 102315462 | 102315462 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-099 | USD_ - Fire Water Pump Shelter Portal Frame, Roof Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-099 | USD_ - Fire Water Pump Shelter Portal Frame, Roof Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-100-01 | USD_ - Fire Water Pump Shelter Plan View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-100-01 | USD_ - Fire Water Pump Shelter Plan View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-101 | USD_ - Fire Water Pump Shelter Architecture Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-101 | USD_ - Fire Water Pump Shelter Architecture Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-102 | USD_ - Fire Water Pump Shelter Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-102 | USD_ - Fire Water Pump Shelter Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-105 | USD_ - WTP Shelter Portal Frame, Roof Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-105 | USD_ - WTP Shelter Portal Frame, Roof Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-106 | USD_ - WTP Shelter Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-106 | USD_ - WTP Shelter Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-107 | USD_ - WTP Shelter Architecture Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-107 | USD_ - WTP Shelter Architecture Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-108 | USD_ - WTP Shelter Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-108 | USD_ - WTP Shelter Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-111-01 | USD_ - Parking Shelter Framing Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-111-01 | USD_ - Parking Shelter Framing Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-111-02 | USD_ - Parking Shelter Framing Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-111-02 | USD_ - Parking Shelter Framing Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-112-01 | USD_ - Parking Shelter Plan View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-112-01 | USD_ - Parking Shelter Plan View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-113 | USD_ - Parking Area Shelter Architecture Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-113 | USD_ - Parking Area Shelter Architecture Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-114 | USD_ - Parking Area Shelter Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-114 | USD_ - Parking Area Shelter Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-117-01 | USD_ - Pump Shelter Framing Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-117-01 | USD_ - Pump Shelter Framing Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-117-02 | USD_ - Pump Shelter Framing Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-117-02 | USD_ - Pump Shelter Framing Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-118-01 | USD_ - Pump Shelter Plan View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-118-01 | USD_ - Pump Shelter Plan View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-118-02 | USD_ - Pump Shelter Elevation View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-118-02 | USD_ - Pump Shelter Elevation View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-119 | USD_ - Fuel Oil Purification Shelter Architecture Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-119 | USD_ - Fuel Oil Purification Shelter Architecture Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-120 | USD_ - Fuel Oil Purification Shelter Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.6007-DWG-120 | USD_ - Fuel Oil Purification Shelter Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6113-SPC-001 | USD_ - Piping Material Class and Specification | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6113-SPC-001 | USD_ - Piping Material Class and Specification | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6204-DTS-054 | USD_ - Datasheet for Crane for Power Generation Building | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6204-DTS-054 | USD_ - Datasheet for Crane for Power Generation Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6204-DTS-057 | USD_ - Datasheet for Crane Warehouse Building | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.6204-DTS-057 | USD_ - Datasheet for Crane Warehouse Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6303-SPC-008 | USD_ - Specification for Cable and Wires | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6303-SPC-008 | USD_ - Specification for Cable and Wires | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6307-LAY-011 | USD_ - Cable & Cable Tray Routing Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6307-LAY-011 | USD_ - Cable & Cable Tray Routing Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6308-SCH-002 | USD_ - Electrical Power and Control Cable Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6308-SCH-002 | USD_ - Electrical Power and Control Cable Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-009 | USD_ - VDR Cable And Wires | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-009 | USD_ - VDR Cable And Wires | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-010 | USD_ - VDR Cable And Wires (11 kV) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-010 | USD_ - VDR Cable And Wires (11 kV) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-011 | USD_ - VDR Cable And Wires (LV Cable) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.630F-VDR-011 | USD_ - VDR Cable And Wires (LV Cable) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6423-SPC-009 | USD_ - Specification for Cable Tray System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6423-SPC-009 | USD_ - Specification for Cable Tray System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6424-DTS-010 | USD_ - Data Sheet Cable Tray System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.6424-DTS-010 | USD_ - Data Sheet Cable Tray System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.642F-VDR-012 | USD_ - VDR Cable Tray System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.642F-VDR-012 | USD_ - VDR Cable Tray System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7003-SPC-001 | USD_ - Specification for General Instrumentation (Field Instrument, Valves, JB, Cable Gland, Cable Tray, Wiring Accessor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7003-SPC-001 | USD_ - Specification for General Instrumentation (Field Instrument, Valves, JB, Cable Gland, Cable Tray, Wiring Accessor | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7003-SPC-005 | USD_ - Specification for Fire & Gas System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7003-SPC-005 | USD_ - Specification for Fire & Gas System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7003-SPC-007 | USD_ - Standard Specification for Concrete Construction | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7003-SPC-007 | USD_ - Standard Specification for Concrete Construction | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7003-SPC-008 | USD_ - Standard Specification for Grouting of Structure and Equipments | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7003-SPC-008 | USD_ - Standard Specification for Grouting of Structure and Equipments | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7003-SPC-012 | USD_ - Specification for Lighting | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7003-SPC-012 | USD_ - Specification for Lighting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-005 | USD_ - Datasheet for Pressure Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-005 | USD_ - Datasheet for Pressure Gauge | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-006 | USD_ - Datasheet for Pressure Transmitter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-006 | USD_ - Datasheet for Pressure Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-007 | USD_ - Datasheet for Flow Transmitter DP Type | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-007 | USD_ - Datasheet for Flow Transmitter DP Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-008 | USD_ - Datasheet for Level Transmitter DP Type | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-008 | USD_ - Datasheet for Level Transmitter DP Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-009 | USD_ - Datasheet for Temperature Gauges & Thermowell | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-009 | USD_ - Datasheet for Temperature Gauges & Thermowell | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-010 | USD_ - Datasheet for Temperature Transmitter & Thermowell | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-010 | USD_ - Datasheet for Temperature Transmitter & Thermowell | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-011 | USD_ - Datasheet for Restriction Orifice | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-011 | USD_ - Datasheet for Restriction Orifice | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-012 | USD_ - Datasheet for Level Gauge Glass | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-012 | USD_ - Datasheet for Level Gauge Glass | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7004-DTS-013 | USD_ - Data Sheet Lighting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7004-DTS-013 | USD_ - Data Sheet Lighting | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-014 | USD_ - Datasheet for Ultrasonic Flow Transmitter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7004-DTS-014 | USD_ - Datasheet for Ultrasonic Flow Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7005-CAL-002 | USD_ - Voltage Drop Calculation for Field Instrument | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.7005-CAL-002 | USD_ - Voltage Drop Calculation for Field Instrument | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-001 | USD_ - Civil and Structural Drawing List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-001 | USD_ - Civil and Structural Drawing List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-002 | USD_ - General Notes for Civil and Structure | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-002 | USD_ - General Notes for Civil and Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-003 | USD_ - Abbreviation & Symbol for Civil Work | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-003 | USD_ - Abbreviation & Symbol for Civil Work | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-004 | USD_ - Standard Drawing Concrete Reinforcement (01 of 03) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-004 | USD_ - Standard Drawing Concrete Reinforcement (01 of 03) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-005 | USD_ - Standard Drawing Concrete Reinforcement (02 of 03) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-005 | USD_ - Standard Drawing Concrete Reinforcement (02 of 03) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-006 | USD_ - Standard Drawing Concrete Reinforcement (03 of 03) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-006 | USD_ - Standard Drawing Concrete Reinforcement (03 of 03) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-007 | USD_ - Standard Drawing Cable Trench & Duct Bank (01 OF 02) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-007 | USD_ - Standard Drawing Cable Trench & Duct Bank (01 OF 02) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-008 | USD_ - Standard Drawing Cable Trench & Duct Bank (02 OF 02) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-008 | USD_ - Standard Drawing Cable Trench & Duct Bank (02 OF 02) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-009 | USD_ - Standard Drawing Pile Head Treatment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-009 | USD_ - Standard Drawing Pile Head Treatment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-010 | USD_ - Standard Drawing Steel Doors and window Details | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-010 | USD_ - Standard Drawing Steel Doors and window Details | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-011 | USD_ - Standard Drawing Member Designation for Steel Structure | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-011 | USD_ - Standard Drawing Member Designation for Steel Structure | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-012 | USD_ - Standard Drawing Column Base Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-012 | USD_ - Standard Drawing Column Base Plate | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-013 | USD_ - Standard Drawing Beam to Column Moment Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-013 | USD_ - Standard Drawing Beam to Column Moment Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-014 | USD_ - Standard Drawing Beam Pin Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-014 | USD_ - Standard Drawing Beam Pin Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-015 | USD_ - Standard Drawing Column Splice | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-015 | USD_ - Standard Drawing Column Splice | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-017 | USD_ - Standard Drawing Horizontal Bracing Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-017 | USD_ - Standard Drawing Horizontal Bracing Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-018 | USD_ - Standard Drawing Anchor Bolts | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-018 | USD_ - Standard Drawing Anchor Bolts | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-019 | USD_ - Standard Drawing Welding Details | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-019 | USD_ - Standard Drawing Welding Details | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-020 | USD_ - Standard Drawing Detail of Typical Insert Plate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-020 | USD_ - Standard Drawing Detail of Typical Insert Plate | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-021 | USD_ - Standard Drawing Handrail Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-021 | USD_ - Standard Drawing Handrail Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-022 | USD_ - Standard Drawing Ladder, Safety Cage and Safety Gate (01 of 02) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-022 | USD_ - Standard Drawing Ladder, Safety Cage and Safety Gate (01 of 02) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-023 | USD_ - Standard Drawing Ladder, Safety Cage and Safety Gate (02 of 02) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-023 | USD_ - Standard Drawing Ladder, Safety Cage and Safety Gate (02 of 02) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-024 | USD_ - Standard Drawing Floor and Joist | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-024 | USD_ - Standard Drawing Floor and Joist | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-025 | USD_ - Standard Drawing Security Fence and Gate | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-025 | USD_ - Standard Drawing Security Fence and Gate | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026 | USD_ - Standard Drawing Steel Stair | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026 | USD_ - Standard Drawing Steel Stair | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026-2 | USD_ - Standard Drawing Steel Stair | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026-2 | USD_ - Standard Drawing Steel Stair | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026-3 | USD_ - Standard Drawing Steel Stair | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-026-3 | USD_ - Standard Drawing Steel Stair | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-027 | USD_ - Standard Drawing Steel Expansion Joint | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-027 | USD_ - Standard Drawing Steel Expansion Joint | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-028 | USD_ - Standard Drawing Fence | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-028 | USD_ - Standard Drawing Fence | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-01 | USD_ - Standard Drawing For Shelter Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-01 | USD_ - Standard Drawing For Shelter Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-02 | USD_ - Standard Drawing For Shelter Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-02 | USD_ - Standard Drawing For Shelter Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-03 | USD_ - Standard Drawing For Shelter Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7007-DWG-031-03 | USD_ - Standard Drawing For Shelter Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7007-LAY-012 | USD_ - Lighting Layout Area | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.7007-LAY-012 | USD_ - Lighting Layout Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-006 | USD_ - VDR for Pressure & Differential Pressure Gauge | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-006 | USD_ - VDR for Pressure & Differential Pressure Gauge | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-007 | USD_ - VDR for Pressure & Differential Pressure Transmitter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-007 | USD_ - VDR for Pressure & Differential Pressure Transmitter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-008 | USD_ - VDR for Flow Transmitter DP Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-008 | USD_ - VDR for Flow Transmitter DP Type | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-009 | USD_ - VDR for Level Transmitter DP Type | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-009 | USD_ - VDR for Level Transmitter DP Type | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-010 | USD_ - VDR for Temperature Gauges & Thermowell | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-010 | USD_ - VDR for Temperature Gauges & Thermowell | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-011 | USD_ - VDR for Temperature Transmitter & Thermowell | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.93 | 3967.24 | 3689.53 | 3689.53 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-011 | USD_ - VDR for Temperature Transmitter & Thermowell | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.93 | 63947164 | 59470863 | 59470863 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-012 | USD_ - VDR for Orifice Plate & Restriction Orifice | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.24 | 3173.79 | 3173.79 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-012 | USD_ - VDR for Orifice Plate & Restriction Orifice | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-013 | USD_ - VDR for Level Gauge Glass | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.24 | 3173.79 | 3173.79 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.700F-VDR-013 | USD_ - VDR for Level Gauge Glass | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.700F-VDR-015 | USD_ - VDR Lighting | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 127894328 | 127894328 | 127894328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.700F-VDR-015 | USD_ - VDR Lighting | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7934.48 | 7934.48 | 7934.48 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-003 | USD_ - Calculation for Grading Cut & fill | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-003 | USD_ - Calculation for Grading Cut & fill | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-036 | USD_ - Foundation Calculation for Fuel Oil Daily Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-036 | USD_ - Foundation Calculation for Fuel Oil Daily Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-050 | USD_ - Foundation Calculation for Combine Raw Water Storage & Fire Water Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-CAL-050 | USD_ - Foundation Calculation for Combine Raw Water Storage & Fire Water Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-001 | USD_ - Study of Application Pile for Tank Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-001 | USD_ - Study of Application Pile for Tank Foundation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-002 | USD_ - Study for Maximum Settlement at Tank Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-002 | USD_ - Study for Maximum Settlement at Tank Foundation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-003 | USD_ - Study for Maximum Settlement at Engine Foundation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7105-SDY-003 | USD_ - Study for Maximum Settlement at Engine Foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-006 | USD_ - Grading Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-006 | USD_ - Grading Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-007 | USD_ - Grading Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-007 | USD_ - Grading Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-150 | USD_ - Foundation for Fuel Oil Daily Tank Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-150 | USD_ - Foundation for Fuel Oil Daily Tank Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-165 | USD_ - Combine Raw Fire Water Tank Piling Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7107-DWG-165 | USD_ - Combine Raw Fire Water Tank Piling Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-025 | USD_ - Foundation Calculation for Engine (Dual Fuel ) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-025 | USD_ - Foundation Calculation for Engine (Dual Fuel ) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-026 | USD_ - Foundation Calculation for Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-026 | USD_ - Foundation Calculation for Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-027 | USD_ - Foundation Calculation for Auxilary Transformer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-027 | USD_ - Foundation Calculation for Auxilary Transformer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-029 | USD_ - Foundation Calculation for HT & LT Cooling Water Radiator | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-029 | USD_ - Foundation Calculation for HT & LT Cooling Water Radiator | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-030 | USD_ - Foundation Calculation for Cooling Water Maintenace Tank & Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-030 | USD_ - Foundation Calculation for Cooling Water Maintenace Tank & Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-031 | USD_ - Foundation Calculation for Lube oil Cooler Console & purifier | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-031 | USD_ - Foundation Calculation for Lube oil Cooler Console & purifier | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-032 | USD_ - Foundation Calculation for Emergency Diesel Generator (Black Start Generator) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-032 | USD_ - Foundation Calculation for Emergency Diesel Generator (Black Start Generator) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-033 | USD_ - Foundation Calculation for Lube Oil Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-033 | USD_ - Foundation Calculation for Lube Oil Storage Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-034 | USD_ - Foundation Calculation for Used/Drain Lube Oil Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-034 | USD_ - Foundation Calculation for Used/Drain Lube Oil Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-035 | USD_ - Foundation Calculation for Lube Oil Unloading and Transfer Pump (Supply) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-035 | USD_ - Foundation Calculation for Lube Oil Unloading and Transfer Pump (Supply) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-038 | USD_ - Foundation Calculation for Fuel Oil Dirty Oil Tanks | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-038 | USD_ - Foundation Calculation for Fuel Oil Dirty Oil Tanks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-044 | USD_ - Foundation Calculation for Gas Metering Analyzer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-044 | USD_ - Foundation Calculation for Gas Metering Analyzer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-045 | USD_ - Foundation Calculation for Starting Air Compressor (electric) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-045 | USD_ - Foundation Calculation for Starting Air Compressor (electric) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-047 | USD_ - Foundation Calculation for Aeration Blower unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-047 | USD_ - Foundation Calculation for Aeration Blower unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-048 | USD_ - Foundation Calculation for Raw Water Lifting and Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-048 | USD_ - Foundation Calculation for Raw Water Lifting and Transfer Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-049 | USD_ - Foundation Calculation for Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-049 | USD_ - Foundation Calculation for Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-051 | USD_ - Foundation Calculation for Motor and Diesel Driven Fire Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-051 | USD_ - Foundation Calculation for Motor and Diesel Driven Fire Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-052 | USD_ - Foundation Calculation for Power House and Annex | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7205-CAL-052 | USD_ - Foundation Calculation for Power House and Annex | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-139 | USD_ - Foundation for Transformer Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-139 | USD_ - Foundation for Transformer Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-140 | USD_ - Foundation for Auxilary Transformer Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-140 | USD_ - Foundation for Auxilary Transformer Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-143 | USD_ - Foundation for HT & LT Cooling Water Radiator Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-143 | USD_ - Foundation for HT & LT Cooling Water Radiator Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-144 | USD_ - Foundation for Cooling Water Maintenace Tank & Pump Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-144 | USD_ - Foundation for Cooling Water Maintenace Tank & Pump Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-145 | USD_ - Foundation for Lube oil Console & purifier Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-145 | USD_ - Foundation for Lube oil Console & purifier Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-146 | USD_ - Foundation for Emergency Diesel Generator (Black Start Generator) Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-146 | USD_ - Foundation for Emergency Diesel Generator (Black Start Generator) Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-147 | USD_ - Foundation for Lube Oil Storage Tank Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-147 | USD_ - Foundation for Lube Oil Storage Tank Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-148 | USD_ - Foundation for Used Lube Oil Tank Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-148 | USD_ - Foundation for Used Lube Oil Tank Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-149 | USD_ - Foundation for Lube Oil Unloading Pump (Supply) and Transfer Pump Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-149 | USD_ - Foundation for Lube Oil Unloading Pump (Supply) and Transfer Pump Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-158 | USD_ - Foundation for Gas Metering Analyzer Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-158 | USD_ - Foundation for Gas Metering Analyzer Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-159 | USD_ - Foundation for Starting Air Compressor (electric) Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-159 | USD_ - Foundation for Starting Air Compressor (electric) Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-162 | USD_ - Foundation for Aeration Blower unit Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-162 | USD_ - Foundation for Aeration Blower unit Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-163 | USD_ - Foundation for Raw Water Lifting and Transfer Pump Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-163 | USD_ - Foundation for Raw Water Lifting and Transfer Pump Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-164 | USD_ - Foundation for Water Treatment Package Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-164 | USD_ - Foundation for Water Treatment Package Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-166 | USD_ - Foundation for Motor and Diesel Driven Fire Pump Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7207-DWG-166 | USD_ - Foundation for Motor and Diesel Driven Fire Pump Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-098 | USD_ - Fire Water Pump Shelter Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-098 | USD_ - Fire Water Pump Shelter Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-104 | USD_ - WTP Shelter Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-104 | USD_ - WTP Shelter Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-110 | USD_ - Parking Area Shelter Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-110 | USD_ - Parking Area Shelter Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-116 | USD_ - Fuel Oil Purification Shelter Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-116 | USD_ - Fuel Oil Purification Shelter Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-125 | USD_ - Switch Yard Foundation Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.7507-DWG-125 | USD_ - Switch Yard Foundation Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-001 | USD_ - PFD Fuel Oil System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-001 | USD_ - PFD Fuel Oil System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-002 | USD_ - PFD Fuel Gas Sytem | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-002 | USD_ - PFD Fuel Gas Sytem | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-003 | USD_ - PFD Lube Oil System Storage & Transfer Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-003 | USD_ - PFD Lube Oil System Storage & Transfer Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-004 | USD_ - PFD Cooling Water System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-004 | USD_ - PFD Cooling Water System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-005 | USD_ - PFD Compressor Air System # Starting & Control Air | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-005 | USD_ - PFD Compressor Air System # Starting & Control Air | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-006 | USD_ - PFD Water Treatment System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8001-PFD-006 | USD_ - PFD Water Treatment System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-002 | USD_ - Specification for Piling Work | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-002 | USD_ - Specification for Piling Work | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-003 | USD_ - Specification for Structural Steel Material | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-003 | USD_ - Specification for Structural Steel Material | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-004 | USD_ - Standard Specification for Structural Steel Construction | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8003-SPC-004 | USD_ - Standard Specification for Structural Steel Construction | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8003-SPC-010 | USD_ - Specification for Outdoor Grounding & Lightning Protection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8003-SPC-010 | USD_ - Specification for Outdoor Grounding & Lightning Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-001 | USD_ - Datasheet for Pressure Regulator Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-001 | USD_ - Datasheet for Pressure Regulator Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-002 | USD_ - Datasheet for Shutdown/Blowdown & On-Off Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-002 | USD_ - Datasheet for Shutdown/Blowdown & On-Off Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-003 | USD_ - Datasheet for Pressure Safety Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-003 | USD_ - Datasheet for Pressure Safety Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-004 | USD_ - Datasheet for Deluge Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.8004-DTS-004 | USD_ - Datasheet for Deluge Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8004-DTS-043 | USD_ - Datasheet for HVAC FOR Central Control Room | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8004-DTS-043 | USD_ - Datasheet for HVAC FOR Central Control Room | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8005-CAL-001 | USD_ - Calculation for Piling Capacity Design | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8005-CAL-001 | USD_ - Calculation for Piling Capacity Design | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8005-CAL-005 | USD_ - Grounding Calculation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8005-CAL-005 | USD_ - Grounding Calculation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-001 | USD_ - Key Plan Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-001 | USD_ - Key Plan Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-002 | USD_ - Foundation & piling Layout (1 of 4) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-002 | USD_ - Foundation & piling Layout (1 of 4) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-003 | USD_ - Foundation & piling Layout (2 of 4) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-003 | USD_ - Foundation & piling Layout (2 of 4) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-004 | USD_ - Foundation & piling Layout (3 of 4) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-004 | USD_ - Foundation & piling Layout (3 of 4) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-005 | USD_ - Foundation & piling Layout (4 of 4) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-005 | USD_ - Foundation & piling Layout (4 of 4) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-012 | USD_ - Underground plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-012 | USD_ - Underground plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-013 | USD_ - Underground section & detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-013 | USD_ - Underground section & detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-070 | USD_ - Laboratory, Workshop, & Warehouse Building Piling Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-070 | USD_ - Laboratory, Workshop, & Warehouse Building Piling Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-080 | USD_ - Toxic & Hazaerd Waste Storage Building Piling Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-080 | USD_ - Toxic & Hazaerd Waste Storage Building Piling Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-087 | USD_ - Power House Building Piling Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-087 | USD_ - Power House Building Piling Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-097 | USD_ - Fire Water Pump Shelter Piling plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6394716 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-097 | USD_ - Fire Water Pump Shelter Piling plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 396.73 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-103 | USD_ - WTP Shelter Piling plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-103 | USD_ - WTP Shelter Piling plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-109 | USD_ - Parking Area Shelter Piling plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-109 | USD_ - Parking Area Shelter Piling plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-115 | USD_ - Fuel Oil Purification Shelter Piling plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-115 | USD_ - Fuel Oil Purification Shelter Piling plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-167 | USD_ - Pile Test Layout (4 Sheets) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-167 | USD_ - Pile Test Layout (4 Sheets) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-167-02 | USD_ - Pile Test Layout PC Spun Pile | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.8007-DWG-167-02 | USD_ - Pile Test Layout PC Spun Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8007-LAY-013 | USD_ - Lightning and Grounding Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.8007-LAY-013 | USD_ - Lightning and Grounding Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-002 | USD_ - VDR for Pressure Regulator Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-002 | USD_ - VDR for Pressure Regulator Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-003 | USD_ - VDR for Shutdown/Blowdown & On-Off Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-003 | USD_ - VDR for Shutdown/Blowdown & On-Off Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-004 | USD_ - VDR for Pressure Safety Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-004 | USD_ - VDR for Pressure Safety Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-005 | USD_ - VDR for Deluge Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.800F-VDR-005 | USD_ - VDR for Deluge Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.800F-VDR-010 | USD_ - VDR for HVAC | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 127894328 | 127894328 | 127894328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.800F-VDR-010 | USD_ - VDR for HVAC | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7934.47 | 7934.47 | 7934.47 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.800F-VDR-013 | USD_ - VDR Outdoor Grounding & Lightning Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 127894328 | 102315462 | 102315462 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.800F-VDR-013 | USD_ - VDR Outdoor Grounding & Lightning Protection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 7934.48 | 6347.58 | 6347.58 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8103-SPC-008 | USD_ - Specification for Atmospheric Storage Tanks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8103-SPC-008 | USD_ - Specification for Atmospheric Storage Tanks | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-018 | USD_ - Datasheet for Combined Raw & Fire Water Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-018 | USD_ - Datasheet for Combined Raw & Fire Water Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-019 | USD_ - Datasheet for Lube Oil Storage Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-019 | USD_ - Datasheet for Lube Oil Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-020 | USD_ - Datasheet for Lube Oil Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-020 | USD_ - Datasheet for Lube Oil Drain Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-021 | USD_ - Datasheet for Fuel Oil Daily Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-021 | USD_ - Datasheet for Fuel Oil Daily Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-024 | USD_ - Datasheet for Sludge Storage Tanks | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-024 | USD_ - Datasheet for Sludge Storage Tanks | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-028 | USD_ - Datasheet for Cooling Water Maintenance Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8104-DTS-028 | USD_ - Datasheet for Cooling Water Maintenance Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.810F-VDR-004 | USD_ - VDR for Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 11901.71 | 11901.71 | 11901.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.810F-VDR-004 | USD_ - VDR for Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 191841492 | 191841492 | 191841492 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-001 | USD_ - VDR for Pipe, Fitting and Flange | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-001 | USD_ - VDR for Pipe, Fitting and Flange | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-002 | USD_ - VDR for Gate Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3967.23 | 3570.51 | 3570.51 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-002 | USD_ - VDR for Gate Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 63947164 | 57552448 | 57552448 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-003 | USD_ - VDR for Ball Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3967.23 | 3570.51 | 3570.51 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-003 | USD_ - VDR for Ball Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 63947164 | 57552448 | 57552448 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-004 | USD_ - VDR for Bolt and Nuts | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-004 | USD_ - VDR for Bolt and Nuts | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-005 | USD_ - VDR for Gasket | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-005 | USD_ - VDR for Gasket | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-006 | USD_ - VDR for Ball Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 63947164 | 57552448 | 57552448 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-006 | USD_ - VDR for Ball Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.9 | 3967.23 | 3570.51 | 3570.51 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-007 | USD_ - VDR for Special Item | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-007 | USD_ - VDR for Special Item | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-008 | USD_ - VDR for Fire Fighting Equipment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 63947164 | 31973582 | 31973582 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.811F-VDR-008 | USD_ - VDR for Fire Fighting Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.5 | 3967.23 | 1983.62 | 1983.62 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-001 | USD_ - Datasheet Maual Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-001 | USD_ - Datasheet Maual Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-002 | USD_ - Datasheet Manual Gate Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-002 | USD_ - Datasheet Manual Gate Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-003 | USD_ - Datasheet Manual Check Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-003 | USD_ - Datasheet Manual Check Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-004 | USD_ - Datasheet Manual Globe Valve | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-004 | USD_ - Datasheet Manual Globe Valve | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-005 | USD_ - Datasheet Special Item - Strainer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-005 | USD_ - Datasheet Special Item - Strainer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-006 | USD_ - Datasheet Special Item - Flexible Hose | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-006 | USD_ - Datasheet Special Item - Flexible Hose | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-007 | USD_ - Datasheet Special Item - Hose Connector | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-007 | USD_ - Datasheet Special Item - Hose Connector | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-008 | USD_ - Datasheet Special Item - Bug Screen | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-008 | USD_ - Datasheet Special Item - Bug Screen | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-009 | USD_ - Datasheet Special Item - Flame Arrester | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-009 | USD_ - Datasheet Special Item - Flame Arrester | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-010 | USD_ - Datasheet Special Item - Automatic Drain (Air Trap) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8144-DTS-010 | USD_ - Datasheet Special Item - Automatic Drain (Air Trap) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-002 | USD_ - Datasheet Special Item | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-002 | USD_ - Datasheet Special Item | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-003 | USD_ - Datasheet Fire Fighting Equipment | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-003 | USD_ - Datasheet Fire Fighting Equipment | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-004 | USD_ - Datasheet for Water Hydrant and Hose Cabinet | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-004 | USD_ - Datasheet for Water Hydrant and Hose Cabinet | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-005 | USD_ - Datasheet for Hose Reel (Indoor) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-005 | USD_ - Datasheet for Hose Reel (Indoor) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-006 | USD_ - Datasheet for Foam Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-006 | USD_ - Datasheet for Foam Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-007 | USD_ - Datasheet for Portable Extinguisher (CO2) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-007 | USD_ - Datasheet for Portable Extinguisher (CO2) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-008 | USD_ - Datasheet for Portable Extinguisher (Dry Chemical) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-008 | USD_ - Datasheet for Portable Extinguisher (Dry Chemical) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-009 | USD_ - Datasheet for Gas Supression System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.8904-DTS-009 | USD_ - Datasheet for Gas Supression System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.72 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.900F-VDR-014 | USD_ - VDR Cathodic Protection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.900F-VDR-014 | USD_ - VDR Cathodic Protection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9103-SPC-003 | USD_ - Specification for Water Treatment Package | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9103-SPC-003 | USD_ - Specification for Water Treatment Package | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9104-DTS-032 | USD_ - Datasheet for WTP | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9104-DTS-032 | USD_ - Datasheet for WTP | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.910F-VDR-006 | USD_ - VDR for WTP & WWTP | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 11901.71 | 9521.37 | 9521.37 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.910F-VDR-006 | USD_ - VDR for WTP & WWTP | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 191841492 | 153473194 | 153473194 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9204-DTS-033 | USD_ - Datasheet for WWTP | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.9204-DTS-033 | USD_ - Datasheet for WWTP | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A005-CAL-005 | USD_ - Calculation of Pipe Support Sleeper & Stanchion | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A005-CAL-005 | USD_ - Calculation of Pipe Support Sleeper & Stanchion | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A005-CAL-008 | USD_ - Calculation for Open Drainage System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A005-CAL-008 | USD_ - Calculation for Open Drainage System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-016 | USD_ - Pipe Sleeper Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-016 | USD_ - Pipe Sleeper Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-017 | USD_ - Pipe Stanchion #1 foundation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-017 | USD_ - Pipe Stanchion #1 foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-018 | USD_ - Pipe Stanchion #2 foundation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-018 | USD_ - Pipe Stanchion #2 foundation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-123 | USD_ - Power Engine Platform Foundation Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-123 | USD_ - Power Engine Platform Foundation Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-123-02 | USD_ - Piling Layout Engine Area | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-123-02 | USD_ - Piling Layout Engine Area | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-124 | USD_ - Power Engine Platform Plan and Section | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-124 | USD_ - Power Engine Platform Plan and Section | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-130 | USD_ - Skimming Pond Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-130 | USD_ - Skimming Pond Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-131 | USD_ - Skimming Pond Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-131 | USD_ - Skimming Pond Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-134 | USD_ - Nutralization Pond Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-134 | USD_ - Nutralization Pond Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-135 | USD_ - Nutralization Pond Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-135 | USD_ - Nutralization Pond Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-136 | USD_ - Power Generation Oily Water Pit Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-136 | USD_ - Power Generation Oily Water Pit Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-137 | USD_ - Transformer Oily Water Pit Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-137 | USD_ - Transformer Oily Water Pit Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-138 | USD_ - Fuel Station Oily Water Pit Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.A007-DWG-138 | USD_ - Fuel Station Oily Water Pit Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.A104-DTS-035 | USD_ - Datasheet for Fuel Gas Coalescing Filter (Common) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.A104-DTS-035 | USD_ - Datasheet for Fuel Gas Coalescing Filter (Common) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.A10F-VDR-007 | USD_ - VDR for Filter | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 127894328 | 127894328 | 127894328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.A10F-VDR-007 | USD_ - VDR for Filter | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7934.47 | 7934.47 | 7934.47 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B205-CAL-004 | USD_ - Calculation for Road Pavement | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B205-CAL-004 | USD_ - Calculation for Road Pavement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-008 | USD_ - Road Pavement, Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-008 | USD_ - Road Pavement, Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-009 | USD_ - Road Pavement Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-009 | USD_ - Road Pavement Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-030 | USD_ - Standard Drawing Road & Pavement | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-030 | USD_ - Standard Drawing Road & Pavement | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-064 | USD_ - Control Room Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-064 | USD_ - Control Room Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-065 | USD_ - Control Room Floor Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B207-DWG-065 | USD_ - Control Room Floor Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-066 | USD_ - Control Room Section & Finishing Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-066 | USD_ - Control Room Section & Finishing Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-067 | USD_ - Control Room Door Key Plan & Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-067 | USD_ - Control Room Door Key Plan & Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-068 | USD_ - Control Room Door & Window Detail & Section | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-068 | USD_ - Control Room Door & Window Detail & Section | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-069 | USD_ - Control Room plumbing & toilet | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 396.73 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.B407-DWG-069 | USD_ - Control Room plumbing & toilet | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6394716 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.B523-SPC-004 | USD_ - Specification for Telecommunication | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.B523-SPC-004 | USD_ - Specification for Telecommunication | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.B52F-VDR-021 | USD_ - VDR for Metering | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.B52F-VDR-021 | USD_ - VDR for Metering | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C005-CAL-006 | USD_ - Calculation for Instrument & Electrical Tray Support | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C005-CAL-006 | USD_ - Calculation for Instrument & Electrical Tray Support | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-019 | USD_ - Pipe Support Stanchion Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-019 | USD_ - Pipe Support Stanchion Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-020 | USD_ - Lighting Pole Foundation, Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-020 | USD_ - Lighting Pole Foundation, Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-022 | USD_ - Instrument & Electrical Tray Support Foundation, Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.C007-DWG-022 | USD_ - Instrument & Electrical Tray Support Foundation, Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C217-DWG-012 | USD_ - Instrument Cable Routing Layout including Junction Boxes and Panel Location | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C217-DWG-012 | USD_ - Instrument Cable Routing Layout including Junction Boxes and Panel Location | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C218-LST-004 | USD_ - Instrument & Telecom Cable Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C218-LST-004 | USD_ - Instrument & Telecom Cable Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C21F-VDR-016 | USD_ - VDR for Instrument Cable (for Control, Safety, Fire & Gas, Power & Grounding) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C21F-VDR-016 | USD_ - VDR for Instrument Cable (for Control, Safety, Fire & Gas, Power & Grounding) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C26F-VDR-017 | USD_ - VDR for Instrument Junction Box & Panel | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C26F-VDR-017 | USD_ - VDR for Instrument Junction Box & Panel | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.24 | 3173.79 | 3173.79 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C32F-VDR-018 | USD_ - VDR for Instrument Hook-up Material (Tubing & Fittings) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.C32F-VDR-018 | USD_ - VDR for Instrument Hook-up Material (Tubing & Fittings) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV1000-BOD-001 | USD_ - Review all Civil and Structure spec & Design Basis | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV1000-BOD-001 | USD_ - Review all Civil and Structure spec & Design Basis | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV6203-SPC-006 | USD_ - Standard Specification for Site Preparation,Grading & Fencing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV6203-SPC-006 | USD_ - Standard Specification for Site Preparation,Grading & Fencing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV7007-DWG-016 | USD_ - Standard Drawing Vertical Bracing Connection | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV7007-DWG-016 | USD_ - Standard Drawing Vertical Bracing Connection | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV8003-SPC-005 | USD_ - Standard Specification for Building | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV8003-SPC-005 | USD_ - Standard Specification for Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV8005-CAL-002 | USD_ - Calculation Single Pile Capacity For Steel Pipe Pile | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.CIV8005-CAL-002 | USD_ - Calculation Single Pile Capacity For Steel Pipe Pile | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D007-DWG-014 | USD_ - Fire & Gas Detector Location Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D007-DWG-014 | USD_ - Fire & Gas Detector Location Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00C-DTS-013 | USD_ - Datasheet for Indoor Fire & Gas Detection System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00C-DTS-013 | USD_ - Datasheet for Indoor Fire & Gas Detection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00C-DTS-014 | USD_ - Datasheet for Outdoor Fire & Gas Detection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00C-DTS-014 | USD_ - Datasheet for Outdoor Fire & Gas Detection System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00F-VDR-014 | USD_ - VDR for Fire & Gas Detection System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 3967.24 | 3173.79 | 3173.79 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.D00F-VDR-014 | USD_ - VDR for Fire & Gas Detection System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 63947164 | 51157731 | 51157731 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.D207-DWG-057-01 | USD_ - Waste Storage Buliding Plan View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.D207-DWG-057-01 | USD_ - Waste Storage Buliding Plan View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.D207-DWG-057-02 | USD_ - Waste Storage Buliding Elevation View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.D207-DWG-057-02 | USD_ - Waste Storage Buliding Elevation View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E003-SPC-003 | USD_ - Telecommunication Specifications | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E003-SPC-003 | USD_ - Telecommunication Specifications | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E007-DWG-020 | USD_ - Telecommunication Cable Routing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E007-DWG-020 | USD_ - Telecommunication Cable Routing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E00F-VDR-019 | USD_ - VDR for Telecommunication & Security System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E00F-VDR-019 | USD_ - VDR for Telecommunication & Security System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E00F-VDR-020 | USD_ - VDR for Telecommunication Cable and FO Cable | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.E00F-VDR-020 | USD_ - VDR for Telecommunication Cable and FO Cable | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.24 | 3967.24 | 3967.24 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E107-DWG-071 | USD_ - Laboratory, Workshop, & Warehouse Building Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E107-DWG-071 | USD_ - Laboratory, Workshop, & Warehouse Building Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-072 | USD_ - Laboratory, Workshop, & Warehouse Building Column Plan, Portal Frame Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-072 | USD_ - Laboratory, Workshop, & Warehouse Building Column Plan, Portal Frame Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-073 | USD_ - Laboratory, Workshop, & Warehouse Building Roof Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 396.73 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-073 | USD_ - Laboratory, Workshop, & Warehouse Building Roof Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0 | 6394716 | 0 | 0 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-074 | USD_ - Laboratory, Workshop, & Warehouse Building Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-074 | USD_ - Laboratory, Workshop, & Warehouse Building Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-074-02 | USD_ - Workshop Warehouse Building Elevation View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-074-02 | USD_ - Workshop Warehouse Building Elevation View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-075 | USD_ - Laboratory, Workshop, & Warehouse Building Floor Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-075 | USD_ - Laboratory, Workshop, & Warehouse Building Floor Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-076 | USD_ - Laboratory, Workshop, & Warehouse Building Framing & Roof Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E207-DWG-076 | USD_ - Laboratory, Workshop, & Warehouse Building Framing & Roof Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-077 | USD_ - Laboratory, Workshop, & Warehouse Building Section & Finishing Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-077 | USD_ - Laboratory, Workshop, & Warehouse Building Section & Finishing Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-078 | USD_ - Laboratory, Workshop, & Warehouse Building Door Key Plan & Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-078 | USD_ - Laboratory, Workshop, & Warehouse Building Door Key Plan & Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-079 | USD_ - Laboratory, Workshop, & Warehouse Building Door & Window Detail & Section | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.E407-DWG-079 | USD_ - Laboratory, Workshop, & Warehouse Building Door & Window Detail & Section | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE1000-BOD-001 | USD_ - Electrical Design Basis | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE1000-BOD-001 | USD_ - Electrical Design Basis | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE5615-CAL-004 | USD_ - AC & DC UPS and Battery Sizing | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE5615-CAL-004 | USD_ - AC & DC UPS and Battery Sizing | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE6304-DTS-009 | USD_ - Data Sheet Cable And Wires | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1E.00 | Engineering - UNSPECIFIED | USD.ELE6304-DTS-009 | USD_ - Data Sheet Cable And Wires | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F005-CAL-016 | USD_ - Calculation for Power House | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F005-CAL-016 | USD_ - Calculation for Power House | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F107-DWG-088 | USD_ - Power House Building Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F107-DWG-088 | USD_ - Power House Building Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-01 | USD_ - Power House Framing Plan, Section and Detail (1 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-01 | USD_ - Power House Framing Plan, Section and Detail (1 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-02 | USD_ - Power House Framing Plan, Section and Detail (2 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-02 | USD_ - Power House Framing Plan, Section and Detail (2 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-03 | USD_ - Power House Framing Plan, Section and Detail (3 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-03 | USD_ - Power House Framing Plan, Section and Detail (3 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-04 | USD_ - Power House Framing Plan, Section and Detail (4 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-04 | USD_ - Power House Framing Plan, Section and Detail (4 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-05 | USD_ - Power House Framing Plan, Section and Detail (5 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-05 | USD_ - Power House Framing Plan, Section and Detail (5 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-06 | USD_ - Power House Framing Plan, Section and Detail (6 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-06 | USD_ - Power House Framing Plan, Section and Detail (6 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-07 | USD_ - Power House Framing Plan, Section and Detail (7 of 7) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-089-07 | USD_ - Power House Framing Plan, Section and Detail (7 of 7) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-090 | USD_ - Power House Building Roof Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-090 | USD_ - Power House Building Roof Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-091 | USD_ - Power House Building Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-091 | USD_ - Power House Building Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-092 | USD_ - Power House Building Floor Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-092 | USD_ - Power House Building Floor Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-093 | USD_ - Power House Building Framing & Roof Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-093 | USD_ - Power House Building Framing & Roof Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-094 | USD_ - Power House Building Section & Finishing Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F207-DWG-094 | USD_ - Power House Building Section & Finishing Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F407-DWG-095 | USD_ - Power House Building Door Key Plan & Schedule | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F407-DWG-095 | USD_ - Power House Building Door Key Plan & Schedule | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F407-DWG-096 | USD_ - Power House Building Door & Window Detail & Section | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.F407-DWG-096 | USD_ - Power House Building Door & Window Detail & Section | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-036 | USD_ - Administration Building Plan View, Arch | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-036 | USD_ - Administration Building Plan View, Arch | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-037 | USD_ - Administration Building Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-037 | USD_ - Administration Building Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-039 | USD_ - Administration Building Framing & Roof Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.G207-DWG-039 | USD_ - Administration Building Framing & Roof Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.I207-DWG-028 | USD_ - Guard House Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.I207-DWG-028 | USD_ - Guard House Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.I207-DWG-029 | USD_ - Guard House Floor Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.I207-DWG-029 | USD_ - Guard House Floor Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.INS7004-DTS-013 | USD_ - Datasheet for Gas Chromatograph Analyzer | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.INS7004-DTS-013 | USD_ - Datasheet for Gas Chromatograph Analyzer | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.INS7007-DWG-016 | USD_ - Instrument Level Sketch | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1I.00 | Engineering - UNSPECIFIED | USD.INS7007-DWG-016 | USD_ - Instrument Level Sketch | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-LST-001 | USD_ - P&ID Drawing Index | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-LST-001 | USD_ - P&ID Drawing Index | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-01 | USD_ - P&ID of Legend & Symbol | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-01 | USD_ - P&ID of Legend & Symbol | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-02 | USD_ - P&ID of Legend & Symbol | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-02 | USD_ - P&ID of Legend & Symbol | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-03 | USD_ - P&ID of Legend & Symbol | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-03 | USD_ - P&ID of Legend & Symbol | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-04 | USD_ - P&ID of Legend & Symbol | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-001-04 | USD_ - P&ID of Legend & Symbol | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-01 | USD_ - P&ID of HSD Fuel Oil System - Receiving Facility | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-01 | USD_ - P&ID of HSD Fuel Oil System - Receiving Facility | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-02 | USD_ - P&ID of HSD Fuel Oil System - Purification Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-02 | USD_ - P&ID of HSD Fuel Oil System - Purification Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-03 | USD_ - P&ID of HSD Fuel Oil System - Day Tank & Transfer Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-03 | USD_ - P&ID of HSD Fuel Oil System - Day Tank & Transfer Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-04 | USD_ - P&ID of HSD Fuel Oil System - FO Supply Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-04 | USD_ - P&ID of HSD Fuel Oil System - FO Supply Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-05 | USD_ - P&ID of HSD Fuel Oil System - Pilot Oil System | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-05 | USD_ - P&ID of HSD Fuel Oil System - Pilot Oil System | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-06 | USD_ - P&ID of HSD Fuel Oil System - Clean Oil & Pilot Oil Drain With Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-06 | USD_ - P&ID of HSD Fuel Oil System - Clean Oil & Pilot Oil Drain With Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-07 | USD_ - P&ID of HSD Fuel Oil System - Dirty Oil Drain Tank With Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-002-07 | USD_ - P&ID of HSD Fuel Oil System - Dirty Oil Drain Tank With Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-01 | USD_ - P&ID of Engine Generator Unit Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-01 | USD_ - P&ID of Engine Generator Unit Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-02 | USD_ - P&ID of Engine Generator Unit Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-02 | USD_ - P&ID of Engine Generator Unit Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-03 | USD_ - P&ID of Engine Generator Unit Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-03 | USD_ - P&ID of Engine Generator Unit Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-04 | USD_ - P&ID of Engine Generator Unit Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-04 | USD_ - P&ID of Engine Generator Unit Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-05 | USD_ - P&ID of Engine Generator Unit Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-05 | USD_ - P&ID of Engine Generator Unit Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-06 | USD_ - P&ID of Engine Generator Unit - LO System - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-06 | USD_ - P&ID of Engine Generator Unit - LO System - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-07 | USD_ - P&ID of Engine Generator Unit - LO System - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-07 | USD_ - P&ID of Engine Generator Unit - LO System - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-08 | USD_ - P&ID of Engine Generator Unit - LO System - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-08 | USD_ - P&ID of Engine Generator Unit - LO System - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-09 | USD_ - P&ID of Engine Generator Unit - LO System - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-09 | USD_ - P&ID of Engine Generator Unit - LO System - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-10 | USD_ - P&ID of Engine Generator Unit - LO System - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-10 | USD_ - P&ID of Engine Generator Unit - LO System - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-11 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-11 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-12 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-12 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-13 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-13 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-14 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-14 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-15 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-15 | USD_ - P&ID of Engine Generator Unit - LO Purifier Unit - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-16 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-16 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-17 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-17 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-18 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-18 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-19 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-19 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-20 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-20 | USD_ - P&ID of Engine Generator Unit - Cooling Water System - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-21 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-21 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-22 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-22 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-23 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-23 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-24 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-24 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-25 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-25 | USD_ - P&ID of Engine Generator Unit - Gas Valve Unit Engine - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-26 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-26 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-27 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-27 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-28 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-28 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-29 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-29 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-30 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-30 | USD_ - P&ID of Engine Generator Unit - HT CW Expansion Tank - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-31 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-31 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-32 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-32 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-33 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-33 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-34 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-34 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-35 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-35 | USD_ - P&ID of Engine Generator Unit - LT CW Expansion Tank - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-36 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-36 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-37 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-37 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-38 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-38 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-39 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-39 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-40 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-40 | USD_ - P&ID of Engine Generator Unit - Nozzle Cooling Water Unit - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-41 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-41 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-42 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-42 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-43 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-43 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-44 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-44 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-45 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-45 | USD_ - P&ID of Engine Generator Unit - Jacket Water Pre-Heater - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-46 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-46 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-47 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-47 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-48 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-48 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-49 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-49 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-50 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-003-50 | USD_ - P&ID of Engine Generator Unit - HT & LT Radiator - Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-01 | USD_ - P&ID of Engine Generator Unit - LO Unloading Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-01 | USD_ - P&ID of Engine Generator Unit - LO Unloading Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-02 | USD_ - P&ID of Engine Generator Unit - Portable Unloading Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-02 | USD_ - P&ID of Engine Generator Unit - Portable Unloading Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-03 | USD_ - P&ID of Engine Generator Unit - LO Storage Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-03 | USD_ - P&ID of Engine Generator Unit - LO Storage Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-04 | USD_ - P&ID of Engine Generator Unit - LO Transfer Pump Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-04 | USD_ - P&ID of Engine Generator Unit - LO Transfer Pump Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-05 | USD_ - P&ID of Engine Generator Unit - LO Drain Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-05 | USD_ - P&ID of Engine Generator Unit - LO Drain Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-06 | USD_ - P&ID of Engine Generator Unit LO Potable (Used) Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-004-06 | USD_ - P&ID of Engine Generator Unit LO Potable (Used) Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-005 | USD_ - P&ID of Compressed Air System-Starting & Control Air | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-005 | USD_ - P&ID of Compressed Air System-Starting & Control Air | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-006-01 | USD_ - P&ID of Fuel Gas System - Metering, Pressure Reducing & Filtration | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-006-01 | USD_ - P&ID of Fuel Gas System - Metering, Pressure Reducing & Filtration | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-006-02 | USD_ - P&ID of Compressed Air System-Service Air Compressor | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-006-02 | USD_ - P&ID of Compressed Air System-Service Air Compressor | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-01 | USD_ - P&ID of Water Treatment System - Pre-Treatment & Raw Water Storage Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-01 | USD_ - P&ID of Water Treatment System - Pre-Treatment & Raw Water Storage Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-02 | USD_ - P&ID of Water Treatment System - Reverse Osmosis Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-02 | USD_ - P&ID of Water Treatment System - Reverse Osmosis Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-03 | USD_ - P&ID of Water Treatment System - Demineralization Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-03 | USD_ - P&ID of Water Treatment System - Demineralization Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-04 | USD_ - P&ID of Water Treatment System - Cooling Water Maintenance Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-04 | USD_ - P&ID of Water Treatment System - Cooling Water Maintenance Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-05 | USD_ - P&ID of Water Treatment System - Cooling Water Maintenance Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-007-05 | USD_ - P&ID of Water Treatment System - Cooling Water Maintenance Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-008-01 | USD_ - P&ID of Fire Water System - Fire Water Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-008-01 | USD_ - P&ID of Fire Water System - Fire Water Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-008-02 | USD_ - P&ID of Fire Water System - Fire Water Ring | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-008-02 | USD_ - P&ID of Fire Water System - Fire Water Ring | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-01 | USD_ - P&ID of Waste Water System - Wwtp - Sanitary & Storm Water | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-01 | USD_ - P&ID of Waste Water System - Wwtp - Sanitary & Storm Water | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-02 | USD_ - P&ID of Waste Water System - Wwtp - Oily Water Separator Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-02 | USD_ - P&ID of Waste Water System - Wwtp - Oily Water Separator Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-03 | USD_ - P&ID of Waste Water System - Wwtp - Neutralization Unit | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-009-03 | USD_ - P&ID of Waste Water System - Wwtp - Neutralization Unit | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-01 | USD_ - P&ID of Engine Building Ventilation Engine A | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-01 | USD_ - P&ID of Engine Building Ventilation Engine A | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-02 | USD_ - P&ID of Engine Building Ventilation Engine B | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-02 | USD_ - P&ID of Engine Building Ventilation Engine B | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-03 | USD_ - P&ID of Engine Building Ventilation Engine C | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-03 | USD_ - P&ID of Engine Building Ventilation Engine C | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-04 | USD_ - P&ID of Engine Building Ventilation Engine D | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-04 | USD_ - P&ID of Engine Building Ventilation Engine D | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-05 | USD_ - P&ID of Engine Building Ventilation Engine E | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.L001-PID-010-05 | USD_ - P&ID of Engine Building Ventilation Engine E | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M107-DWG-081 | USD_ - Toxic & Hazaerd Waste Storage Building Foundation Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M107-DWG-081 | USD_ - Toxic & Hazaerd Waste Storage Building Foundation Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-082 | USD_ - Toxic & Hazaerd Waste Storage Building Column Plan, Portal Frame Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-082 | USD_ - Toxic & Hazaerd Waste Storage Building Column Plan, Portal Frame Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-083 | USD_ - Toxic & Hazaerd Waste Storage Building Roof Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-083 | USD_ - Toxic & Hazaerd Waste Storage Building Roof Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-084 | USD_ - Toxic & Hazaerd Waste Storage Building Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394716 | 5115773 | 5115773 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-084 | USD_ - Toxic & Hazaerd Waste Storage Building Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.73 | 317.38 | 317.38 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-085 | USD_ - Toxic & Hazaerd Waste Storage Building Floor Plan, Section & Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-085 | USD_ - Toxic & Hazaerd Waste Storage Building Floor Plan, Section & Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-086 | USD_ - Toxic & Hazaerd Waste Storage Building Framing & Roof Plan | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.M207-DWG-086 | USD_ - Toxic & Hazaerd Waste Storage Building Framing & Roof Plan | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC1000-BOD-001 | USD_ - Basic of Design | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.71 | 396.71 | 396.71 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC1000-BOD-001 | USD_ - Basic of Design | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394718 | 6394718 | 6394718 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC6203-SPC-006 | USD_ - Specification for Overhead Crane and Hoist | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC6203-SPC-006 | USD_ - Specification for Overhead Crane and Hoist | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC6204-DTS-056 | USD_ - Datasheet for Crane Workshop Building | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.MEC6204-DTS-056 | USD_ - Datasheet for Crane Workshop Building | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.N006-RPT-003 | USD_ - Line Sizing & Hydraulic Report | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 396.71 | 317.37 | 317.37 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.N006-RPT-003 | USD_ - Line Sizing & Hydraulic Report | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 0.8 | 6394718 | 5115774 | 5115774 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.N008-LST-001 | USD_ - Line List | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.N008-LST-001 | USD_ - Line List | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z127-DWG-048 | USD_ - Mosque Plan View, arch | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z127-DWG-048 | USD_ - Mosque Plan View, arch | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z127-DWG-049 | USD_ - Mosque Plan View, Section and Elevation | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z127-DWG-049 | USD_ - Mosque Plan View, Section and Elevation | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z147-DWG-053 | USD_ - Toilet and Ablution Building Plan View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z147-DWG-053 | USD_ - Toilet and Ablution Building Plan View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z147-DWG-054 | USD_ - Toilet and Ablution Building Elevation View | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z147-DWG-054 | USD_ - Toilet and Ablution Building Elevation View | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z207-DWG-010 | USD_ - Parking Area Pavement, Plan, Section and Detail | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z207-DWG-010 | USD_ - Parking Area Pavement, Plan, Section and Detail | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z207-DWG-011 | USD_ - Parking Area Pavement Layout | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.73 | 396.73 | 396.73 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1C.00 | Engineering - UNSPECIFIED | USD.Z207-DWG-011 | USD_ - Parking Area Pavement Layout | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z214-DTS-017 | USD_ - Datasheet for Fire Water Pump & Jockey Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z214-DTS-017 | USD_ - Datasheet for Fire Water Pump & Jockey Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394717 | 6394717 | 6394717 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z21F-VDR-003 | USD_ - VDR for FW Pump | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 3967.23 | 3967.23 | 3967.23 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z21F-VDR-003 | USD_ - VDR for FW Pump | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 63947164 | 63947164 | 63947164 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z30F-VDR-012 | USD_ - VDR for Crane & Hoist | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 127894328 | 127894328 | 127894328 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z30F-VDR-012 | USD_ - VDR for Crane & Hoist | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 7934.47 | 7934.47 | 7934.47 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z30F-VDR-014 | USD_ - VDR for Field Erected Tank | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.Z30F-VDR-014 | USD_ - VDR for Field Erected Tank | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.xxx | USD_ - 3D Model (SP3D) | USD | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 396.72 | 396.72 | 396.72 | 0 | 0 |  | 0
P-15-K-062 | PLTG-MG Mobile PP Nias | C-07-17-CRTY01-003 | Contract Agreement No.0372.PJ/DAN.02.01/DIR/2017 for Mobile Power Plant Nias (25 MW) between PT PLN (Persero) with Consortium PT. Tripatra Engineers and Constructors - PT. Prastiwahyu Trimitra Engineering | P.4A6.04.90.06.3.EX1M.00 | Engineering - UNSPECIFIED | USD.xxx | USD_ - 3D Model (SP3D) | IDR | 400033218 | PT.TRIPATRA ENGINEERS&CONSTRUCTORS | 1 | 2019 | 20190206091459 | 1 | 6394716 | 6394716 | 6394716 | 0 | 0 |  | 0
[16 empty] | 208966424780.5217 | 194536138089.9426 | 14430286690.58 | 1090 | 0 | 158749023501.1704
[15 empty] | 221065425687 | 208946069612 | 194518423393 | 14427646219 |  |  | 158682624326
[16 empty] | 213553476641 | 208946069612 | 4607407029
[15 empty] | 12119356075 |  | 208946069612
223373715831